## Sheet1
Address |  |  | Location | Status | Actual Start | Actual Completion | Hard Surface Start | Hard Surface Complete | Soft Surface Start | Soft Surface Complete
ALEXANDER ST | 2308 | ALEXANDER ST | 40-01-407-014 | Completed | 2024-09-11 | 2024-10-11 | 2024-09-11 | 2024-09-16 | 2024-10-11 | 2024-10-11
ALPHA WAY | 2937 | ALPHA WAY | 47-33-101-018 | Completed | 2024-09-16 | 2024-10-11 | 2024-09-16 | 2024-09-18 | 2024-10-11 | 2024-10-11
ARLINGTON AVE | 1717 | ARLINGTON AVE | 41-08-202-021 | Soft Surface needed | 2024-09-13 |  | 2024-09-13 | 2024-10-07
AVENUE A | 1209 | AVENUE A | 40-12-276-040 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
AVENUE A | 1819 | AVENUE A | 40-01-481-015 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
BALDWIN BLVD | 5406 | BALDWIN BLVD | 46-26-479-010 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
BALDWIN BLVD | 5610 | BALDWIN BLVD | 46-26-428-022 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
BARNEY AVE | 1024 | BARNEY AVE | 40-14-365-013 | Completed | 2024-09-10 | 2024-09-23 | 2024-09-10 | 2024-09-10 | 2024-09-23 | 2024-09-23
BEECHWOOD DR | 2316 | BEECHWOOD DR | 41-05-410-010 | Soft Surface needed | 2024-09-13 |  | 2024-09-13 | 2024-09-19
BEECHWOOD DR | 2317 | BEECHWOOD DR | 41-05-428-013 | Soft Surface needed | 2024-09-13 |  | 2024-09-13 | 2024-10-12
BEGOLE ST | 2954 | BEGOLE ST | 40-02-352-003 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-30 | 2024-10-08 | 2024-10-08
BEGOLE ST | 3102 | BEGOLE ST | 40-02-351-015 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-09-26
BIRCHCREST DR | 4915 | BIRCHCREST DR | 46-35-104-020 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
BRANCH RD | 2008 | BRANCH RD | 41-04-383-004 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BRANCH RD | 2016 | BRANCH RD | 41-04-383-001 | Completed | 2024-09-18 | 2024-10-02 | 2024-09-18 | 2024-09-19 | 2024-10-02 | 2024-10-02
BRENTWOOD DR | 3315 | BRENTWOOD DR | 40-14-160-010 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
BRENTWOOD DR | 3720 | BRENTWOOD DR | 40-14-154-002 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
BREWSTER AVE | 3406 | BREWSTER AVE | 41-09-209-022 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BREWSTER AVE | 3426 | BREWSTER AVE | 41-09-209-005 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BREWSTER AVE | 3430 | BREWSTER AVE | 41-09-209-006 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BROWNELL BLVD | 2201 | BROWNELL BLVD | 40-02-327-044 | Completed | 2024-09-10 | 2024-10-07 | 2024-09-10 | 2024-09-10 | 2024-10-07 | 2024-10-07
BROWNELL BLVD | 2419 | BROWNELL BLVD | 40-02-327-050 | Soft Surface needed | 2024-10-01 |  | 2024-10-01 | 2024-10-07
BROWNELL BLVD | 2620 | BROWNELL BLVD | 40-02-178-010 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
BROWNELL BLVD | 2632 | BROWNELL BLVD | 40-02-178-008 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
BROWNELL BLVD | 2714 | BROWNELL BLVD | 40-02-178-001 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
BROWNELL BLVD | 2719 | BROWNELL BLVD | 40-02-160-027 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
BROWNELL BLVD | 3326 | BROWNELL BLVD | 40-02-126-002 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-09
BROWNELL BLVD | 4014 | BROWNELL BLVD | 46-35-328-033 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-09
BROWNELL BLVD | 4026 | BROWNELL BLVD | 46-35-328-029 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-09
BROWNELL BLVD | 4105 | BROWNELL BLVD | 46-35-327-022 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
BUCKINGHAM AVE | 415 | BUCKINGHAM AVE | 41-29-126-019 | No restoration work needed; door hanger left 9/24/24
BUCKINGHAM AVE | 601 | BUCKINGHAM AVE | 41-29-201-033 | No restoration work needed; door hanger left 9/11/24
CHATHAM DR | 1416 | CHATHAM DR | 46-26-251-016 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
CHEYENNE AVE | 3810 | CHEYENNE AVE | 41-29-227-010 | Soft Surface needed | 2024-10-11 |  | 2024-10-11 | 2024-10-11
CHEYENNE AVE | 3814 | CHEYENNE AVE | 41-29-227-011 | No restoration work needed; door hanger left 10/2/24
CHURCHILL AVE | 2521 | CHURCHILL AVE | 41-05-481-031 | Completed | 2024-09-18 | 2024-10-02 | 2024-09-18 | 2024-09-18 | 2024-10-02 | 2024-10-02
CIRCLE DR | 3417 | CIRCLE DR | 41-20-452-007 | No restoration work needed; door hanger left 9/11/24
CLAIRMONT ST | 3814 | CLAIRMONT ST | 40-22-278-032 | Soft Surface needed | 2024-09-06 |  | 2024-09-06 | 2024-09-09
CLAIRMONT ST | 3913 | CLAIRMONT ST | 40-22-280-006 | Soft Surface needed | 2024-09-06 |  | 2024-09-06 | 2024-09-09
CLIO RD | 2637 | CLIO RD | 40-02-151-010 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
CLIO RD | 3221 | CLIO RD | 40-02-106-004 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
CLOVERLAWN DR | 4702 | CLOVERLAWN DR | 46-35-130-006 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
COLONIAL DR | 6802 | COLONIAL DR | 46-26-205-009 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-25 | 2024-10-08 | 2024-10-08
COPEMAN BLVD | 611 | COPEMAN BLVD | 40-12-109-008 | Soft Surface needed | 2024-09-20 |  | 2024-09-20 | 2024-09-26
CRAPO ST | 612 | CRAPO ST | 41-07-476-012 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-09-19
DARYLL DR | 6514 | DARYLL DR | 46-26-230-030 | Completed | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-09-30 | Not needed
DARYLL DR | 7005 | DARYLL DR | 46-26-226-007 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
DARYLL DR | 7014 | DARYLL DR | 46-26-227-004 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
DELAWARE AVE | 3151 | DELAWARE AVE | 41-04-326-015 | No restoration work needed; door hanger left 10/4/24
DELAWARE AVE | 3227 | DELAWARE AVE | 41-04-327-006 | No restoration work needed; door hanger left 10/4/24
DUPONT ST | 5905 | DUPONT ST | 46-26-429-028 | Completed | 2024-09-25 | 2024-10-02 | 2024-09-25 | 2024-09-25 | 2024-10-02 | 2024-10-02
E BUNDY AVE | 1200 | E BUNDY AVE | 47-30-227-045 | Soft Surface needed | 2024-09-18 |  | 2024-09-18 | 2024-09-18
E CARPENTER RD | 414 | E CARPENTER RD | 46-25-226-055 | Completed | 2024-09-12 | 2024-10-01 | 2024-09-12 | 2024-10-01 | 2024-10-01 | 2024-10-01
E DARTMOUTH ST | 614 | E DARTMOUTH ST | 40-01-280-006 | Soft Surface needed | 2024-09-11 |  | 2024-09-11 | 2024-09-16
E DAYTON ST | 315 | E DAYTON ST | 40-01-402-013 | Completed | 2024-09-30 | 2024-10-03 | 2024-09-30 | 2024-10-03 | Not needed
E DAYTON ST | 626 | E DAYTON ST | 40-01-430-008 | Soft Surface needed | 2024-09-30 |  | 2024-09-30 | 2024-10-07
E HAMILTON AVE | 151 | E HAMILTON AVE | 40-01-411-019 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 152 | E HAMILTON AVE | 40-01-415-001 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 301 | E HAMILTON AVE | 40-01-413-011 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 529 | E HAMILTON AVE | 40-01-433-021 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-10-03 | 2024-10-03 | 2024-10-03
E JAMIESON ST | 626 | E JAMIESON ST | 40-01-231-020 | Completed | 2024-09-11 | 2024-10-02 | 2024-09-11 | 2024-09-16 | 2024-10-02 | 2024-10-02
E NINTH ST | 814 | E NINTH ST | 41-18-284-007 | Completed | 2024-09-17 | 2024-09-27 | 2024-09-17 | 2024-09-27 | 2024-09-20 | 2024-09-20
E NINTH ST | 818 | E NINTH ST | 41-18-284-008 | Completed | 2024-09-18 | 2024-09-27 | 2024-09-18 | 2024-09-27 | 2024-09-20 | 2024-09-20
E PASADENA AVE | 743 | E PASADENA AVE | 47-31-354-033 | No restoration work needed; door hanger left 10/1/24 | Appears city repaired sidewalk
E PIERSON RD | 313 | E PIERSON RD | 46-25-455-018 | Completed | 2024-09-10 | 2024-10-02 | 2024-09-10 | 2024-09-10 | 2024-10-02 | 2024-10-02
E PIERSON RD | 410 | E PIERSON RD | 46-36-226-007 | Completed | 2024-09-10 | 2024-10-02 | 2024-09-10 | 2024-09-10 | 2024-10-02 | 2024-10-24
E PIERSON RD | 1133 | E PIERSON RD | 47-30-462-030 | Soft Surface needed | 2024-09-10 |  | 2024-09-10 | 2024-09-10
E SECOND ST | 627 | E SECOND ST | 41-07-451-019 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
E STEWART AVE | 129 | E STEWART AVE | 46-36-255-025 | No restoration work needed; door hanger left 10/8/24
E THIRD ST | 714 | E THIRD ST | 41-18-207-004 | Soft Surface needed | 2024-09-13 |  | 2024-09-13 | 2024-10-07
E WITHERBEE ST | 302 | E WITHERBEE ST | 40-01-454-001 | Soft Surface needed | 2024-09-30 |  | 2024-09-30 | 2024-10-03
E WITHERBEE ST | 306 | E WITHERBEE ST | 40-01-455-004 | Soft Surface needed | 2024-09-30 |  | 2024-09-30 | 2024-10-07
E WOOD ST | 470 | E WOOD ST | 40-12-276-063 | Soft Surface needed | 2024-09-20 |  | 2024-09-20 | 2024-09-26
EASTHAMPTON DR | 3620 | EASTHAMPTON DR | 41-16-229-005 | No restoration work found; door hanger left 10/10/24 | Blue paint from COF that says sidewalk settling is not from SLE work
EASTHAMPTON DR | 3719 | EASTHAMPTON DR | 41-16-228-030 | Soft Surface needed | 2024-10-11 |  | 2024-10-11 | 2024-10-11
EUCLID AVE | 1613 | EUCLID AVE | 40-12-105-030 | Completed | 2024-09-13 | 2024-10-02 | 2024-09-13 | 2024-09-18 | 2024-10-02 | 2024-10-02
FIRST AVE | 411 | FIRST AVE | 40-13-226-009 | Soft Surface needed | 2024-09-16 |  | 2024-09-16 | 2024-09-18
FISK DR | 806 | FISK DR | 41-07-117-010 | Soft Surface needed | 2024-09-20 |  | 2024-09-20 | 2024-10-11
FLEMING RD | 3905 | FLEMING RD | 46-35-380-033 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
FLEMING RD | 5719 | FLEMING RD | 46-26-331-039 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
FLEMING RD | 6505 | FLEMING RD | 46-26-177-018 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-25 | 2024-10-08 | 2024-10-08
FRAZER ST | 3906 | FRAZER ST | 40-15-427-004 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
FREMONT ST | 608 | FREMONT ST | 40-11-378-003 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
FREMONT ST | 907 | FREMONT ST | 40-11-304-025 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
FROST ST | 721 | FROST ST | 40-13-102-014 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-09-20
GARLAND ST | 1115 | GARLAND ST | 40-12-258-025 | Hard surface needed | 2024-09-25 |  | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
GIBSON ST | 2310 | GIBSON ST | 40-14-478-019 | Completed | 2024-09-11 | 2024-10-03 | 2024-09-11 | 2024-09-20 | 2024-10-03 | 2024-10-03
GIBSON ST | 2602 | GIBSON ST | 40-14-454-027 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
GLENN AVE | 5918 | GLENN AVE | 46-26-427-002 | Completed | 2024-09-25 | 2024-10-02 | 2024-09-25 | 2024-09-25 | 2024-10-02 | 2024-10-02
GRATIOT AVE | 3710 | GRATIOT AVE | 40-14-157-019 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-02
GRATIOT AVE | 3722 | GRATIOT AVE | 40-14-157-016 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-24 | 2024-10-03 | 2024-10-03
GREENLAWN DR | 4617 | GREENLAWN DR | 46-35-130-032 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-30 | 2024-10-08 | 2024-10-08
HILLCREST AVE | 2702 | HILLCREST AVE | 41-20-253-007 | No restoration work needed; door hanger left 9/9/24
HILLCREST AVE | 2721 | HILLCREST AVE | 41-20-254-010 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
HOLLY AVE | 3833 | HOLLY AVE | 41-04-476-081 | Soft Surface needed | 2024-09-16 |  | 2024-09-16 | 2024-09-18
HUBBARD AVE | 711 | HUBBARD AVE | 40-14-305-003 | No restoration work needed; door hanger left 9/23/24
HUBBARD AVE | 730 | HUBBARD AVE | 40-14-301-022 | Soft Surface needed | 2024-09-23 |  | 2024-09-23 | 2024-09-27
HUGGINS ST | 3807 | HUGGINS ST | 47-33-452-033 | Soft Surface needed | 2024-09-23 |  | 2024-09-23 | 2024-09-23
ILLINOIS AVE | 1405 | ILLINOIS AVE | 41-08-103-026 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-09-19
IVANHOE AVE | 3818 | IVANHOE AVE | 41-09-231-005 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
JOSEPHINE ST | 602 | JOSEPHINE ST | 40-01-353-017 | Hard surface needed | 2024-09-25 |  | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
JOYNER ST | 3820 | JOYNER ST | 40-15-432-042 | Completed | 2024-09-13 | 2024-10-11 | 2024-09-13 | 2024-10-02 | 2024-10-11 | 2024-10-11
KANSAS AVE | 1706 | KANSAS AVE | 41-08-185-002 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-09-19
KELLAR AVE | 2414 | KELLAR AVE | 40-02-309-006 | Soft Surface needed | 2024-09-12 |  | 2024-09-12 | 2024-09-16
KELLAR AVE | 2905 | KELLAR AVE | 40-02-109-029 | Completed | 2024-09-09 | 2024-10-02 | 2024-09-09 | 2024-09-09 | 2024-10-02 | 2024-10-02
KELLAR AVE | 4207 | KELLAR AVE | 46-35-304-013 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
KELLAR AVE | 4225 | KELLAR AVE | 46-35-304-010 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
KIRKWOOD LN | 3209 | KIRKWOOD LN | 40-02-126-038 | No restoration work needed; door hanger left 10/2/24 | It was determined road patch was not related to SLE; it was CtoC
KUMMER ST | 804 | KUMMER ST | 40-14-426-018 | Completed | 2024-09-12 | 2024-09-27 | 2024-09-12 | 2024-09-27 | 2024-09-18 | 2024-09-18
LAKE FOREST DR | 1421 | LAKE FOREST DR | 46-35-252-006 | No restoration work needed; door hanger left 10/3/24 | Appears the city may have replaced the sidewalk
LAPEER RD | 1109 | LAPEER RD | 41-18-276-003 | Completed | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-20 | 2024-09-23 | 2024-09-23
LAPEER RD | 1113 | LAPEER RD | 41-18-276-004 | Completed | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-20 | 2024-09-23 | 2024-09-23
LAPEER RD | 2357 | LAPEER RD | 41-17-401-004 | Soft Surface needed | 2024-10-08 |  | 2024-10-08 | 2024-10-12
LARCHMONT ST | 3805 | LARCHMONT ST | 40-22-282-016 | No restoration work needed; door hanger left 9/11/24
LAWNDALE AVE | 2314 | LAWNDALE AVE | 40-02-405-012 | Completed | 2024-09-09 | 2024-10-03 | 2024-09-09 | 2024-09-09 | 2024-10-03 | 2024-10-03
LAWNDALE AVE | 2402 | LAWNDALE AVE | 40-02-405-007 | Completed | 2024-09-09 | 2024-10-03 | 2024-09-09 | 2024-09-09 | 2024-10-03 | 2024-10-03
LAWNDALE AVE | 3701 | LAWNDALE AVE | 46-35-454-033 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-23 | 2024-10-02 | 2024-10-02
LAWNDALE AVE | 4101 | LAWNDALE AVE | 46-35-407-030 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-23 | 2024-10-02 | 2024-10-02
LE ERDA AVE | 3505 | LE ERDA AVE | 46-35-383-027 | Soft Surface needed | 2024-09-19 |  | 2024-09-19 | 2024-10-02
LEVERN ST | 1713 | LEVERN ST | 41-08-226-020 | Completed | 2024-09-19 | 2024-10-02 | 2024-09-19 | 2024-09-19 | 2024-10-02 | 2024-10-02
LILLIAN DR | 1401 | LILLIAN DR | 46-26-253-005 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
LOMITA AVE | 921 | LOMITA AVE | 47-31-126-030 | Soft Surface needed | 2024-09-20 |  | 2024-09-20 | 2024-10-11
LORRAINE AVE | 3712 | LORRAINE AVE | 41-09-234-003 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
LYON ST | 1116 | LYON ST | 40-12-258-008 | Completed | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | Not needed
M L KING AVE | 4002 | M L KING AVE | 46-36-408-004 | Soft Surface needed | 2024-10-09 |  | 2024-10-09 | 2024-10-09
MACKIN RD | 2927 | MACKIN RD | 40-11-106-002 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3105 | MACKIN RD | 40-10-227-015 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3126 | MACKIN RD | 40-10-226-010 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3430 | MACKIN RD | 40-03-484-014 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MANHALL AVE | 3926 | MANHALL AVE | 40-15-477-019 | Soft Surface needed | 2024-09-18 |  | 2024-09-18 | 2024-09-26
MANN AVE | 915 | MANN AVE | 40-14-354-008 | Completed | 2024-09-18 | 2024-10-11 | 2024-09-18 | 2024-09-26 | 2024-10-11 | 2024-10-11
MARMION AVE | 3826 | MARMION AVE | 41-09-229-007 | Soft Surface needed | 2024-10-11 |  | 2024-10-11 | 2024-10-11
MASON ST | 2515 | MASON ST | 40-01-160-015 | Soft Surface needed | 2024-10-01 |  | 2024-10-01 | 2024-10-07
MASON ST | 2915 | MASON ST | 40-01-152-030 | Completed | 2024-10-01 | 2024-10-03 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-03
MASON ST | 3007 | MASON ST | 40-01-108-029 | No restoration work needed; door hanger left 10/1/24 | When Dewane visited site on 8/20/24, sidewalk needed to be replaced. When Greg and the contractor went back on 10/1/24, the sidewalk had been replaced and greenbelt restored. Assuming this was part of the city's sidewalk replacement program currently taking place.
MASON ST | 3401 | MASON ST | 46-36-376-042 | Soft Surface needed | 2024-09-30 |  | 2024-09-30 | 2024-10-03
MASON ST | 3717 | MASON ST | 46-36-376-017 | Soft Surface needed | 2024-09-30 |  | 2024-09-30 | 2024-10-07
MC KINLEY AVE | 810 | MC KINLEY AVE | 41-29-252-010 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MEISNER ST | 2976 | MEISNER ST | 47-33-355-019 | Soft Surface needed | 2024-10-11 |  | 2024-10-11 | 2024-10-11
MENTON AVE | 4135 | MENTON AVE | 41-29-178-005 | Soft Surface needed | 2024-08-20 |  | 2024-08-20 | 2024-08-26 | 2024-09-09 | 2024-09-09
MILBOURNE AVE | 3610 | MILBOURNE AVE | 46-35-482-002 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
MILLER RD | 2610 | MILLER RD | 40-23-212-023 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILLER RD | 3105 | MILLER RD | 40-23-305-028 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILTON DR | 4525 | MILTON DR | 41-29-152-022 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILTON DR | 4629 | MILTON DR | 41-29-152-029 | Soft Surface needed | 2024-08-20 |  | 2024-08-20 | 2024-08-26
MONTEITH ST | 1909 | MONTEITH ST | 40-14-229-015 | Completed | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-18 | Not needed
MONTERAY AVE | 1514 | MONTERAY AVE | 40-23-211-007 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MONTERAY AVE | 1518 | MONTERAY AVE | 40-23-211-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MOUNTAIN AVE | 2526 | MOUNTAIN AVE | 41-08-484-008 | No restoration work needed; door hanger left 10/12/24
N BALLENGER HWY | 1701 | N BALLENGER HWY | 40-02-356-026 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
N CHEVROLET AVE | 1348 | N CHEVROLET AVE | 40-11-281-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
N CHEVROLET AVE | 2722 | N CHEVROLET AVE | 40-02-279-004 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
N GRAND TRAVERSE | 622 | N GRAND TRAVERSE | 40-12-457-004 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N GRAND TRAVERSE | 1636 | N GRAND TRAVERSE | 40-12-107-010 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N MEADE ST | 1709 | N MEADE ST | 41-08-228-013 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 2502 | N STEVENSON ST | 40-11-179-033 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 2606 | N STEVENSON ST | 40-11-179-023 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 3018 | N STEVENSON ST | 40-10-232-015 | Soft Surface needed | 2024-07-24 |  | 2024-07-24 | 2024-07-31
N VERNON AVE | 2007 | N VERNON AVE | 41-05-457-016 | Soft Surface needed | 2024-08-19 |  | 2024-08-19 | 2024-08-21
NEBRASKA AVE | 2004 | NEBRASKA AVE | 41-08-255-008 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
NEBRASKA AVE | 2100 | NEBRASKA AVE | 41-08-255-014 | Soft Surface needed | 2024-07-31 |  | 2024-07-31 | 2024-07-31
NORBERT ST | 2714 | NORBERT ST | 40-11-304-017 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
NORWOOD DR | 3314 | NORWOOD DR | 40-14-160-022 | Completed | 2024-07-18 | 2024-10-08 | 2024-07-18 | 2024-07-19 | 2024-10-08 | 2024-10-08
NORWOOD DR | 3315 | NORWOOD DR | 40-14-304-010 | Completed | 2024-07-18 | 2024-10-08 | 2024-07-18 | 2024-07-19 | 2024-10-08 | 2024-10-08
NORWOOD DR | 3510 | NORWOOD DR | 40-14-160-015 | Completed | 2024-09-03 | 2024-10-11 | 2024-09-03 | 2024-09-04 | 2024-10-11 | 2024-10-11
NORWOOD DR | 3628 | NORWOOD DR | 40-14-155-030 | Soft Surface needed | 2024-07-18 |  | 2024-07-18 | 2024-08-08
OGEMA AVE | 4319 | OGEMA AVE | 41-29-254-004 | Soft Surface needed | 2024-07-31 |  | 2024-07-31 | 2024-07-31
OWEN ST | 1857 | OWEN ST | 41-17-430-042 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
OXLEY DR | 1811 | OXLEY DR | 46-26-379-014 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PADDINGTON AVE | 950 | PADDINGTON AVE | 41-19-155-018 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PADUCAH ST | 2518 | PADUCAH ST | 40-11-376-031 | Soft Surface needed | 2024-10-04 |  | 2024-10-04 | 2024-10-12
PADUCAH ST | 2547 | PADUCAH ST | 40-11-377-010 | Hard surface needed | 2024-09-18 |  |  |  | 2024-09-18 | 2024-09-18
PAGE ST | 309 | PAGE ST | 40-01-462-019 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PAGE ST | 517 | PAGE ST | 40-01-486-014 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PENCOMBE PL | 3117 | PENCOMBE PL | 40-14-180-014 | Soft Surface needed | 2024-07-16 |  | 2024-07-16 | 2024-07-31
PENCOMBE PL | 3205 | PENCOMBE PL | 40-14-180-009 | Soft Surface needed | 2024-10-04 |  | 2024-10-04 | 2024-10-12
PENCOMBE PL | 3324 | PENCOMBE PL | 40-14-177-014 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PENOYER CT | 1720 | PENOYER CT | 41-08-205-011 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
PETTIBONE AVE | 747 | PETTIBONE AVE | 41-19-382-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PINEHURST AVE | 1036 | PINEHURST AVE | 40-25-281-023 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PITKIN AVE | 3701 | PITKIN AVE | 41-09-230-015 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
PITKIN AVE | 3846 | PITKIN AVE | 41-09-233-013 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PROCTOR AVE | 2213 | PROCTOR AVE | 40-02-405-037 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PROCTOR AVE | 2614 | PROCTOR AVE | 40-02-276-036 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PROSPECT ST | 1517 | PROSPECT ST | 40-12-304-004 | Soft Surface needed | 2024-07-31 |  | 2024-07-31 | 2024-07-31
RADCLIFFE AVE | 2202 | RADCLIFFE AVE | 40-24-104-005 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
RASKOB ST | 2001 | RASKOB ST | 40-11-431-008 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2206 | RASKOB ST | 40-11-405-036 | No restoration work needed; door hanger left 10/7/24 | Once MissDig marked the water line, it was determined that the repairs were not related to the SLE
RASKOB ST | 2218 | RASKOB ST | 40-11-405-032 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2321 | RASKOB ST | 40-11-406-006 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2501 | RASKOB ST | 40-11-402-003 | Soft Surface needed | 2024-07-23 |  | 2024-07-23 | 2024-07-24
RASKOB ST | 2506 | RASKOB ST | 40-11-401-011 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASPBERRY LN | 1601 | RASPBERRY LN | 40-25-254-026 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
REMINGTON AVE | 1133 | REMINGTON AVE | 40-24-278-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
S BALLENGER HWY | 921 | S BALLENGER HWY | 40-14-351-004 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
S BALLENGER HWY | 1706 | S BALLENGER HWY | 40-22-281-026 | Hard surface needed | 2024-08-28 |  | 2024-08-28 |  | 2024-09-09 | 2024-09-09
S GRAND TRAVERSE | 936 | S GRAND TRAVERSE | 41-18-302-017 | Soft Surface needed | 2024-10-10 |  | 2024-10-10 | 2024-10-10
S GRAND TRAVERSE | 1114 | S GRAND TRAVERSE | 41-18-308-025 | Soft Surface needed | 2024-10-10 |  | 2024-10-10 | 2024-10-10
S GRAND TRAVERSE | 2902 | S GRAND TRAVERSE | 41-19-331-029 | Soft Surface needed | 2024-10-02 |  | 2024-10-02 | 2024-10-02
S GRAND TRAVERSE | 2914 | S GRAND TRAVERSE | 41-19-331-032 | Soft Surface needed | 2024-10-02 |  | 2024-10-02 | 2024-10-02
S GRAND TRAVERSE | 3520 | S GRAND TRAVERSE | 41-19-381-026 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
S GRAND TRAVERSE | 3902 | S GRAND TRAVERSE | 41-30-129-021 | Soft Surface needed | 2024-10-02 |  | 2024-10-02 | 2024-10-02
S GRAND TRAVERSE | 3906 | S GRAND TRAVERSE | 41-30-129-022 | Soft Surface needed | 2024-10-02 |  | 2024-10-02 | 2024-10-02
S GRAND TRAVERSE | 3914 | S GRAND TRAVERSE | 41-30-129-024 | Soft Surface needed | 2024-10-02 |  | 2024-10-02 | 2024-10-02
S VERNON AVE | 617 | S VERNON AVE | 41-08-455-014 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SALLY CT | 6122 | SALLY CT | 46-26-255-011 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SENECA ST | 3017 | SENECA ST | 40-02-108-029 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SENECA ST | 4227 | SENECA ST | 46-35-303-006 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SEYMOUR ST | 1810 | SEYMOUR ST | 41-17-402-007 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SEYMOUR ST | 1827 | SEYMOUR ST | 41-17-403-010 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SHAWNEE AVE | 4314 | SHAWNEE AVE | 41-29-254-027 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3119 | SHERWOOD DR | 40-14-326-007 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3409 | SHERWOOD DR | 40-14-159-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3515 | SHERWOOD DR | 40-14-159-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SLOAN ST | 2013 | SLOAN ST | 40-11-476-002 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SLOAN ST | 2536 | SLOAN ST | 40-11-402-012 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SLOAN ST | 2602 | SLOAN ST | 40-11-326-032 | Soft Surface needed | 2024-10-04 |  | 2024-10-04 | 2024-10-12
SLOAN ST | 2620 | SLOAN ST | 40-11-326-026 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SOMERSET LN | 1223 | SOMERSET LN | 41-16-229-025 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
STERLING ST | 4033 | STERLING ST | 46-35-406-011 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
STOCKDALE ST | 908 | STOCKDALE ST | 40-02-481-031 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SUNSET DR | 3759 | SUNSET DR | 40-14-103-004 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SUTTON AVE | 1310 | SUTTON AVE | 40-10-232-003 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SWAYZE ST | 2306 | SWAYZE ST | 40-14-484-025 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TACKEN ST | 870 | TACKEN ST | 40-15-433-005 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TACKEN ST | 878 | TACKEN ST | 40-15-433-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TACKEN ST | 964 | TACKEN ST | 40-15-454-025 | Completed | 2024-08-21 | 2024-10-11 | 2024-08-21 | 2024-08-30 | 2024-10-11 | 2024-10-11
TEBO ST | 1936 | TEBO ST | 41-16-378-025 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
TENNYSON AVE | 359 | TENNYSON AVE | 41-29-158-012 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TERM ST | 3411 | TERM ST | 41-04-201-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
THETA PASSAGE | 4927 | THETA PASSAGE | 47-32-228-017 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TIFFIN ST | 2517 | TIFFIN ST | 40-11-376-016 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TRUMBULL AVE | 2608 | TRUMBULL AVE | 40-02-181-008 | Soft Surface needed | 2024-10-04 |  | 2024-10-04 | 2024-10-12
TRUMBULL AVE | 3813 | TRUMBULL AVE | 46-35-379-022 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
VOSBURG ST | 917 | VOSBURG ST | 40-14-480-004 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W BAKER ST | 515 | W BAKER ST | 40-01-159-009 | No restoration work needed; door hanger left 9/17/24
W BALTIMORE BLVD | 909 | W BALTIMORE BLVD | 46-35-277-003 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
W CARPENTER RD | 325 | W CARPENTER RD | 46-25-126-064 | Soft Surface needed | 2024-08-27 |  | 2024-08-27 | 2024-08-29
W CARPENTER RD | 1001 | W CARPENTER RD | 46-26-227-028 | Completed | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25
W CARPENTER RD | 1735 | W CARPENTER RD | 46-26-126-044 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W COURT ST | 608 | W COURT ST | 40-13-286-041 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1533 | W COURT ST | 40-13-376-008 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1605 | W COURT ST | 40-13-376-007 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 1632 | W COURT ST | 40-13-328-045 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1701 | W COURT ST | 40-13-364-004 | Soft Surface needed | 2024-08-28 |  | 2024-08-28 | 2024-08-28
W COURT ST | 1715 | W COURT ST | 40-13-364-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2020 | W COURT ST | 40-14-429-014 | Completed | 2024-09-25 | 2024-10-04 | 2024-09-25 | 2024-09-30 | 2024-10-04 | 2024-10-04
W COURT ST | 2455 | W COURT ST | 40-14-453-011 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2477 | W COURT ST | 40-14-453-013 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2489 | W COURT ST | 40-14-453-003 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2605 | W COURT ST | 40-14-451-015 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2609 | W COURT ST | 40-14-451-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2663 | W COURT ST | 40-14-381-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 3009 | W COURT ST | 40-14-356-003 | Completed | 2024-08-29 | 2024-10-07 | 2024-08-29 | 2024-08-29 | 2024-10-07 | 2024-10-07
W COURT ST | 3106 | W COURT ST | 40-14-307-047 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3205 | W COURT ST | 40-14-354-004 | Completed | 2024-08-29 | 2024-10-04 | 2024-08-29 | 2024-08-29 | 2024-10-04 | 2024-10-04
W COURT ST | 3208 | W COURT ST | 40-14-307-039 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3209 | W COURT ST | 40-14-354-003 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3610 | W COURT ST | 40-15-435-013 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3614 | W COURT ST | 40-15-435-012 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3702 | W COURT ST | 40-15-435-011 | Completed | 2024-08-29 | 2024-10-04 | 2024-08-29 | 2024-08-29 | 2024-10-04 | 2024-10-04
W COURT ST | 3802 | W COURT ST | 40-15-434-029 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W COURT ST | 3810 | W COURT ST | 40-15-434-027 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W COURT ST | 3822 | W COURT ST | 40-15-434-023 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
W COURT ST | 4018 | W COURT ST | 40-15-433-010 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W DARTMOUTH ST | 312 | W DARTMOUTH ST | 40-01-152-029 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W DARTMOUTH ST | 426 | W DARTMOUTH ST | 40-01-152-018 | Soft Surface needed | 2024-09-09 |  | 2024-09-09 | 2024-09-09
W DARTMOUTH ST | 722 | W DARTMOUTH ST | 40-02-277-023 | Soft Surface needed | 2024-09-09 |  | 2024-09-09 | 2024-09-09
W DARTMOUTH ST | 1533 | W DARTMOUTH ST | 40-02-177-006 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-29 | 2024-10-02 | 2024-10-02
W DARTMOUTH ST | 1701 | W DARTMOUTH ST | 40-02-176-017 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-29 | 2024-10-02 | 2024-10-02
W DAYTON ST | 319 | W DAYTON ST | 40-01-304-014 | Completed | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-09-30 | Not needed
W DAYTON ST | 2108 | W DAYTON ST | 40-02-305-002 | Completed | 2024-09-25 | 2024-09-30 | 2024-09-25 | 2024-09-30 | Not needed
W DEWEY ST | 200 | W DEWEY ST | 40-01-126-025 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W DEWEY ST | 220 | W DEWEY ST | 40-01-126-018 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W DEWEY ST | 406 | W DEWEY ST | 40-01-102-022 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W FLINT PARK BLVD | 633 | W FLINT PARK BLVD | 46-36-153-003 | Soft Surface needed | 2024-09-25 |  | 2024-09-25 | 2024-09-25
W FOSS AVE | 306 | W FOSS AVE | 46-25-132-021 | Completed | 2024-08-26 | 2024-10-01 | 2024-08-26 | 2024-08-28 | 2024-10-01 | 2024-10-01
W GENESEE ST | 132 | W GENESEE ST | 40-01-129-026 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
W GENESEE ST | 1508 | W GENESEE ST | 40-02-130-022 | Completed | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | Not needed
W GENESEE ST | 1902 | W GENESEE ST | 40-02-129-017 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W GRACELAWN AVE | 211 | W GRACELAWN AVE | 46-25-303-038 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-28 | 2024-10-02 | 2024-10-02
W GRACELAWN AVE | 606 | W GRACELAWN AVE | 46-25-302-043 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-29
W HAMILTON AVE | 519 | W HAMILTON AVE | 40-01-311-009 | Soft Surface needed | 2024-09-24 |  | 2024-09-24 | 2024-09-24
W HOME AVE | 1502 | W HOME AVE | 46-26-401-006 | Completed | 2024-08-26 | 2024-10-08 | 2024-08-26 | 2024-08-29 | 2024-10-08 | 2024-10-08
W JACKSON AVE | 1802 | W JACKSON AVE | 40-02-176-024 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W KEARSLEY ST | 3909 | W KEARSLEY ST | 40-15-432-008 | Completed | 2024-09-25 | 2024-10-04 | 2024-09-25 | 2024-09-25 | 2024-10-04 | 2024-10-04
W LORADO AVE | 509 | W LORADO AVE | 46-25-154-005 | Completed | 2024-08-28 | 2024-10-01 | 2024-08-28 | 2024-08-28 | 2024-10-01 | 2024-10-01
W MARENGO AVE | 520 | W MARENGO AVE | 46-36-102-048 | No restoration work needed; door hanger left 9/16/24
W MARENGO AVE | 549 | W MARENGO AVE | 46-36-103-013 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W MC CLELLAN ST | 129 | W MC CLELLAN ST | 40-01-129-011 | Completed | 2024-08-26 | 2024-10-03 | 2024-08-26 | 2024-08-28 | 2024-10-03 | 2024-10-03
W MC CLELLAN ST | 315 | W MC CLELLAN ST | 40-01-108-013 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W MOTT AVE | 1510 | W MOTT AVE | 46-26-403-042 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-30 | 2024-10-08 | 2024-10-08
W PASADENA AVE | 1717 | W PASADENA AVE | 40-02-126-013 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PATERSON ST | 1410 | W PATERSON ST | 40-02-451-017 | Completed | 2024-08-26 | 2024-10-07 | 2024-08-26 | 2024-08-29 | 2024-10-07 | 2024-10-07
W PATERSON ST | 1530 | W PATERSON ST | 40-02-377-013 | Completed | 2024-09-11 | 2024-10-07 | 2024-09-11 | 2024-09-11 | 2024-10-07 | 2024-10-07
W PHILADELPHIA BLV | 105 | W PHILADELPHIA BLV | 46-36-129-023 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PHILADELPHIA BLV | 127 | W PHILADELPHIA BLV | 46-36-129-019 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PIERSON RD | 624 | W PIERSON RD | 46-25-355-018 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PIERSON RD | 1310 | W PIERSON RD | 46-26-455-027 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W PIPER AVE | 221 | W PIPER AVE | 46-25-328-003 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Not needed
W RANKIN ST | 418 | W RANKIN ST | 40-01-156-016 | Completed | 2024-08-26 | 2024-10-03 | 2024-08-26 | 2024-08-28 | 2024-10-03 | 2024-10-03
W RIDGEWAY AVE | 624 | W RIDGEWAY AVE | 46-25-354-011 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W STEWART AVE | 117 | W STEWART AVE | 46-36-180-027 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W STEWART AVE | 121 | W STEWART AVE | 46-36-180-026 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W STEWART AVE | 218 | W STEWART AVE | 46-36-179-053 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 325 | W STEWART AVE | 46-36-180-011 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 401 | W STEWART AVE | 46-36-180-009 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 402 | W STEWART AVE | 46-36-179-041 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 410 | W STEWART AVE | 46-36-179-040 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 516 | W STEWART AVE | 46-36-154-043 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 525 | W STEWART AVE | 46-36-155-013 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 542 | W STEWART AVE | 46-36-154-038 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 602 | W STEWART AVE | 46-36-154-035 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 614 | W STEWART AVE | 46-36-154-032 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 817 | W STEWART AVE | 46-35-282-004 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 841 | W STEWART AVE | 46-35-281-024 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 845 | W STEWART AVE | 46-35-281-025 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1208 | W STEWART AVE | 46-35-255-044 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1301 | W STEWART AVE | 46-35-256-017 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1309 | W STEWART AVE | 46-35-256-016 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1317 | W STEWART AVE | 46-35-256-013 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1419 | W STEWART AVE | 46-35-256-008 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1922 | W STEWART AVE | 46-35-155-056 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2010 | W STEWART AVE | 46-35-155-050 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2014 | W STEWART AVE | 46-35-155-049 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2213 | W STEWART AVE | 46-35-158-001 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2218 | W STEWART AVE | 46-35-155-035 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W TWELFTH ST | 210 | W TWELFTH ST | 41-18-451-062 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-27
W TWELFTH ST | 1025 | W TWELFTH ST | 40-24-231-007 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-27
W TWELFTH ST | 1029 | W TWELFTH ST | 40-24-231-006 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-27
W WITHERBEE ST | 210 | W WITHERBEE ST | 40-01-331-024 | Completed | 2024-08-26 | 2024-10-04 | 2024-08-26 | 2024-08-28 | 2024-10-04 | 2024-10-04
W WITHERBEE ST | 524 | W WITHERBEE ST | 40-01-311-019 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W YORK AVE | 112 | W YORK AVE | 46-25-126-044 | Completed | 2024-08-26 | 2024-10-01 | 2024-08-26 | 2024-08-30 | 2024-10-01 | 2024-10-01
WALDMAN AVE | 720 | WALDMAN AVE | 41-19-382-024 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-27
WARRINGTON DR | 4618 | WARRINGTON DR | 46-35-178-068 | Completed | 2024-08-29 | 2024-10-08 | 2024-08-29 | 2024-08-29 | 2024-10-08 | 2024-10-08
WASHINGTON AVE | 1320 | WASHINGTON AVE | 41-07-277-011 | Completed | 2024-09-10 | 2024-10-01 | 2024-09-10 | 2024-09-10 | 2024-10-01 | 2024-10-01
WEBSTER RD | 6920 | WEBSTER RD | 47-29-201-010 | Completed | 2024-09-25 | 2024-10-01 | 2024-09-25 | 2024-09-25 | 2024-10-01 | 2024-10-01
WELCH BLVD | 112 | WELCH BLVD | 40-12-126-030 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
WELCH BLVD | 2331 | WELCH BLVD | 40-02-306-010 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WELLER ST | 611 | WELLER ST | 40-11-379-010 | Soft Surface needed | 2024-09-18 |  | 2024-09-18 | 2024-09-18
WESTCOMBE AVE | 324 | WESTCOMBE AVE | 40-14-153-014 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WESTCOMBE AVE | 412 | WESTCOMBE AVE | 40-14-154-023 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-10-04 | 2024-10-04 | 2024-10-04
WESTCOMBE AVE | 460 | WESTCOMBE AVE | 40-14-156-017 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-09-11 | 2024-10-04 | 2024-10-04
WESTERN RD | 4801 | WESTERN RD | 47-32-230-037 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITNEY AVE | 3613 | WHITNEY AVE | 40-22-233-009 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
WHITTIER ST | 3125 | WHITTIER ST | 41-04-334-022 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3822 | WHITTIER ST | 41-04-476-021 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3829 | WHITTIER ST | 41-04-434-020 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3837 | WHITTIER ST | 41-04-434-022 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WILBERFORCE DR | 716 | WILBERFORCE DR | 41-07-114-005 | Completed | 2024-08-26 | 2024-10-04 | 2024-08-26 | 2024-08-27 | 2024-10-04 | 2024-10-04
WILTON PL | 2702 | WILTON PL | 47-29-476-005 | Completed | 2024-09-11 | 2024-10-01 | 2024-09-11 | 2024-09-11 | 2024-10-01 | 2024-10-01
WINDEMERE AVE | 2618 | WINDEMERE AVE | 41-08-482-011 | Soft Surface needed | 2024-09-10 |  | 2024-09-10 | 2024-09-10
WINDSOR LN | 1820 | WINDSOR LN | 40-25-104-035 | No restoration work needed; door hanger left 9/16/24
WINDSOR LN | 1830 | WINDSOR LN | 40-25-104-032 | Soft Surface needed | 2024-08-27 |  | 2024-08-27 | 2024-08-30
WINONA ST | 4120 | WINONA ST | 46-35-327-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WINONA ST | 4124 | WINONA ST | 46-35-327-002 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WINONA ST | 4128 | WINONA ST | 46-35-327-029 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WISCONSIN AVE | 2314 | WISCONSIN AVE | 41-08-210-013 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WISNER ST | 3105 | WISNER ST | 40-02-107-028 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
WISNER ST | 4235 | WISNER ST | 46-35-156-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WOLCOTT ST | 2526 | WOLCOTT ST | 40-11-255-030 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 2741 | WOLCOTT ST | 40-11-178-009 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 2953 | WOLCOTT ST | 40-11-111-002 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 3201 | WOLCOTT ST | 40-10-231-011 | Soft Surface needed | 2024-08-29 |  | 2024-08-29 | 2024-08-29
WOODBRIDGE ST | 1342 | WOODBRIDGE ST | 40-11-427-030 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOODCROFT AVE | 1415 | WOODCROFT AVE | 40-23-233-003 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-27
WOODHALL DR | 1402 | WOODHALL DR | 46-35-252-033 | Soft Surface needed | 2024-08-26 |  | 2024-08-26 | 2024-08-28
WOODHALL DR | 1418 | WOODHALL DR | 46-35-252-029 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
WOODLIN DR | 1714 | WOODLIN DR | 46-26-126-018 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WOODLIN DR | 1810 | WOODLIN DR | 46-26-126-037 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WOODROW AVE | 3801 | WOODROW AVE | 41-04-432-013 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WOODSLEA DR | 1809 | WOODSLEA DR | 41-20-276-006 | Completed | 2024-08-27 | 2024-10-01 | 2024-08-27 | 2024-09-23 | 2024-10-01 | 2024-10-01
WYOMING AVE | 1618 | WYOMING AVE | 41-05-130-004 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WYOMING AVE | 3013 | WYOMING AVE | 41-04-102-035 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WYOMING AVE | 3130 | WYOMING AVE | 41-04-128-008 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
YALE ST | 3018 | YALE ST | 40-23-181-015 | Completed | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-09-30 | 2024-10-04 | 2024-10-04
ZIMMERMAN ST | 1801 | ZIMMERMAN ST | 40-13-360-013 | Completed | 2024-09-11 | 2024-09-26 | 2024-09-11 | 2024-09-26 | Not needed
ZIMMERMAN ST | 3816 | ZIMMERMAN ST | 40-15-476-028 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-09-11 | 2024-10-04 | 2024-10-04
Priority homes

## Sheet2
7020 Industrial | Reported as no work w/e 8/17/24; field visit on 8/23/24 determined work was on the side of the house; soft restroation needed