## Sheet1
Address |  |  | Location | Status | Actual Start | Actual Completion | Hard Surface Start | Hard Surface Complete | Soft Surface Start | Soft Surface Complete
ADDISON ST | 818 | ADDISON ST | 47-31-377-001 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11 | #N/A
ADDISON ST | 922 | ADDISON ST | 47-31-377-038 | No restoration work needed; door hanger left 8/20/24
AITKEN AVE | 2026 | AITKEN AVE | 41-17-377-021 | Completed | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-08 | 2024-08-12 | 2024-08-12
AITKEN AVE | 2226 | AITKEN AVE | 41-20-128-017 | Completed | 2024-08-05 | 2024-08-29 | 2024-08-05 | 2024-08-29 | 2024-08-20 | 2024-08-20
ALEXANDER ST | 2308 | ALEXANDER ST | 40-01-407-014 | Completed | 2024-09-11 | 2024-10-11 | 2024-09-11 | 2024-09-16 | 2024-10-11 | 2024-10-11
ALPHA WAY | 2605 | ALPHA WAY | 47-32-226-020 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
ALPHA WAY | 2937 | ALPHA WAY | 47-33-101-018 | Completed | 2024-09-16 | 2024-10-11 | 2024-09-16 | 2024-09-18 | 2024-10-11 | 2024-10-11
ALPHA WAY | 5017 | ALPHA WAY | 47-32-226-011 | Completed | 2023-09-07 | 2024-07-17 | 2023-09-07 | 2023-12-22 | 2024-07-17 | 2024-07-17
ALVORD AVE | 842 | ALVORD AVE | 41-30-108-020 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 849 | ALVORD AVE | 41-30-110-008 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1041 | ALVORD AVE | 40-25-277-010 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1213 | ALVORD AVE | 40-25-276-011 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1217 | ALVORD AVE | 40-25-276-037 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1220 | ALVORD AVE | 40-25-232-018 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1230 | ALVORD AVE | 40-25-232-017 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ALVORD AVE | 1240 | ALVORD AVE | 40-25-232-015 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
ARIZONA AVE | 1510 | ARIZONA AVE | 41-05-103-006 | Completed | 2024-10-04 | 2024-10-16 | 2024-10-04 | 2024-10-16 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 1705 | ARIZONA AVE | 41-05-127-021 | Completed | 2024-10-04 | 2024-10-16 | 2024-10-04 | 2024-10-16 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 1725 | ARIZONA AVE | 41-05-127-026 | Completed | 2024-10-04 | 2024-10-16 | 2024-10-04 | 2024-10-16 | Not needed
ARIZONA AVE | 1817 | ARIZONA AVE | 41-05-127-035 | Completed | 2024-10-04 | 2024-10-16 | 2024-10-04 | 2024-10-16 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3014 | ARIZONA AVE | 41-04-102-016 | Completed | 2024-10-04 | 2024-10-15 | 2024-10-04 | 2024-10-10 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3018 | ARIZONA AVE | 41-04-102-017 | Completed | 2024-10-04 | 2024-10-15 | 2024-10-04 | 2024-10-10 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3022 | ARIZONA AVE | 41-04-102-018 | Completed | 2024-10-04 | 2024-10-15 | 2024-10-04 | 2024-10-10 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3029 | ARIZONA AVE | 41-04-101-035 | Completed | 2024-10-09 | 2024-10-15 | 2024-10-09 | 2024-10-10 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3113 | ARIZONA AVE | 41-04-126-031 | No restoration work needed; door hanger left 8/29/24
ARIZONA AVE | 3126 | ARIZONA AVE | 41-04-127-008 | No restoration work needed; door hanger left 8/29/24
ARIZONA AVE | 3138 | ARIZONA AVE | 41-04-127-011 | No restoration work needed; door hanger left 8/29/24
ARIZONA AVE | 3209 | ARIZONA AVE | 41-04-126-044 | No restoration work needed; door hanger left 8/29/24
ARIZONA AVE | 3222 | ARIZONA AVE | 41-04-127-020 | Completed | 2024-10-09 | 2024-10-15 | 2024-10-09 | 2024-10-10 | 2024-10-15 | 2024-10-15
ARIZONA AVE | 3229 | ARIZONA AVE | 41-04-126-050 | No restoration work needed; door hanger left 8/29/24
ARLENE AVE | 3217 | ARLENE AVE | 40-23-152-005 | No restoration work needed; door hanger left 8/14/24
ARLENE AVE | 3505 | ARLENE AVE | 40-23-151-006 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-13 | 2024-09-19 | 2024-09-19
ARLENE AVE | 3805 | ARLENE AVE | 40-22-276-011 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-09 | 2024-09-19 | 2024-09-19
ARLENE AVE | 3806 | ARLENE AVE | 40-22-232-028 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
ARLENE AVE | 3913 | ARLENE AVE | 40-22-276-033 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-09 | 2024-09-19 | 2024-09-19
ARLINGTON AVE | 1717 | ARLINGTON AVE | 41-08-202-021 | Completed | 2024-09-13 | 2024-10-19 | 2024-09-13 | 2024-10-07 | 2024-10-19 | 2024-10-19
ARLINGTON AVE | 2313 | ARLINGTON AVE | 41-05-407-035 | No restoration work needed; door hanger left 8/18/24
ARROW LN | 1510 | ARROW LN | 41-20-253-002 | No restoration work needed; door hanger left 7/11/24
AUGUSTA ST | 3418 | AUGUSTA ST | 40-23-101-018 | Completed | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-10 | 2024-09-17 | 2024-09-17
AVENUE A | 1209 | AVENUE A | 40-12-276-040 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
AVENUE A | 1303 | AVENUE A | 40-12-276-036 | Completed | 2024-10-14 | 2024-10-30 | 2024-10-14 | 2024-10-21 | 2024-10-30 | 2024-10-30
AVENUE A | 1314 | AVENUE A | 40-12-277-036 | Completed | 2024-10-14 | 2024-10-30 | 2024-10-14 | 2024-10-21 | 2024-10-30 | 2024-10-30
AVENUE A | 1819 | AVENUE A | 40-01-481-015 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
AVENUE A | 2211 | AVENUE A | 40-01-431-023 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
AVON ST | 509 | AVON ST | 41-07-453-037 | No restoration work needed; door hanger left 9/3/24
AVON ST | 602 | AVON ST | 41-07-455-011 | No restoration work needed; door hanger left 8/18/24
BAGLEY ST | 2001 | BAGLEY ST | 40-11-480-007 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
BALDWIN BLVD | 5016 | BALDWIN BLVD | 46-35-229-012 | No restoration work needed; door hanger left 8/22/24
BALDWIN BLVD | 5314 | BALDWIN BLVD | 46-26-479-015 | No restoration work needed; door hanger left 9/3/24
BALDWIN BLVD | 5321 | BALDWIN BLVD | 46-26-478-036 | No restoration work needed; door hanger left 9/3/24
BALDWIN BLVD | 5406 | BALDWIN BLVD | 46-26-479-010 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
BALDWIN BLVD | 5510 | BALDWIN BLVD | 46-26-479-004 | No restoration work needed; door hanger left 8/22/24
BALDWIN BLVD | 5514 | BALDWIN BLVD | 46-26-479-002 | No restoration work needed; door hanger left 7/17/24
BALDWIN BLVD | 5518 | BALDWIN BLVD | 46-26-479-001 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BALDWIN BLVD | 5601 | BALDWIN BLVD | 46-26-427-047 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BALDWIN BLVD | 5610 | BALDWIN BLVD | 46-26-428-022 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
BALDWIN BLVD | 5717 | BALDWIN BLVD | 46-26-427-037 | No restoration work needed; door hanger left 8/22/24
BALDWIN BLVD | 5810 | BALDWIN BLVD | 46-26-428-009 | No restoration work needed; door hanger left 7/9/24
BARBARA DR | 1805 | BARBARA DR | 46-26-178-009 | Completed | 2024-10-09 | 2024-10-30 | 2024-10-09 | 2024-10-23 | 2024-10-30 | 2024-10-30
BARBARA DR | 1806 | BARBARA DR | 46-26-176-056 | No restoration work needed; door hanger left 8/23/24
BARBARA DR | 1821 | BARBARA DR | 46-26-178-004 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BARKS ST | 2046 | BARKS ST | 41-17-457-029 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
BARLOW AVE | 1026 | BARLOW AVE | 40-24-231-012 | Completed | 2024-08-09 | 2024-08-09 |  |  | 2024-08-09 | 2024-08-09
BARNEY AVE | 801 | BARNEY AVE | 40-14-306-006 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13
BARNEY AVE | 940 | BARNEY AVE | 40-14-352-018 | No restoration work needed; door hanger left 8/30/24
BARNEY AVE | 991 | BARNEY AVE | 40-14-360-010 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
BARNEY AVE | 1012 | BARNEY AVE | 40-14-365-003 | No restoration work needed; door hanger left 8/15/24
BARNEY AVE | 1024 | BARNEY AVE | 40-14-365-013 | Completed | 2024-09-10 | 2024-09-23 | 2024-09-10 | 2024-09-10 | 2024-09-23 | 2024-09-23
BARNEY AVE | 1028 | BARNEY AVE | 40-14-365-008 | No restoration work needed; door hanger left 9/4/24
BARNEY AVE | 1302 | BARNEY AVE | 40-23-106-010 | No restoration work needed; door hanger left 8/30/24
BARRIE AVE | 729 | BARRIE AVE | 41-19-330-007 | No restoration work needed; door hanger left 7/26/24
BARRIE AVE | 736 | BARRIE AVE | 41-19-328-035 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BARRIE AVE | 836 | BARRIE AVE | 41-19-304-016 | Completed | 2024-07-22 | 2024-08-09 | 2024-07-22 | 2024-07-24 | 2024-08-09 | 2024-08-09
BARRIE AVE | 840 | BARRIE AVE | 41-19-304-015 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
BARRIE AVE | 926 | BARRIE AVE | 41-19-303-020 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
BARRIE AVE | 1106 | BARRIE AVE | 40-24-427-029 | No restoration work needed; door hanger left 7/22/24
BARRIE AVE | 1109 | BARRIE AVE | 40-24-428-009 | Completed | 2023-09-09 | 2024-07-31 | 2023-09-09 | 2024-07-24 | 2024-07-31 | 2024-07-31
BARTH ST | 1821 | BARTH ST | 40-11-279-028 | Completed | 2024-09-20 | 2024-10-18 | 2024-09-20 | 2024-10-02 | 2024-10-18 | 2024-10-18
BARTH ST | 1829 | BARTH ST | 40-11-279-027 | No restoration work needed; door hanger left 8/21/24
BARTH ST | 2109 | BARTH ST | 40-11-279-010 | No restoration work needed; door hanger left 8/21/24
BARTH ST | 2220 | BARTH ST | 40-11-252-020 | Completed | 2024-07-25 | 2024-08-09 | 2024-07-25 | 2024-08-08 | 2024-08-09 | 2024-08-09
BARTH ST | 2832 | BARTH ST | 40-11-131-021 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-17 | 2024-09-18 | 2024-09-18
BARTH ST | 3025 | BARTH ST | 40-11-103-002 | No restoration work needed; door hanger left 8/21/24
BAYBERRY LN | 1701 | BAYBERRY LN | 40-24-378-037 | No restoration work needed; door hanger left 7/26/24
BAYBERRY LN | 1702 | BAYBERRY LN | 40-24-377-039 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BAYBERRY LN | 1709 | BAYBERRY LN | 40-24-378-036 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BAYBERRY LN | 1806 | BAYBERRY LN | 40-24-377-017 | No restoration work needed; door hanger left 7/26/24
BAYBERRY LN | 1911 | BAYBERRY LN | 40-24-378-025 | No restoration work needed; door hanger left 7/26/24
BEARD ST | 1220 | BEARD ST | 41-17-105-011 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
BEARD ST | 1313 | BEARD ST | 41-17-131-029 | Completed | 2024-08-08 | 2024-08-20 | 2024-08-08 | 2024-08-19 | 2024-08-20 | 2024-08-20
BECKER ST | 1906 | BECKER ST | 40-13-355-023 | Completed | 2024-08-21 | 2024-09-05 | 2024-08-21 | 2024-08-29 | 2024-09-05 | 2024-09-05
BEDE ST | 405 | BEDE ST | 41-29-156-021 | No restoration work needed; door hanger left 7/17/24
BEECHER RD | 3413 | BEECHER RD | 40-14-303-004 | Completed | 2024-10-23 | 2024-10-26 | 2024-10-23 | 2024-10-25 | 2024-10-26 | 2024-10-26
BEECHER RD | 3506 | BEECHER RD | 40-14-304-014 | Completed | 2024-11-01 | 2024-11-08 | 2024-11-07 | 2024-11-08 | 2024-11-01 | 2024-11-01
BEECHER RD | 3718 | BEECHER RD | 40-14-156-023 | No restoration work needed; door hanger left 8/15/24
BEECHWOOD AVE | 3212 | BEECHWOOD AVE | 41-04-331-003 | No restoration work needed; door hanger left 8/29/24
BEECHWOOD DR | 2316 | BEECHWOOD DR | 41-05-410-010 | Completed | 2024-09-13 | 2024-10-19 | 2024-09-13 | 2024-09-19 | 2024-10-19 | 2024-10-19
BEECHWOOD DR | 2317 | BEECHWOOD DR | 41-05-428-013 | Completed | 2024-09-13 | 2024-10-19 | 2024-09-13 | 2024-10-12 | 2024-10-19 | 2024-10-19
BEGOLE ST | 1912 | BEGOLE ST | 40-11-230-028 | No restoration work needed; door hanger left 8/20/24
BEGOLE ST | 2109 | BEGOLE ST | 40-11-232-006 | Completed | 2024-10-02 | 2024-10-18 | 2024-10-02 | 2024-10-02 | 2024-10-18 | 2024-10-18
BEGOLE ST | 2219 | BEGOLE ST | 40-11-231-011 | No restoration work needed; door hanger left 8/20/24
BEGOLE ST | 2401 | BEGOLE ST | 40-11-202-017 | No restoration work needed; door hanger left 8/20/24
BEGOLE ST | 2954 | BEGOLE ST | 40-02-352-003 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-30 | 2024-10-08 | 2024-10-08
BEGOLE ST | 3102 | BEGOLE ST | 40-02-351-015 | Completed | 2024-09-19 | 2024-10-17 | 2024-09-19 | 2024-09-26 | 2024-10-17 | 2024-10-17
BEGOLE ST | 3118 | BEGOLE ST | 40-02-351-013 | No restoration work needed; door hanger left 8/21/24
BELLCREEK DR | 1317 | BELLCREEK DR | 46-26-251-010 | No restoration work needed; door hanger left 8/23/24
BELLCREEK DR | 1322 | BELLCREEK DR | 46-26-204-047 | No restoration work needed; door hanger left 8/23/24
BELLE AVE | 1802 | BELLE AVE | 41-05-331-013 | No restoration work needed; door hanger left 9/3/24
BENNETT AVE | 1231 | BENNETT AVE | 41-06-476-019 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
BENNETT AVE | 1717 | BENNETT AVE | 41-05-377-024 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
BENNETT AVE | 1821 | BENNETT AVE | 41-05-377-035 | Completed | 2024-07-18 | 2024-07-18 | 2023-09-05 | 2023-12-22 | 2024-07-18 | 2024-07-18
BENNETT AVE | 3718 | BENNETT AVE | 41-04-476-044 | No restoration work needed; door hanger left 8/28/24
BERGER DR | 4320 | BERGER DR | 46-35-254-014 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
BERKLEY ST | 2026 | BERKLEY ST | 40-11-429-023 | No restoration work needed; door hanger left 8/21/24
BERKLEY ST | 2609 | BERKLEY ST | 40-11-183-019 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
BERKLEY ST | 2616 | BERKLEY ST | 40-11-181-031 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
BERKLEY ST | 2637 | BERKLEY ST | 40-11-183-012 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
BERKLEY ST | 2927 | BERKLEY ST | 40-11-155-008 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
BERKLEY ST | 3006 | BERKLEY ST | 40-10-234-023 | No restoration work needed; door hanger left 7/16/24
BERKLEY ST | 3123 | BERKLEY ST | 40-10-276-005 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
BIRCHCREST DR | 4725 | BIRCHCREST DR | 46-35-104-034 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BIRCHCREST DR | 4734 | BIRCHCREST DR | 46-35-105-016 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BIRCHCREST DR | 4735 | BIRCHCREST DR | 46-35-104-032 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BIRCHCREST DR | 4915 | BIRCHCREST DR | 46-35-104-020 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
BLACKINGTON AVE | 3914 | BLACKINGTON AVE | 40-15-482-011 | Completed | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-12 | 2024-09-17 | 2024-09-17
BLACKINGTON AVE | 3915 | BLACKINGTON AVE | 40-15-483-007 | Completed | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-12 | 2024-09-17 | 2024-09-17
BLAIR ST | 905 | BLAIR ST | 40-11-380-040 | No restoration work needed; house demo'd
BLOOR AVE | 819 | BLOOR AVE | 41-19-304-008 | No restoration work needed; door hanger left 7/31/24
BLOOR AVE | 902 | BLOOR AVE | 41-19-301-012 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BLOOR AVE | 940 | BLOOR AVE | 41-19-301-004 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BOLAN DR | 1401 | BOLAN DR | 46-26-455-009 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
BOSTON AVE | 1118 | BOSTON AVE | 40-13-357-019 | Completed | 2024-08-21 | 2024-09-05 | 2024-08-21 | 2024-08-29 | 2024-09-05 | 2024-09-05
BOSTON AVE | 1224 | BOSTON AVE | 40-24-102-008 | Completed | 2024-08-21 | 2024-08-29 | 2024-08-21 | 2024-08-29 | Not needed
BOSTON AVE | 1225 | BOSTON AVE | 40-24-103-001 | Completed | 2024-08-21 | 2024-09-05 | 2024-08-21 | 2024-08-29 | 2024-09-05 | 2024-09-05
BRABYN AVE | 1114 | BRABYN AVE | 40-14-463-016 | No restoration work needed; door hanger left 7/29/24
BRABYN AVE | 1417 | BRABYN AVE | 40-23-229-006 | No restoration work needed; door hanger left 7/29/24
BRABYN AVE | 1430 | BRABYN AVE | 40-23-228-019 | No restoration work needed; door hanger left 7/29/24
BRADLEY AVE | 1019 | BRADLEY AVE | 40-14-390-005 | Completed | 2023-11-13 | 2024-07-29 | 2023-11-13 | 2023-12-15 | 2024-07-29 | 2024-07-29
BRADLEY AVE | 1420 | BRADLEY AVE | 40-23-207-012 | Completed | 2024-08-28 | 2024-09-17 | 2024-08-28 | 2024-09-09 | 2024-09-17 | 2024-09-17
BRADLEY AVE | 1549 | BRADLEY AVE | 40-23-254-005 | Completed | 2024-08-28 | 2024-09-18 | 2024-08-28 | 2024-09-09 | 2024-09-18 | 2024-09-18
BRANCH RD | 2008 | BRANCH RD | 41-04-383-004 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BRANCH RD | 2016 | BRANCH RD | 41-04-383-001 | Completed | 2024-09-18 | 2024-10-02 | 2024-09-18 | 2024-09-19 | 2024-10-02 | 2024-10-02
BRANDON ST | 2805 | BRANDON ST | 40-23-182-011 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
BRANDON ST | 2844 | BRANDON ST | 40-23-180-015 | No restoration work needed; door hanger left 7/30/24
BRANDON ST | 2909 | BRANDON ST | 40-23-181-010 | Completed | 2024-09-04 | 2024-09-19 | 2024-09-04 | 2024-09-09 | 2024-09-19 | 2024-09-19
BRANDON ST | 3017 | BRANDON ST | 40-23-181-002 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
BRANDON ST | 3117 | BRANDON ST | 40-23-162-015 | Completed | 2024-09-04 | 2024-09-19 | 2024-09-04 | 2024-09-09 | 2024-09-19 | 2024-09-19
BRANDON ST | 3505 | BRANDON ST | 40-23-302-010 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
BRANDON ST | 3507 | BRANDON ST | 40-23-302-009 | Completed | 2024-09-04 | 2024-09-19 | 2024-09-04 | 2024-09-09 | 2024-09-19 | 2024-09-19
BRENT AVE | 3405 | BRENT AVE | 41-09-209-011 | Completed | 2024-09-19 | 2024-09-19 |  |  | 2024-09-19 | 2024-09-19
BRENTWOOD DR | 3109 | BRENTWOOD DR | 40-14-328-023 | No restoration work needed; door hanger left 7/29/24
BRENTWOOD DR | 3202 | BRENTWOOD DR | 40-14-329-011 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
BRENTWOOD DR | 3315 | BRENTWOOD DR | 40-14-160-010 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
BRENTWOOD DR | 3720 | BRENTWOOD DR | 40-14-154-002 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
BREWSTER AVE | 3406 | BREWSTER AVE | 41-09-209-022 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BREWSTER AVE | 3426 | BREWSTER AVE | 41-09-209-005 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BREWSTER AVE | 3430 | BREWSTER AVE | 41-09-209-006 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
BRIARWOOD DR | 1711 | BRIARWOOD DR | 40-24-377-029 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
BRIARWOOD DR | 3301 | BRIARWOOD DR | 40-24-376-063 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
BROADWAY BLVD | 1284 | BROADWAY BLVD | 41-06-482-012 | No restoration work needed; door hanger left 7/18/24
BROADWAY BLVD | 2328 | BROADWAY BLVD | 41-05-480-007 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
BROOKS ST | 2040 | BROOKS ST | 40-24-228-005 | Completed | 2024-08-01 | 2024-08-09 | 2024-08-01 | 2024-08-02 | 2024-08-09 | 2024-08-09
BROOKSIDE DR | 2407 | BROOKSIDE DR | 41-17-231-018 | Completed | 2024-08-08 | 2024-08-20 | 2024-08-08 | 2024-08-13 | 2024-08-20 | 2024-08-20
BROOKWOOD AVE | 1602 | BROOKWOOD AVE | 41-17-177-012 | Completed | 2024-08-07 | 2024-08-20 | 2024-08-07 | 2024-08-19 | 2024-08-20 | 2024-08-20
BROOKWOOD AVE | 1609 | BROOKWOOD AVE | 41-17-176-022 | No restoration work needed; door hanger left 8/9/24
BROWN ST | 2505 | BROWN ST | 40-23-206-014 | No restoration work needed; door hanger left 8/22/24
BROWN ST | 2601 | BROWN ST | 40-23-205-013 | No restoration work needed; door hanger left 8/13/24
BROWN ST | 2737 | BROWN ST | 40-23-134-013 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
BROWNELL BLVD | 2201 | BROWNELL BLVD | 40-02-327-044 | Completed | 2024-09-10 | 2024-10-07 | 2024-09-10 | 2024-09-10 | 2024-10-07 | 2024-10-07
BROWNELL BLVD | 2419 | BROWNELL BLVD | 40-02-327-050 | Completed | 2024-10-01 | 2024-10-16 | 2024-10-01 | 2024-10-07 | 2024-10-16 | 2024-10-16
BROWNELL BLVD | 2613 | BROWNELL BLVD | 40-02-160-037 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
BROWNELL BLVD | 2620 | BROWNELL BLVD | 40-02-178-010 | Completed | 2024-10-08 | 2024-10-12 | 2024-10-08 | 2024-10-12 | 2024-09-04 | 2024-09-04
BROWNELL BLVD | 2632 | BROWNELL BLVD | 40-02-178-008 | Completed | 2024-10-08 | 2024-10-16 | 2024-10-08 | 2024-10-12 | 2024-10-16 | 2024-10-16
BROWNELL BLVD | 2714 | BROWNELL BLVD | 40-02-178-001 | Completed | 2024-10-08 | 2024-10-16 | 2024-10-08 | 2024-10-12 | 2024-10-16 | 2024-10-16
BROWNELL BLVD | 2719 | BROWNELL BLVD | 40-02-160-027 | Completed | 2024-10-08 | 2024-10-16 | 2024-10-08 | 2024-10-12 | 2024-10-16 | 2024-10-16
BROWNELL BLVD | 3117 | BROWNELL BLVD | 40-02-105-037 | Completed | 2024-10-08 | 2024-10-30 | 2024-10-08 | 2024-10-23 | 2024-10-30 | 2024-10-30
BROWNELL BLVD | 3326 | BROWNELL BLVD | 40-02-126-002 | Completed | 2024-10-08 | 2024-10-16 | 2024-10-08 | 2024-10-09 | 2024-10-16 | 2024-10-16
BROWNELL BLVD | 3913 | BROWNELL BLVD | 46-35-376-016 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
BROWNELL BLVD | 4014 | BROWNELL BLVD | 46-35-328-033 | Completed | 2024-10-08 | 2024-10-15 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-15
BROWNELL BLVD | 4026 | BROWNELL BLVD | 46-35-328-029 | Completed | 2024-10-08 | 2024-10-15 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-15
BROWNELL BLVD | 4105 | BROWNELL BLVD | 46-35-327-022 | Completed | 2024-10-08 | 2024-10-15 | 2024-10-08 | 2024-10-12 | 2024-10-15 | 2024-10-15
BROWNELL BLVD | 4110 | BROWNELL BLVD | 46-35-328-061 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
BROWNELL BLVD | 4201 | BROWNELL BLVD | 46-35-326-018 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
BRUNSWICK AVE | 3418 | BRUNSWICK AVE | 41-19-353-028 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
BRYANT ST | 4526 | BRYANT ST | 41-30-278-022 | Completed | 2024-07-17 | 2024-08-09 | 2024-07-17 | 2024-08-02 | 2024-08-09 | 2024-08-09
BRYANT ST | 4614 | BRYANT ST | 41-30-278-032 | No restoration work needed; door hanger left 7/17/24
BUCKINGHAM AVE | 415 | BUCKINGHAM AVE | 41-29-126-019 | No restoration work needed; door hanger left 9/24/24
BUCKINGHAM AVE | 601 | BUCKINGHAM AVE | 41-29-201-033 | No restoration work needed; door hanger left 9/11/24
BURLINGTON DR | 1121 | BURLINGTON DR | 41-16-227-020 | No restoration work needed; door hanger left 7/25/24
BURR BLVD | 1937 | BURR BLVD | 41-17-452-004 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
BURR BLVD | 2014 | BURR BLVD | 41-17-381-019 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
BURROUGHS AVE | 341 | BURROUGHS AVE | 41-29-102-030 | No restoration work needed; door hanger left 7/25/24
BURROUGHS AVE | 425 | BURROUGHS AVE | 41-29-127-018 | Completed | 2024-07-11 | 2024-07-19 | 2024-07-11 | 2024-07-19 | 2024-07-18 | 2024-07-18
BURROUGHS AVE | 521 | BURROUGHS AVE | 41-29-202-025 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CALUMET ST | 2017 | CALUMET ST | 41-17-204-015 | No restoration work needed; door hanger left 8/8/24
CAMPBELL ST | 841 | CAMPBELL ST | 41-30-104-008 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
CAMPBELL ST | 842 | CAMPBELL ST | 41-30-102-023 | No restoration work needed; door hanger left 7/26/24
CANNIFF ST | 2218 | CANNIFF ST | 46-35-153-028 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CARLTON ST | 4520 | CARLTON ST | 47-31-177-007 | Completed | 2024-08-20 | 2024-08-20 |  |  | 2024-08-20 | 2024-08-20
CARMANBROOK PKWY | 1713 | CARMANBROOK PKWY | 40-24-376-010 | No restoration work needed; door hanger left 7/22/24
CARMANBROOK PKWY | 1806 | CARMANBROOK PKWY | 40-24-378-016 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
CARTIER ST | 2026 | CARTIER ST | 40-14-229-038 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
CARTIER ST | 2030 | CARTIER ST | 40-14-229-037 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
CARTIER ST | 2111 | CARTIER ST | 40-14-201-030 | No restoration work needed; door hanger left 8/16/24
CARTON ST | 414 | CARTON ST | 46-36-480-004 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
CARTON ST | 802 | CARTON ST | 47-31-378-001 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
CECIL DR | 6701 | CECIL DR | 47-29-126-034 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
CHALMERS ST | 425 | CHALMERS ST | 41-08-433-004 | Completed | 2024-08-08 | 2024-09-03 | 2024-08-08 | 2024-08-20 | 2024-09-03 | 2024-09-03
CHALMERS ST | 434 | CHALMERS ST | 41-08-432-021 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CHANDLER AVE | 519 | CHANDLER AVE | 41-08-476-005 | Completed | 2024-08-08 | 2024-09-03 | 2024-08-08 | 2024-08-20 | 2024-09-03 | 2024-09-03
CHATHAM DR | 702 | CHATHAM DR | 46-26-231-059 | Completed | 2023-07-24 | 2024-07-09 |  |  | 2023-07-24 | 2024-07-09
CHATHAM DR | 1416 | CHATHAM DR | 46-26-251-016 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
CHATHAM DR | 1423 | CHATHAM DR | 46-26-252-021 | No restoration work needed; door hanger left 8/23/24
CHELAN ST | 2035 | CHELAN ST | 41-17-480-009 | Completed | 2024-08-09 | 2024-08-13 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-13
CHELSEA CIR | 1702 | CHELSEA CIR | 40-24-107-013 | Completed | 2024-08-21 | 2024-09-05 | 2024-08-21 | 2024-08-26 | 2024-09-05 | 2024-09-05
CHELSEA CIR | 1706 | CHELSEA CIR | 40-24-107-014 | Completed | 2024-08-21 | 2024-09-05 | 2024-08-21 | 2024-08-26 | 2024-09-05 | 2024-09-05
CHEROKEE AVE | 3009 | CHEROKEE AVE | 41-20-427-007 | Completed | 2024-07-11 | 2024-07-18 | 2024-07-11 | 2024-07-16 | 2024-07-18 | 2024-07-18
CHEROKEE AVE | 3417 | CHEROKEE AVE | 41-20-476-010 | Completed | 2024-07-11 | 2024-07-19 | 2024-07-11 | 2024-07-19 | 2024-07-18 | 2024-07-18
CHEROKEE AVE | 3814 | CHEROKEE AVE | 41-29-205-033 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CHEROKEE AVE | 3914 | CHEROKEE AVE | 41-29-228-003 | Completed | 2024-07-11 | 2024-07-19 | 2024-07-11 | 2024-07-19 | 2024-07-18 | 2024-07-18
CHERRYLAWN DR | 1822 | CHERRYLAWN DR | 46-35-128-035 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
CHERRYLAWN DR | 1918 | CHERRYLAWN DR | 46-35-128-027 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-16 | 2024-09-18 | 2024-09-18
CHEYENNE AVE | 2914 | CHEYENNE AVE | 41-20-428-022 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CHEYENNE AVE | 2917 | CHEYENNE AVE | 41-20-429-005 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CHEYENNE AVE | 3810 | CHEYENNE AVE | 41-29-227-010 | Completed | 2024-10-11 | 2024-10-15 | 2024-10-11 | 2024-10-11 | 2024-10-15 | 2024-10-15
CHEYENNE AVE | 3814 | CHEYENNE AVE | 41-29-227-011 | No restoration work needed; door hanger left 10/2/24
CHEYENNE AVE | 4424 | CHEYENNE AVE | 41-29-276-050 | Completed | 2024-07-12 | 2024-07-12 |  |  | 2024-07-12 | 2024-07-12
CHEYENNE AVE | 4428 | CHEYENNE AVE | 41-29-276-051 | Completed | 2024-07-12 | 2024-07-12 |  |  | 2024-07-12 | 2024-07-12
CHEYENNE AVE | 4506 | CHEYENNE AVE | 41-29-276-054 | Completed | 2020-09-16 | 2024-07-16 | 2020-09-16 | 2020-09-16 | 2024-07-16 | 2024-07-16
CHURCH ST | 1507 | CHURCH ST | 41-18-383-037 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
CHURCHILL AVE | 2517 | CHURCHILL AVE | 41-05-481-030 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
CHURCHILL AVE | 2518 | CHURCHILL AVE | 41-05-485-004 | No restoration work needed; door hanger left 8/18/24
CHURCHILL AVE | 2521 | CHURCHILL AVE | 41-05-481-031 | Completed | 2024-09-18 | 2024-10-02 | 2024-09-18 | 2024-09-18 | 2024-10-02 | 2024-10-02
CHURCHILL AVE | 2618 | CHURCHILL AVE | 41-05-485-013 | No restoration work needed; door hanger left 8/18/24
CIRCLE DR | 2722 | CIRCLE DR | 41-20-178-019 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 2822 | CIRCLE DR | 41-20-178-021 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3001 | CIRCLE DR | 41-20-403-001 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3002 | CIRCLE DR | 41-20-401-001 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3010 | CIRCLE DR | 41-20-401-002 | Completed | 2024-07-11 | 2024-09-03 | 2024-07-11 | 2024-08-29 | 2024-09-03 | 2024-09-03
CIRCLE DR | 3019 | CIRCLE DR | 41-20-403-005 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3030 | CIRCLE DR | 41-20-401-004 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3101 | CIRCLE DR | 41-20-403-007 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3114 | CIRCLE DR | 41-20-401-006 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3122 | CIRCLE DR | 41-20-401-008 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3123 | CIRCLE DR | 41-20-403-009 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3201 | CIRCLE DR | 41-20-403-010 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3216 | CIRCLE DR | 41-20-401-011 | Completed | 2024-08-13 | 2024-08-13 | Not needed |  | 2024-08-13 | 2024-08-13
CIRCLE DR | 3224 | CIRCLE DR | 41-20-401-012 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3301 | CIRCLE DR | 41-20-452-001 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3309 | CIRCLE DR | 41-20-452-002 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3412 | CIRCLE DR | 41-20-451-005 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3417 | CIRCLE DR | 41-20-452-007 | No restoration work needed; door hanger left 9/11/24
CIRCLE DR | 3418 | CIRCLE DR | 41-20-451-006 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3501 | CIRCLE DR | 41-20-452-008 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3502 | CIRCLE DR | 41-20-451-007 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3601 | CIRCLE DR | 41-20-454-005 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CIRCLE DR | 3602 | CIRCLE DR | 41-20-376-015 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3611 | CIRCLE DR | 41-20-454-004 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3612 | CIRCLE DR | 41-20-376-012 | No restoration work needed; door hanger left 8/13/24
CIRCLE DR | 3617 | CIRCLE DR | 41-20-454-003 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3709 | CIRCLE DR | 41-20-377-004 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3714 | CIRCLE DR | 41-20-376-006 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3715 | CIRCLE DR | 41-20-377-003 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3813 | CIRCLE DR | 41-29-201-020 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3814 | CIRCLE DR | 41-29-126-027 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3818 | CIRCLE DR | 41-29-126-028 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CIRCLE DR | 3902 | CIRCLE DR | 41-29-127-023 | No restoration work needed; door hanger left 8/12/24
CIRCLE DR | 3907 | CIRCLE DR | 41-29-202-002 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CIRCLE DR | 4011 | CIRCLE DR | 41-29-203-003 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
CIRCLE DR | 4306 | CIRCLE DR | 41-29-178-047 | No restoration work needed; door hanger left 7/25/24
CIRCLE DR | 4408 | CIRCLE DR | 41-29-179-027 | No restoration work needed; door hanger left 7/25/24
CLAIRMONT ST | 3617 | CLAIRMONT ST | 40-22-281-010 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
CLAIRMONT ST | 3618 | CLAIRMONT ST | 40-22-279-028 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
CLAIRMONT ST | 3705 | CLAIRMONT ST | 40-22-281-006 | Completed | 2024-09-19 | 2024-09-19 |  |  | 2024-09-19 | 2024-09-19
CLAIRMONT ST | 3713 | CLAIRMONT ST | 40-22-281-003 | No restoration work needed; door hanger left 8/14/24
CLAIRMONT ST | 3714 | CLAIRMONT ST | 40-22-279-017 | No restoration work needed; door hanger left 8/14/24
CLAIRMONT ST | 3717 | CLAIRMONT ST | 40-22-281-002 | No restoration work needed; door hanger left 8/14/24
CLAIRMONT ST | 3721 | CLAIRMONT ST | 40-22-281-001 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
CLAIRMONT ST | 3814 | CLAIRMONT ST | 40-22-278-032 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-09 | 2024-09-19 | 2024-09-19
CLAIRMONT ST | 3913 | CLAIRMONT ST | 40-22-280-006 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-09 | 2024-09-19 | 2024-09-19
CLANCY AVE | 1310 | CLANCY AVE | 40-23-133-046 | Completed | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-05 | Not needed
CLEMENT ST | 2010 | CLEMENT ST | 40-11-277-030 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
CLEMENT ST | 2947 | CLEMENT ST | 40-11-102-005 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
CLEMENT ST | 3007 | CLEMENT ST | 40-02-359-012 | No restoration work needed; door hanger left 8/21/24
CLEMENT ST | 3305 | CLEMENT ST | 40-03-483-006 | No restoration work needed; door hanger left 8/21/24
CLEVELAND AVE | 1375 | CLEVELAND AVE | 41-07-278-021 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
CLIFFORD ST | 2019 | CLIFFORD ST | 41-18-485-030 | No restoration work needed; door hanger left 7/31/24
CLIFFORD ST | 2027 | CLIFFORD ST | 41-18-485-011 | No restoration work needed; door hanger left 7/31/24 | 2023-08-21 | 2023-08-21 | Sidewalk was missing when VI'd 4/6/23; replaced when revisited |  | 2023-08-21 | 2023-08-21
CLINTON ST | 519 | CLINTON ST | 41-30-251-011 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CLINTON ST | 648 | CLINTON ST | 41-30-135-013 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CLINTON ST | 652 | CLINTON ST | 41-30-135-012 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CLINTON ST | 806 | CLINTON ST | 41-30-110-028 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CLINTON ST | 842 | CLINTON ST | 41-30-110-021 | Completed | 2024-07-23 | 2024-08-09 | 2024-07-23 | 2024-08-05 | 2024-08-09 | 2024-08-09
CLINTON ST | 845 | CLINTON ST | 41-30-152-005 | No restoration work needed; door hanger left 7/26/24
CLINTON ST | 849 | CLINTON ST | 41-30-152-004 | Completed | 2019-09-18 | 2024-07-18 | 2019-09-18 | 2019-09-18 | 2024-07-18 | 2024-07-18
CLIO RD | 2524 | CLIO RD | 40-02-156-011 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
CLIO RD | 2637 | CLIO RD | 40-02-151-010 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
CLIO RD | 3221 | CLIO RD | 40-02-106-004 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
CLOVERDALE PL | 340 | CLOVERDALE PL | 40-14-151-015 | No restoration work needed; door hanger left 8/16/24
CLOVERLAWN DR | 4702 | CLOVERLAWN DR | 46-35-130-006 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
CLOVERLAWN DR | 4717 | CLOVERLAWN DR | 46-35-105-053 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
CLOVERLAWN DR | 4808 | CLOVERLAWN DR | 46-35-130-002 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
CLOVERLAWN DR | 5805 | CLOVERLAWN DR | 46-26-302-025 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
COGGINS AVE | 3910 | COGGINS AVE | 47-33-354-012 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
COGGINS AVE | 4123 | COGGINS AVE | 47-33-306-022 | No restoration work needed; door hanger left 7/17/24
COLCHESTER RD | 1911 | COLCHESTER RD | 40-23-401-008 | No restoration work needed; door hanger left 7/30/24
COLFAX AVE | 2211 | COLFAX AVE | 40-24-151-003 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
COLLADAY CT | 2123 | COLLADAY CT | 41-08-203-033 | No restoration work needed; door hanger left 7/18/24
COLONIAL DR | 6709 | COLONIAL DR | 46-26-204-034 | No restoration work needed; door hanger left 8/23/24
COLONIAL DR | 6802 | COLONIAL DR | 46-26-205-009 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-25 | 2024-10-08 | 2024-10-08
COLORADO AVE | 1733 | COLORADO AVE | 41-05-131-042 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
COLORADO AVE | 1802 | COLORADO AVE | 41-05-133-045 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
COLORADO AVE | 2901 | COLORADO AVE | 41-04-103-027 | No restoration work needed; door hanger left 7/17/24
COLORADO AVE | 2909 | COLORADO AVE | 41-04-103-030 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
COLORADO AVE | 2917 | COLORADO AVE | 41-04-103-033 | No restoration work needed; door hanger left 7/17/24
COLORADO AVE | 3013 | COLORADO AVE | 41-04-103-039 | No restoration work needed; door hanger left 7/17/24
COLORADO AVE | 3218 | COLORADO AVE | 41-04-129-021 | No restoration work needed; door hanger left 7/17/24
COLUMBIA DR | 1307 | COLUMBIA DR | 41-07-107-010 | No restoration work needed; door hanger left 8/18/24
COMANCHE AVE | 3310 | COMANCHE AVE | 41-20-453-018 | No restoration work needed; door hanger left 8/12/24
COMANCHE AVE | 3617 | COMANCHE AVE | 41-20-457-022 | Completed | 2024-07-11 | 2024-07-18 | 2024-07-11 | 2024-07-16 | 2024-07-18 | 2024-07-18
COMMONWEALTH AVE | 205 | COMMONWEALTH AVE | 41-08-432-003 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
COMMONWEALTH AVE | 234 | COMMONWEALTH AVE | 41-08-429-028 | No restoration work needed; door hanger left 7/23/24
COMMONWEALTH AVE | 440 | COMMONWEALTH AVE | 41-08-407-017 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
COMMONWEALTH AVE | 808 | COMMONWEALTH AVE | 41-08-456-017 | Completed | 2024-08-08 | 2024-09-03 | 2024-08-08 | 2024-08-20 | 2024-09-03 | 2024-09-03
CONCORD ST | 2840 | CONCORD ST | 40-11-127-022 | Completed | 2024-08-08 |  | 2024-08-08 |  | 2024-07-16 | 2024-07-16
CONCORD ST | 2843 | CONCORD ST | 40-11-129-006 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
CONCORD ST | 2844 | CONCORD ST | 40-11-127-021 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
CONCORD ST | 2913 | CONCORD ST | 40-11-101-001 | No restoration work needed; door hanger left 7/16/24
CONCORD ST | 2914 | CONCORD ST | 40-02-356-022 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
CONCORD ST | 2932 | CONCORD ST | 40-02-356-027 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
CONCORD ST | 2937 | CONCORD ST | 40-02-358-005 | No restoration work needed; door hanger left 7/16/24
CONCORD ST | 2944 | CONCORD ST | 40-02-356-017 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
CONCORD ST | 3030 | CONCORD ST | 40-02-355-016 | Completed | 2024-10-21 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-21
COPEMAN BLVD | 602 | COPEMAN BLVD | 40-12-104-027 | Completed
COPEMAN BLVD | 611 | COPEMAN BLVD | 40-12-109-008 | Completed | 2024-09-20 | 2024-10-18 | 2024-09-20 | 2024-09-26 | 2024-10-18 | 2024-10-18
COPEMAN BLVD | 711 | COPEMAN BLVD | 40-11-230-015 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
COPEMAN BLVD | 935 | COPEMAN BLVD | 40-11-229-034 | No restoration work needed; door hanger left 7/16/24
COPEMAN BLVD | 2219 | COPEMAN BLVD | 40-02-311-006 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
CORNELIA ST | 831 | CORNELIA ST | 41-07-117-043 | No restoration work needed; door hanger left 7/30/24
CORUNNA RD | 2116 | CORUNNA RD | 40-14-480-038 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
CORUNNA RD | 2502 | CORUNNA RD | 40-14-462-028 | No restoration work needed; door hanger left 7/29/24
CORUNNA RD | 3215 | CORUNNA RD | 40-23-104-002 | Completed | 2024-10-24 | 2024-10-31 | 2024-10-24 | 2024-10-24 | 2024-10-31 | 2024-10-31
COTTAGE GROVE AVE | 531 | COTTAGE GROVE AV | 40-13-106-014 | No restoration work needed; house demo'd 8/16/24
COVENTRY CT | 2707 | COVENTRY CT | 40-14-330-004 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
CRANWOOD DR | 6602 | CRANWOOD DR | 46-26-231-024 | No restoration work needed; door hanger left 8/23/24
CRANWOOD DR | 6621 | CRANWOOD DR | 46-26-230-038 | No restoration work needed; door hanger left 7/9/24
CRANWOOD DR | 6818 | CRANWOOD DR | 46-26-231-008 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
CRAPO ST | 514 | CRAPO ST | 41-07-453-043 | Completed | 2024-10-22 | 2024-11-07 | 2024-10-22 | 2024-11-07 | 2024-10-26 | 2024-10-26
CRAPO ST | 518 | CRAPO ST | 41-07-453-044 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
CRAPO ST | 612 | CRAPO ST | 41-07-476-012 | Completed | 2024-09-19 | 2024-10-19 | 2024-09-19 | 2024-09-19 | 2024-10-19 | 2024-10-19
CRAPO ST | 710 | CRAPO ST | 41-07-477-022 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
CRAWFORD ST | 702 | CRAWFORD ST | 41-30-130-027 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CRAWFORD ST | 809 | CRAWFORD ST | 41-30-108-016 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CRAWFORD ST | 817 | CRAWFORD ST | 41-30-108-031 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
CRAWFORD ST | 830 | CRAWFORD ST | 41-30-106-025 | No restoration work needed; door hanger left 7/26/24
CRAWFORD ST | 1012 | CRAWFORD ST | 40-25-231-029 | No restoration work needed; door hanger left 7/26/24
CRAWFORD ST | 1032 | CRAWFORD ST | 40-25-231-023 | No restoration work needed; door hanger left 7/26/24
CRAWFORD ST | 1220 | CRAWFORD ST | 40-25-230-023 | No restoration work needed; door hanger left 7/29/24
CRAWFORD ST | 1314 | CRAWFORD ST | 40-25-230-014 | No restoration work needed; door hanger left 7/26/24
CRESTBROOK LN | 1601 | CRESTBROOK LN | 40-25-251-021 | Completed | 2024-07-22 | 2024-07-31 | 2024-07-22 | 2024-07-24 | 2024-07-31 | 2024-07-31
CROCKER AVE | 2026 | CROCKER AVE | 41-17-358-029 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
CROCKER AVE | 2122 | CROCKER AVE | 41-20-104-014 | No restoration work needed; door hanger left 7/24/24
CROMWELL AVE | 1620 | CROMWELL AVE | 41-08-378-006 | No restoration work needed; door hanger left 7/23/24
CUMINGS AVE | 2118 | CUMINGS AVE | 40-23-227-026 | Completed | 2024-08-22 | 2024-09-05 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-05
CUMINGS AVE | 2302 | CUMINGS AVE | 40-23-226-024 | Completed | 2024-08-28 | 2024-09-18 | 2024-08-28 | 2024-09-13 | 2024-09-18 | 2024-09-18
CUMINGS AVE | 2406 | CUMINGS AVE | 40-23-226-018 | No restoration work needed; door hanger left 8/13/24
CUMINGS AVE | 2602 | CUMINGS AVE | 40-23-205-026 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
CUMINGS AVE | 2645 | CUMINGS AVE | 40-23-208-001 | No restoration work needed; door hanger left 8/13/24
CUMINGS AVE | 2707 | CUMINGS AVE | 40-23-207-008 | No restoration work needed; door hanger left 8/13/24
CUSTER AVE | 4309 | CUSTER AVE | 41-29-177-018 | No restoration work needed; door hanger left 7/25/24
CUSTER AVE | 4310 | CUSTER AVE | 41-29-176-058 | Completed | 2024-07-11 | 2024-07-18 | 2024-07-11 | 2024-07-16 | 2024-07-18 | 2024-07-18
CUTHBERTSON ST | 4012 | CUTHBERTSON ST | 41-30-203-025 | No restoration work needed; door hanger left 7/17/24
DAKOTA AVE | 1420 | DAKOTA AVE | 41-05-155-010 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DAKOTA AVE | 1717 | DAKOTA AVE | 41-05-179-031 | Completed | 2024-10-21 | 2024-11-07 | 2024-10-21 | 2024-11-07 | 2024-10-31 | 2024-10-31
DAKOTA AVE | 3027 | DAKOTA AVE | 41-04-158-013 | Completed | 2024-10-10 | 2024-10-16 | 2024-10-10 | 2024-10-16 | 2024-10-15 | 2024-10-15
DAMON ST | 746 | DAMON ST | 47-31-303-014 | No restoration work needed; door hanger left 8/20/24
DARLING ST | 963 | DARLING ST | 40-15-481-005 | No restoration work needed; door hanger left 8/15/24
DARYLL DR | 6514 | DARYLL DR | 46-26-230-030 | Completed | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-09-30 | Not needed
DARYLL DR | 7005 | DARYLL DR | 46-26-226-007 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
DARYLL DR | 7014 | DARYLL DR | 46-26-227-004 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
DAVIS ST | 925 | DAVIS ST | 40-13-427-023 | Completed | 2024-10-14 | 2024-10-17 | 2024-10-14 | 2024-10-17 | Not needed
DAVISON RD | 1271 | DAVISON RD | 41-06-482-028 | No restoration work needed; door hanger left 7/18/24
DAVISON RD | 2221 | DAVISON RD | 41-05-458-029 | Completed | 2024-10-24 | 2024-10-29 | 2024-10-24 | 2024-10-29 | Not needed
DAWSON ST | 2607 | DAWSON ST | 41-19-254-003 | Completed | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17
DEARBORN ST | 3622 | DEARBORN ST | 41-20-455-014 | No restoration work needed; door hanger left 7/11/24
DEARBORN ST | 3708 | DEARBORN ST | 41-20-455-019 | Completed | 2024-07-12 | 2024-07-19 | 2024-07-12 | 2024-07-19 | 2024-07-18 | 2024-07-18
DECKER ST | 1011 | DECKER ST | 41-07-284-013 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
DECKER ST | 1220 | DECKER ST | 41-08-152-002 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 1457 | DELAWARE AVE | 41-05-157-025 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
DELAWARE AVE | 1510 | DELAWARE AVE | 41-05-302-003 | Completed | 2024-10-15 | 2024-10-31 | 2024-10-15 | 2024-10-30 | 2024-10-31 | 2024-10-31
DELAWARE AVE | 1602 | DELAWARE AVE | 41-05-326-001 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 1801 | DELAWARE AVE | 41-05-183-031 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 1809 | DELAWARE AVE | 41-05-183-033 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 1810 | DELAWARE AVE | 41-05-327-013 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 1829 | DELAWARE AVE | 41-05-183-040 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 2001 | DELAWARE AVE | 41-05-401-011 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
DELAWARE AVE | 2017 | DELAWARE AVE | 41-05-401-015 | Completed | 2024-10-15 | 2024-10-31 | 2024-10-15 | 2024-10-18 | 2024-10-31 | 2024-10-31
DELAWARE AVE | 2221 | DELAWARE AVE | 41-05-401-029 | Completed | 2024-10-15 | 2024-10-31 | 2024-10-15 | 2024-10-30 | 2024-10-31 | 2024-10-31
DELAWARE AVE | 3151 | DELAWARE AVE | 41-04-326-015 | No restoration work needed; door hanger left 10/4/24
DELAWARE AVE | 3223 | DELAWARE AVE | 41-04-327-005 | Completed | 2024-10-15 | 2024-10-16 | 2024-10-15 | 2024-10-16 | Not needed
DELAWARE AVE | 3227 | DELAWARE AVE | 41-04-327-006 | No restoration work needed; door hanger left 10/4/24
DELAWARE AVE | 3710 | DELAWARE AVE | 41-04-427-004 | No restoration work needed; door hanger left 7/17/24
DELAWARE AVE | 3717 | DELAWARE AVE | 41-04-426-005 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DELAWARE AVE | 3829 | DELAWARE AVE | 41-04-426-030 | Completed | 2024-10-15 | 2024-10-31 | 2024-10-15 | 2024-10-18 | 2024-10-31 | 2024-10-31
DELIA ST | 317 | DELIA ST | 40-01-455-014 | No restoration work needed; door hanger left 8/19/24
DELMAR AVE | 2305 | DELMAR AVE | 40-02-402-031 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DELMAR AVE | 2334 | DELMAR AVE | 40-02-403-013 | Completed | 2024-09-11 | 2024-09-17 | 2024-09-11 | 2024-09-17
DELMAR AVE | 2337 | DELMAR AVE | 40-02-402-022 | Completed | 2024-09-11 | 2024-09-17 | 2024-09-11 | 2024-09-17
DICKINSON ST | 717 | DICKINSON ST | 40-14-253-050 | No restoration work needed; door hanger left 8/16/24
DOLPHAINE LN | 3610 | DOLPHAINE LN | 41-04-203-011 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3701 | DOLPHAINE LN | 47-33-476-030 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3702 | DOLPHAINE LN | 41-04-226-074 | No restoration work needed; door hanger left 7/23/24
DOLPHAINE LN | 3710 | DOLPHAINE LN | 41-04-226-003 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3718 | DOLPHAINE LN | 41-04-226-004 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3722 | DOLPHAINE LN | 41-04-226-006 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DOLPHAINE LN | 3725 | DOLPHAINE LN | 47-33-477-021 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3726 | DOLPHAINE LN | 41-04-226-007 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3730 | DOLPHAINE LN | 41-04-226-008 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DOLPHAINE LN | 3732 | DOLPHAINE LN | 41-04-226-009 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3738 | DOLPHAINE LN | 41-04-226-010 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3742 | DOLPHAINE LN | 41-04-226-011 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3746 | DOLPHAINE LN | 41-04-226-012 | No restoration work needed; door hanger left 7/17/24
DOLPHAINE LN | 3750 | DOLPHAINE LN | 41-04-226-013 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3813 | DOLPHAINE LN | 47-33-476-057 | No restoration work needed; door hanger left 8/28/24
DOLPHAINE LN | 3819 | DOLPHAINE LN | 47-33-476-058 | No restoration work needed; door hanger left 7/17/24
DOLPHAINE LN | 3825 | DOLPHAINE LN | 47-33-476-089 | No restoration work needed; door hanger left 7/17/24
DOLPHAINE LN | 3831 | DOLPHAINE LN | 47-33-476-094 | No restoration work needed; door hanger left 7/17/24
DOLPHAINE LN | 3845 | DOLPHAINE LN | 47-33-476-093 | No restoration work needed; door hanger left 7/17/24
DONALDSON ST | 1127 | DONALDSON ST | 40-10-282-010 | No restoration work needed; door hanger left 8/21/24
DOROTHY DR | 1723 | DOROTHY DR | 41-09-204-009 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DUPONT ST | 1451 | DUPONT ST | 40-11-277-044 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
DUPONT ST | 1501 | DUPONT ST | 40-11-276-038 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
DUPONT ST | 1508 | DUPONT ST | 40-12-152-014 | Completed | 2024-10-17 | 2024-10-30 | 2024-10-17 | 2024-10-21 | 2024-10-30 | 2024-10-30
DUPONT ST | 1512 | DUPONT ST | 40-12-152-013 | No restoration work needed; C/P home, no door hanger left
DUPONT ST | 1559 | DUPONT ST | 40-11-232-032 | Completed | 2024-10-17 | 2024-11-01 | 2024-10-17 | 2024-10-21 | 2024-11-01 | 2024-11-01
DUPONT ST | 2017 | DUPONT ST | 40-02-479-030 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
DUPONT ST | 2117 | DUPONT ST | 40-02-479-024 | No restoration work needed; door hanger left 8/20/24
DUPONT ST | 2710 | DUPONT ST | 40-01-151-009 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
DUPONT ST | 2801 | DUPONT ST | 40-02-278-031 | No restoration work needed; door hanger left 8/20/24
DUPONT ST | 3102 | DUPONT ST | 40-01-105-003 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
DUPONT ST | 3112 | DUPONT ST | 40-01-105-002 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
DUPONT ST | 3212 | DUPONT ST | 40-01-103-004 | No restoration work needed; door hanger left 8/20/24
DUPONT ST | 3301 | DUPONT ST | 40-02-228-011 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
DUPONT ST | 5716 | DUPONT ST | 46-25-303-002 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
DUPONT ST | 5905 | DUPONT ST | 46-26-429-028 | Completed | 2024-09-25 | 2024-10-02 | 2024-09-25 | 2024-09-25 | 2024-10-02 | 2024-10-02
DUPONT ST | 7001 | DUPONT ST | 46-26-228-027 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
DURAND ST | 1419 | DURAND ST | 40-24-101-003 | Completed | 2024-08-22 | 2024-08-29 | 2024-08-22 | 2024-08-29 | Not needed
DURAND ST | 1431 | DURAND ST | 40-24-101-006 | No restoration work needed; door hanger left 8/13/24
DWIGHT AVE | 2015 | DWIGHT AVE | 41-17-357-006 | Completed | 2024-08-01 | 2024-08-13 | 2024-08-01 | 2024-08-12 | 2024-08-13 | 2024-08-13
E ALMA AVE | 522 | E ALMA AVE | 46-25-229-013 | Completed | 2024-08-16 | 2024-09-05 | 2024-08-16 | 2024-09-05 | Not needed
E ALMA AVE | 738 | E ALMA AVE | 47-30-104-011 | No restoration work needed; door hanger left 8/15/24
E ALMA AVE | 901 | E ALMA AVE | 47-30-130-026 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
E ATHERTON RD | 465 | E ATHERTON RD | 41-20-376-002 | No restoration work needed; door hanger left 8/12/24
E ATHERTON RD | 522 | E ATHERTON RD | 41-29-201-044 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E ATHERTON RD | 601 | E ATHERTON RD | 41-20-454-012 | No restoration work needed; door hanger left 8/12/24
E ATHERTON RD | 628 | E ATHERTON RD | 41-29-201-015 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E ATHERTON RD | 816 | E ATHERTON RD | 41-29-205-010 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E AUSTIN AVE | 509 | E AUSTIN AVE | 46-25-280-027 | No restoration work needed; door hanger left 8/15/24
E AUSTIN AVE | 1053 | E AUSTIN AVE | 47-30-181-047 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E BAKER ST | 237 | E BAKER ST | 40-01-258-041 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
E BAKER ST | 305 | E BAKER ST | 40-01-260-011 | No restoration work needed; door hanger left 7/16/24
E BAKER ST | 422 | E BAKER ST | 40-01-403-007 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
E BAKER ST | 427 | E BAKER ST | 40-01-285-019 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
E BAKER ST | 630 | E BAKER ST | 40-01-427-010 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
E BALTIMORE BLVD | 217 | E BALTIMORE BLVD | 46-36-204-050 | Completed | 2023-09-08 | 2024-07-08 | 2023-09-08 | 2023-09-15 | 2024-07-08 | 2024-07-08
E BALTIMORE BLVD | 317 | E BALTIMORE BLVD | 46-36-204-056 | No restoration work needed; door hanger left 7/8/24
E BALTIMORE BLVD | 809 | E BALTIMORE BLVD | 47-31-132-021 | No restoration work needed; door hanger left 8/14/24
E BELVIDERE AVE | 142 | E BELVIDERE AVE | 41-19-431-014 | Completed | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-23 | 2024-07-31 | 2024-07-31
E BUNDY AVE | 1200 | E BUNDY AVE | 47-30-227-045 | Completed | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | Not needed
E CARPENTER RD | 358 | E CARPENTER RD | 46-25-202-011 | Completed | 2024-09-12 | 2024-09-18 | 2024-09-12 | 2024-09-12 | 2024-09-18 | 2024-09-18
E CARPENTER RD | 414 | E CARPENTER RD | 46-25-226-055 | Completed | 2024-09-12 | 2024-10-01 | 2024-09-12 | 2024-10-01 | 2024-10-01 | 2024-10-01
E COURT ST | 1604 | E COURT ST | 41-17-127-001 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E COURT ST | 1618 | E COURT ST | 41-17-127-004 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E COURT ST | 1622 | E COURT ST | 41-17-127-005 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E COURT ST | 1809 | E COURT ST | 41-08-384-024 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E COURT ST | 2034 | E COURT ST | 41-17-202-008 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
E COURT ST | 2114 | E COURT ST | 41-17-202-012 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E COURT ST | 2508 | E COURT ST | 41-17-227-002 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E COURT ST | 2610 | E COURT ST | 41-17-227-009 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E COURT ST | 2614 | E COURT ST | 41-17-227-010 | Completed | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-29 | 2024-07-31 | 2024-07-31
E COURT ST | 2618 | E COURT ST | 41-17-227-012 | No restoration work needed; door hanger left 9/3/24
E DARTMOUTH ST | 614 | E DARTMOUTH ST | 40-01-280-006 | Completed | 2024-09-11 | 2024-10-18 | 2024-09-11 | 2024-09-16 | 2024-10-18 | 2024-10-18
E DAYTON ST | 315 | E DAYTON ST | 40-01-402-013 | Completed | 2024-09-30 | 2024-10-03 | 2024-09-30 | 2024-10-03 | Not needed
E DAYTON ST | 626 | E DAYTON ST | 40-01-430-008 | Completed | 2024-09-30 | 2024-10-17 | 2024-09-30 | 2024-10-07 | 2024-10-17 | 2024-10-17
E DEWEY ST | 501 | E DEWEY ST | 40-01-227-022 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E DEWEY ST | 502 | E DEWEY ST | 40-01-229-001 | No restoration work needed; door hanger left 7/11/24
E EDDINGTON AVE | 138 | E EDDINGTON AVE | 41-19-428-013 | No restoration work needed; door hanger left 7/25/24 |  |  | 2023-09-27 | 2023-10-13 | 2023-10-19 | 2023-10-19
E EIGHTH ST | 818 | E EIGHTH ST | 41-18-280-008 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E EIGHTH ST | 830 | E EIGHTH ST | 41-18-280-013 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E EIGHTH ST | 834 | E EIGHTH ST | 41-18-280-014 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E EIGHTH ST | 842 | E EIGHTH ST | 41-18-280-016 | No restoration work needed; door hanger left 7/24/24
E EIGHTH ST | 845 | E EIGHTH ST | 41-18-277-030 | No restoration work needed; door hanger left 7/24/24
E EIGHTH ST | 846 | E EIGHTH ST | 41-18-280-031 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E EIGHTH ST | 902 | E EIGHTH ST | 41-18-281-002 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E EIGHTH ST | 915 | E EIGHTH ST | 41-18-229-011 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E FLINT PARK BLVD | 146 | E FLINT PARK BLVD | 46-36-253-011 | Completed | 2023-07-31 | 2024-07-08 | 2023-07-31 | 2023-08-01 | 2024-07-08 | 2024-07-08
E FORK DR | 917 | E FORK DR | 41-17-104-005 | No restoration work needed; door hanger left 8/9/24
E FOSS AVE | 333 | E FOSS AVE | 46-25-208-024 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E FOSS AVE | 357 | E FOSS AVE | 46-25-208-032 | No restoration work needed; door hanger left 7/11/24
E GENESEE ST | 317 | E GENESEE ST | 40-01-204-028 | No restoration work needed; door hanger left 8/20/24
E GENESEE ST | 406 | E GENESEE ST | 40-01-252-015 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E HAMILTON AVE | 151 | E HAMILTON AVE | 40-01-411-019 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 152 | E HAMILTON AVE | 40-01-415-001 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 214 | E HAMILTON AVE | 40-01-416-005 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
E HAMILTON AVE | 301 | E HAMILTON AVE | 40-01-413-011 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-26 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 529 | E HAMILTON AVE | 40-01-433-021 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-10-03 | 2024-10-03 | 2024-10-03
E HAMILTON AVE | 1438 | E HAMILTON AVE | 41-05-355-012 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
E HAMILTON AVE | 1504 | E HAMILTON AVE | 41-05-356-001 | No restoration work needed; door hanger left 7/18/24
E HAMILTON AVE | 1506 | E HAMILTON AVE | 41-05-356-003 | No restoration work needed; door hanger left 7/18/24
E HAMILTON AVE | 1810 | E HAMILTON AVE | 41-05-381-013 | No restoration work needed; door hanger left 7/18/24
E HEMPHILL RD | 337 | E HEMPHILL RD | 41-29-160-034 | Completed | 2024-07-31 | 2024-08-09 | 2024-07-31 | 2024-08-08 | 2024-08-09 | 2024-08-09
E HEMPHILL RD | 433 | E HEMPHILL RD | 41-29-180-019 | No restoration work needed; door hanger left 7/25/24
E HOBSON AVE | 249 | E HOBSON AVE | 46-25-405-031 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-08-28 | 2024-09-05 | 2024-09-05
E HOBSON AVE | 357 | E HOBSON AVE | 46-25-406-032 | No restoration work needed; door hanger left 8/14/24
E HOBSON AVE | 1217 | E HOBSON AVE | 47-30-406-029 | No restoration work needed; door hanger left 8/14/24
E HOLBROOK AVE | 738 | E HOLBROOK AVE | 47-30-105-038 | No restoration work needed; door hanger left 7/11/24
E HOLBROOK AVE | 762 | E HOLBROOK AVE | 47-30-105-019 | Completed | 2024-08-16 | 2024-09-05 | 2024-08-16 | 2024-08-28 | 2024-09-05 | 2024-09-05
E HOME AVE | 229 | E HOME AVE | 46-25-403-023 | No restoration work needed; door hanger left 8/14/24
E JACKSON AVE | 120 | E JACKSON AVE | 40-01-255-007 | Completed | 2024-09-18 | 2024-09-18 |  |  | 2024-09-18 | 2024-09-18
E JAMIESON ST | 626 | E JAMIESON ST | 40-01-231-020 | Completed | 2024-09-11 | 2024-10-02 | 2024-09-11 | 2024-09-16 | 2024-10-02 | 2024-10-02
E KEARSLEY ST | 724 | E KEARSLEY ST | 41-07-451-004 | Completed | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-10-31 | 2024-10-30 | 2024-10-30
E LAKEVIEW AVE | 120 | E LAKEVIEW AVE | 41-19-437-005 | Completed | 2020-07-11 | 2024-07-19 | 2020-07-11 | 2024-07-19
E LAKEVIEW AVE | 123 | E LAKEVIEW AVE | 41-19-434-019 | Completed | 2020-04-27 | 2024-07-16 | 2020-04-27 | 2020-06-18 | 2024-07-16 | 2024-07-16
E LAKEVIEW AVE | 144 | E LAKEVIEW AVE | 41-19-437-010 | Completed | 2020-07-11 | 2024-07-19 | 2020-07-11 | 2024-07-19 | 2024-07-18 | 2024-07-18
E LAKEVIEW AVE | 220 | E LAKEVIEW AVE | 41-19-437-016 | Completed | 2024-07-12 | 2024-07-19 | 2024-07-12 | 2024-07-19 | 2024-07-16 | 2024-07-16
E LORADO AVE | 510 | E LORADO AVE | 46-25-278-011 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-08-28 | 2024-09-05 | 2024-09-05
E LYNDON AVE | 306 | E LYNDON AVE | 46-25-453-002 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E LYNDON AVE | 505 | E LYNDON AVE | 46-25-476-025 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E LYNDON AVE | 715 | E LYNDON AVE | 47-30-352-014 | No restoration work needed; door hanger left 8/14/24
E LYNDON AVE | 739 | E LYNDON AVE | 47-30-352-020 | No restoration work needed; door hanger left 8/14/24
E MARENGO AVE | 513 | E MARENGO AVE | 46-36-227-047 | No restoration work needed; door hanger left 8/14/24
E MARENGO AVE | 662 | E MARENGO AVE | 46-36-228-036 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-09-05 | 2024-09-05 | 2024-09-05
E MARENGO AVE | 1038 | E MARENGO AVE | 47-31-131-013 | No restoration work needed; door hanger left 8/14/24
E MC CLELLAN ST | 905 | E MC CLELLAN ST | 41-06-129-050 | Completed | 2024-09-11 | 2024-10-30 | 2024-09-11 | 2024-09-11 | 2024-10-30 | 2024-10-30
E MOORE ST | 627 | E MOORE ST | 46-36-427-008 | No restoration work needed; door hanger left 9/4/24
E MOORE ST | 629 | E MOORE ST | 46-36-427-009 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E MOORE ST | 633 | E MOORE ST | 46-36-427-010 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E MOORE ST | 822 | E MOORE ST | 47-31-327-009 | No restoration work needed; door hanger left 8/20/24
E MOTT AVE | 318 | E MOTT AVE | 46-25-452-006 | No restoration work needed; door hanger left 8/14/24
E MOTT AVE | 342 | E MOTT AVE | 46-25-452-012 | No restoration work needed; door hanger left 8/14/24
E NINTH ST | 804 | E NINTH ST | 41-18-284-001 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-20
E NINTH ST | 814 | E NINTH ST | 41-18-284-007 | Completed | 2024-09-17 | 2024-09-27 | 2024-09-17 | 2024-09-27 | 2024-09-20 | 2024-09-20
E NINTH ST | 818 | E NINTH ST | 41-18-284-008 | Completed | 2024-09-18 | 2024-09-27 | 2024-09-18 | 2024-09-27 | 2024-09-20 | 2024-09-20
E NINTH ST | 825 | E NINTH ST | 41-18-280-023 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E NINTH ST | 834 | E NINTH ST | 41-18-284-012 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E NINTH ST | 842 | E NINTH ST | 41-18-284-015 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E NINTH ST | 909 | E NINTH ST | 41-18-281-011 | No restoration work needed; door hanger left 7/24/24
E PARKWAY AVE | 341 | E PARKWAY AVE | 46-25-453-026 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-09-05 | 2024-09-05 | 2024-09-05
E PARKWAY AVE | 734 | E PARKWAY AVE | 47-30-354-012 | No restoration work needed; door hanger left 8/14/24
E PASADENA AVE | 159 | E PASADENA AVE | 46-36-459-021 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E PASADENA AVE | 317 | E PASADENA AVE | 46-36-461-018 | No restoration work needed; door hanger left 9/3/24
E PASADENA AVE | 371 | E PASADENA AVE | 46-36-462-020 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E PASADENA AVE | 633 | E PASADENA AVE | 46-36-484-023 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E PASADENA AVE | 743 | E PASADENA AVE | 47-31-354-033 | No restoration work needed; door hanger left 10/1/24 | Appears city repaired sidewalk
E PHILADELPHIA BLV | 132 | E PHILADELPHIA BLV | 46-36-204-009 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E PIERSON RD | 313 | E PIERSON RD | 46-25-455-018 | Completed | 2024-09-10 | 2024-10-02 | 2024-09-10 | 2024-09-10 | 2024-10-02 | 2024-10-02
E PIERSON RD | 318 | E PIERSON RD | 46-36-201-021 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E PIERSON RD | 410 | E PIERSON RD | 46-36-226-007 | Completed | 2024-09-10 | 2024-10-02 | 2024-09-10 | 2024-09-10 | 2024-10-02 | 2024-10-24
E PIERSON RD | 905 | E PIERSON RD | 47-30-378-018 | Completed | 2024-07-26 | 2024-07-31 | 2024-07-26 | 2024-07-29 | 2024-07-31 | 2024-07-31
E PIERSON RD | 1133 | E PIERSON RD | 47-30-462-030 | Completed | 2024-09-10 | 2024-10-21 | 2024-09-10 | 2024-09-10 | 2024-10-21 | 2024-10-21
E PIPER AVE | 121 | E PIPER AVE | 46-25-327-007 | No restoration work needed; door hanger left 8/15/24
E PIPER AVE | 353 | E PIPER AVE | 46-25-402-015 | No restoration work needed; door hanger left 8/15/24
E PIPER AVE | 505 | E PIPER AVE | 46-25-426-009 | No restoration work needed; door hanger left 8/15/24
E PULASKI ST | 414 | E PULASKI ST | 46-36-227-010 | No restoration work needed; door hanger left 8/14/24
E RANKIN ST | 116 | E RANKIN ST | 40-01-258-006 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
E RIDGEWAY AVE | 330 | E RIDGEWAY AVE | 46-25-455-009 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-08-28 | 2024-09-05 | 2024-09-05
E RIDGEWAY AVE | 601 | E RIDGEWAY AVE | 46-25-481-012 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E RIDGEWAY AVE | 637 | E RIDGEWAY AVE | 46-25-481-027 | Completed | 2024-08-15 | 2024-09-05 | 2024-08-15 | 2024-08-28 | 2024-09-05 | 2024-09-05
E RIDGEWAY AVE | 802 | E RIDGEWAY AVE | 47-30-378-001 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E RIDGEWAY AVE | 1126 | E RIDGEWAY AVE | 47-30-458-007 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
E RUSSELL AVE | 642 | E RUSSELL AVE | 46-25-285-011 | Completed | 2020-06-29 | 2024-07-11 | 2020-06-29 | 2020-06-29 | 2024-07-11 | 2024-07-11
E SECOND ST | 610 | E SECOND ST | 41-18-202-003 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E SECOND ST | 627 | E SECOND ST | 41-07-451-019 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
E SECOND ST | 914 | E SECOND ST | 41-07-476-008 | No restoration work needed; door hanger left 7/24/24
E SECOND ST | 1714 | E SECOND ST | 41-08-378-003 | No restoration work needed; door hanger left 8/8/24
E SECOND ST | 2123 | E SECOND ST | 41-08-409-010 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E SECOND ST | 2132 | E SECOND ST | 41-08-452-007 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
E SEVENTH ST | 821 | E SEVENTH ST | 41-18-276-027 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E SEVENTH ST | 822 | E SEVENTH ST | 41-18-277-009 | No restoration work needed; door hanger left 7/24/24
E SEVENTH ST | 825 | E SEVENTH ST | 41-18-276-028 | No restoration work needed; door hanger left 7/24/24
E SEVENTH ST | 826 | E SEVENTH ST | 41-18-277-010 | No restoration work needed; door hanger left 7/24/24
E SEVENTH ST | 829 | E SEVENTH ST | 41-18-276-029 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
E SEVENTH ST | 846 | E SEVENTH ST | 41-18-277-016 | No restoration work needed; door hanger left 7/24/24
E SEVENTH ST | 849 | E SEVENTH ST | 41-18-276-034 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E SIXTH ST | 718 | E SIXTH ST | 41-18-276-009 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E STEWART AVE | 129 | E STEWART AVE | 46-36-255-025 | No restoration work needed; door hanger left 10/8/24
E STEWART AVE | 822 | E STEWART AVE | 47-31-326-009 | Completed | 2024-08-05 | 2024-08-19 | 2024-08-05 | 2024-08-19 | 2024-08-09 | 2024-08-09
E STEWART AVE | 832 | E STEWART AVE | 47-31-326-012 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
E THIRD ST | 621 | E THIRD ST | 41-18-202-018 | No restoration work needed; door hanger left 7/24/24
E THIRD ST | 714 | E THIRD ST | 41-18-207-004 | Completed | 2024-09-13 | 2024-10-18 | 2024-09-13 | 2024-10-07 | 2024-10-18 | 2024-10-18
E THIRD ST | 806 | E THIRD ST | 41-18-208-003 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E TWELFTH ST | 706 | E TWELFTH ST | 41-17-309-002 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E VAN WAGONER AVE | 221 | E VAN WAGONER AVE | 46-36-452-012 | Completed | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | Not needed
E WELLINGTON AVE | 824 | E WELLINGTON AVE | 41-17-152-011 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E WELLINGTON AVE | 929 | E WELLINGTON AVE | 41-17-151-020 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
E WITHERBEE ST | 302 | E WITHERBEE ST | 40-01-454-001 | Completed | 2024-09-30 | 2024-10-17 | 2024-09-30 | 2024-10-03 | 2024-10-17 | 2024-10-17
E WITHERBEE ST | 306 | E WITHERBEE ST | 40-01-455-004 | Completed | 2024-09-30 | 2024-10-17 | 2024-09-30 | 2024-10-07 | 2024-10-17 | 2024-10-17
E WOOD ST | 470 | E WOOD ST | 40-12-276-063 | Completed | 2024-09-20 | 2024-10-21 | 2024-09-20 | 2024-09-26 | 2024-10-21 | 2024-10-21
E YORK AVE | 1001 | E YORK AVE | 47-30-129-023 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
EAST ST | 724 | EAST ST | 41-18-203-021 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
EASTHAMPTON DR | 3437 | EASTHAMPTON DR | 41-16-226-034 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
EASTHAMPTON DR | 3620 | EASTHAMPTON DR | 41-16-229-005 | No restoration work found; door hanger left 10/10/24 | Blue paint from COF that says sidewalk settling is not from SLE work
EASTHAMPTON DR | 3719 | EASTHAMPTON DR | 41-16-228-030 | Completed | 2024-10-11 | 2024-10-15 | 2024-10-11 | 2024-10-11 | 2024-10-15 | 2024-10-15
EATON PL | 2734 | EATON PL | 47-28-355-071 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
EATON PL | 2738 | EATON PL | 47-28-355-070 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
EDITH AVE | 1141 | EDITH AVE | 40-24-431-002 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
EDMUND ST | 414 | EDMUND ST | 46-36-476-004 | Completed | 2024-10-02 | 2024-10-16 | 2024-10-02 | 2024-10-16 | Not needed
EDMUND ST | 713 | EDMUND ST | 47-31-304-016 | Completed | 2024-10-02 | 2024-10-16 | 2024-10-02 | 2024-10-16 | 2024-10-15 | 2024-10-15
EDWARDS AVE | 5817 | EDWARDS AVE | 46-26-428-030 | Completed
EDWIN AVE | 134 | EDWIN AVE | 46-36-406-008 | No restoration work needed; door hanger left 7/16/24
EDWIN AVE | 147 | EDWIN AVE | 46-36-403-029 | Completed | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11
ELEVENTH AVE | 314 | ELEVENTH AVE | 40-12-181-030 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
ELMRIDGE DR | 6709 | ELMRIDGE DR | 47-29-176-024 | Completed | 2024-07-08 | 2024-07-08 |  |  | 2024-07-08 | 2024-07-08
EPSILON TR | 2722 | EPSILON TR | 47-33-104-001 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
EPSILON TR | 2825 | EPSILON TR | 47-33-103-033 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
EPSILON TR | 2829 | EPSILON TR | 47-33-103-034 | No restoration work needed; door hanger left 7/17/24
EPSILON TR | 2914 | EPSILON TR | 47-33-104-017 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
EPSILON TR | 2930 | EPSILON TR | 47-33-104-023 | No restoration work needed; door hanger left 7/17/24
ESTHER ST | 3614 | ESTHER ST | 46-36-455-015 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
ESTHER ST | 3702 | ESTHER ST | 46-36-455-011 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
ESTHER ST | 3706 | ESTHER ST | 46-36-455-010 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
EUCLID AVE | 1606 | EUCLID AVE | 40-12-106-033 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
EUCLID AVE | 1613 | EUCLID AVE | 40-12-105-030 | Completed | 2024-09-13 | 2024-10-02 | 2024-09-13 | 2024-09-18 | 2024-10-02 | 2024-10-02
EUCLID AVE | 1627 | EUCLID AVE | 40-12-105-028 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
EUCLID AVE | 1629 | EUCLID AVE | 40-12-105-027 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
EUCLID AVE | 1641 | EUCLID AVE | 40-12-105-024 | No restoration work needed; C/P home, no door hanger left
EUCLID AVE | 1656 | EUCLID AVE | 40-12-106-006 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
EVERGREEN PKWY | 3502 | EVERGREEN PKWY | 41-16-403-005 | No restoration work needed; door hanger left 8/13/24
EVERGREEN PKWY | 3532 | EVERGREEN PKWY | 41-16-403-010 | No restoration work needed; door hanger left 8/13/24
EVERGREEN PKWY | 3624 | EVERGREEN PKWY | 41-16-403-016 | No restoration work needed; door hanger left 7/25/24
EVERGREEN PKWY | 3630 | EVERGREEN PKWY | 41-16-403-034 | No restoration work needed; door hanger left 8/9/24 | 2023-12-15 | 2023-12-22 | 2023-12-15 | 2023-12-20 | 2023-12-22 | 2023-12-22
EVERGREEN PKWY | 3645 | EVERGREEN PKWY | 41-16-476-001 | No restoration work needed; door hanger left 8/9/24 | 2023-12-15 | 2023-12-22 | 2023-12-15 | 2023-12-20 | 2023-12-22 | 2023-12-22
EVERGREEN PKWY | 3662 | EVERGREEN PKWY | 41-16-452-029 | No restoration work needed; door hanger left 8/9/24 | 2023-12-15 | 2023-12-22 | 2023-12-15 | 2023-12-20 | 2023-12-22 | 2023-12-22
EVERGREEN PKWY | 3667 | EVERGREEN PKWY | 41-16-477-079 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
EVERGREEN PKWY | 3743 | EVERGREEN PKWY | 41-16-477-069 | No restoration work needed; door hanger left 8/9/24
EVERGREEN PKWY | 3749 | EVERGREEN PKWY | 41-16-477-030 | No restoration work needed; door hanger left 8/9/24 | 2023-12-15 | 2023-12-22 | 2023-12-15 | 2023-12-20 | 2023-12-22 | 2023-12-22
FENTON RD | 737 | FENTON RD | 41-18-354-012 | Completed | 2024-10-08 | 2024-10-18 | 2024-10-08 | 2024-10-09 | 2024-10-18 | 2024-10-18
FENTON RD | 1556 | FENTON RD | 40-24-227-008 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
FENTON RD | 2606 | FENTON RD | 40-24-278-036 | Completed | 2024-10-08 | 2024-10-26 | 2024-10-08 | 2024-10-09 | 2024-10-26 | 2024-10-26
FENTON RD | 4417 | FENTON RD | 41-30-153-006 | No restoration work needed; door hanger left 7/26/24
FENTON RD | 4609 | FENTON RD | 41-30-157-002 | No restoration work needed; door hanger left 7/26/24
FIELDING ST | 2906 | FIELDING ST | 40-14-382-005 | Completed | 2024-09-11 | 2024-09-20 | 2024-09-11 | 2024-09-20 | 2024-09-18 | 2024-09-18
FIRST AVE | 322 | FIRST AVE | 40-12-482-006 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12
FIRST AVE | 324 | FIRST AVE | 40-12-482-006 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12
FIRST AVE | 411 | FIRST AVE | 40-13-226-009 | Completed | 2024-09-16 | 2024-10-18 | 2024-09-16 | 2024-09-18 | 2024-10-18 | 2024-10-18
FIRST AVE | 426 | FIRST AVE | 40-12-481-015 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
FISK DR | 806 | FISK DR | 41-07-117-010 | Completed | 2024-09-20 | 2024-10-30 | 2024-09-20 | 2024-10-11 | 2024-10-30 | 2024-10-30
FLEMING RD | 3112 | FLEMING RD | 40-02-201-013 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
FLEMING RD | 3905 | FLEMING RD | 46-35-380-033 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
FLEMING RD | 4018 | FLEMING RD | 46-35-404-006 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
FLEMING RD | 4103 | FLEMING RD | 46-35-333-042 | No restoration work needed; door hanger left 8/22/24
FLEMING RD | 4221 | FLEMING RD | 46-35-331-008 | Completed | 2023-10-11 | 2024-07-08 | 2023-10-11 | 2023-12-11 | 2024-07-08 | 2024-07-08
FLEMING RD | 5010 | FLEMING RD | 46-35-201-008 | No restoration work needed; door hanger left 8/22/24
FLEMING RD | 5311 | FLEMING RD | 46-26-380-032 | No restoration work needed; door hanger left 7/9/24
FLEMING RD | 5501 | FLEMING RD | 46-26-380-024 | Completed | 2023-07-15 | 2024-07-09 |  |  | 2023-07-15 | 2024-07-09
FLEMING RD | 5610 | FLEMING RD | 46-26-403-016 | No restoration work needed; door hanger left 7/9/24
FLEMING RD | 5615 | FLEMING RD | 46-26-331-052 | Completed | 2020-10-07 | 2024-07-09 | 2020-10-07 | 2020-10-07 | 2024-07-09 | 2024-07-09
FLEMING RD | 5631 | FLEMING RD | 46-26-331-044 | No restoration work needed; door hanger left 8/22/24
FLEMING RD | 5701 | FLEMING RD | 46-26-331-043 | No restoration work needed; door hanger left 9/3/24
FLEMING RD | 5719 | FLEMING RD | 46-26-331-039 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
FLEMING RD | 6005 | FLEMING RD | 46-26-331-027 | Completed | 2024-09-18 | 2024-09-18 |  |  | 2024-09-18 | 2024-09-18
FLEMING RD | 6505 | FLEMING RD | 46-26-177-018 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-25 | 2024-10-08 | 2024-10-08
FLEMING RD | 6610 | FLEMING RD | 46-26-202-019 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
FLEMING RD | 6614 | FLEMING RD | 46-26-202-018 | Completed | 2023-07-15 | 2024-07-09 |  |  | 2023-07-15 | 2024-07-09
FLEMING RD | 6710 | FLEMING RD | 46-26-202-012 | No restoration work needed; door hanger left 7/9/24
FLEMING RD | 6714 | FLEMING RD | 46-26-202-011 | No restoration work needed; door hanger left 7/9/24
FLUSHING RD | 1901 | FLUSHING RD | 40-11-477-019 | Completed | 2024-10-17 | 2024-10-30 | 2024-10-17 | 2024-10-17 | 2024-10-30 | 2024-10-30
FLUSHING RD | 1934 | FLUSHING RD | 40-11-476-017 | No restoration work needed; door hanger left 7/16/24
FLUSHING RD | 2114 | FLUSHING RD | 40-11-407-050 | Completed | 2024-10-09 | 2024-10-15 | 2024-10-09 | 2024-10-10 | 2024-10-15 | 2024-10-15
FLUSHING RD | 2300 | FLUSHING RD | 40-11-407-038 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
FOREST HILL AVE | 1257 | FOREST HILL AVE | 40-11-180-035 | No restoration work needed; door hanger left 7/16/24
FOREST HILL AVE | 1609 | FOREST HILL AVE | 40-02-459-030 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
FOREST HILL AVE | 1913 | FOREST HILL AVE | 40-02-455-015 | No restoration work needed; door hanger left 8/22/24
FOREST HILL AVE | 2122 | FOREST HILL AVE | 40-02-452-010 | No restoration work needed; door hanger left 7/17/24
FOREST HILL AVE | 3906 | FOREST HILL AVE | 46-35-453-004 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
FRANK ST | 730 | FRANK ST | 40-14-253-017 | No restoration work needed; door hanger left 7/30/24
FRANK ST | 834 | FRANK ST | 40-14-253-006 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
FRANK ST | 841 | FRANK ST | 40-14-252-036 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
FRAZER ST | 3906 | FRAZER ST | 40-15-427-004 | Completed | 2024-09-19 | 2024-10-11 | 2024-09-19 | 2024-09-20 | 2024-10-11 | 2024-10-11
FRAZER ST | 3909 | FRAZER ST | 40-15-430-010 | No restoration work needed; door hanger left 7/29/24
FREEMAN AVE | 729 | FREEMAN AVE | 41-19-336-009 | Completed | 2024-07-22 | 2024-08-09 | 2024-07-22 | 2024-07-24 | 2024-08-09 | 2024-08-09
FREMONT ST | 608 | FREMONT ST | 40-11-378-003 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
FREMONT ST | 813 | FREMONT ST | 40-11-304-031 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
FREMONT ST | 825 | FREMONT ST | 40-11-304-028 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
FREMONT ST | 907 | FREMONT ST | 40-11-304-025 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
FREMONT ST | 925 | FREMONT ST | 40-11-304-022 | Completed | 2024-10-24 | 2024-10-30 | 2024-10-24 | 2024-10-29 | 2024-10-30 | 2024-10-30
FROST ST | 721 | FROST ST | 40-13-102-014 | Completed | 2024-09-19 | 2024-10-18 | 2024-09-19 | 2024-09-20 | 2024-10-18 | 2024-10-18
GAINEY AVE | 975 | GAINEY AVE | 40-14-455-006 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
GAINEY AVE | 1015 | GAINEY AVE | 40-14-461-010 | Completed | 2023-07-17 | 2024-07-29 |  |  | 2023-07-17 | 2024-07-29
GAINEY AVE | 1422 | GAINEY AVE | 40-23-209-011 | Completed | 2023-12-13 | 2024-07-29 | 2023-12-13 | 2023-12-15 | 2024-07-29 | 2024-07-29
GAINEY AVE | 1523 | GAINEY AVE | 40-23-213-004 | No restoration work needed; door hanger left 8/13/24
GAINEY AVE | 1524 | GAINEY AVE | 40-23-212-016 | No restoration work needed; door hanger left 7/29/24
GAMMA LN | 2809 | GAMMA LN | 47-33-102-030 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
GARLAND ST | 1115 | GARLAND ST | 40-12-258-025 | Completed | 2024-09-25 | 2024-10-30 | 2024-09-25 | 2024-10-30 | 2024-10-03 | 2024-10-03
GARLAND ST | 1534 | GARLAND ST | 40-12-130-012 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
GARLAND ST | 1536 | GARLAND ST | 40-12-130-011 | No restoration work needed; door hanger left 7/16/24
GARLAND ST | 1606 | GARLAND ST | 40-12-130-005 | Completed | 2024-10-17 | 2024-10-30 | 2024-10-17 | 2024-10-30 | 2024-10-03 | 2024-10-03
GIBSON ST | 2310 | GIBSON ST | 40-14-478-019 | Completed | 2024-09-11 | 2024-10-03 | 2024-09-11 | 2024-09-20 | 2024-10-03 | 2024-10-03
GIBSON ST | 2457 | GIBSON ST | 40-14-462-006 | No restoration work needed; door hanger left 8/15/24
GIBSON ST | 2458 | GIBSON ST | 40-14-459-013 | Completed | 2024-09-11 | 2024-09-19 | 2024-09-11 | 2024-09-19 | 2024-09-18 | 2024-09-18
GIBSON ST | 2466 | GIBSON ST | 40-14-457-012 | Completed | 2024-09-11 | 2024-09-20 | 2024-09-11 | 2024-09-20 | 2024-09-18 | 2024-09-18
GIBSON ST | 2469 | GIBSON ST | 40-14-462-003 | No restoration work needed; door hanger left 8/30/24
GIBSON ST | 2602 | GIBSON ST | 40-14-454-027 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-27 | 2024-10-03 | 2024-10-03
GIBSON ST | 2814 | GIBSON ST | 40-14-384-009 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
GILMARTIN ST | 1815 | GILMARTIN ST | 41-16-329-006 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1823 | GILMARTIN ST | 41-16-329-008 | No restoration work needed; door hanger left 7/24/24
GILMARTIN ST | 1827 | GILMARTIN ST | 41-16-329-010 | Completed | 2024-08-09 | 2024-08-13 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-13
GILMARTIN ST | 1901 | GILMARTIN ST | 41-16-378-001 | No restoration work needed; door hanger left 7/24/24
GILMARTIN ST | 1902 | GILMARTIN ST | 41-16-377-002 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1910 | GILMARTIN ST | 41-16-377-003 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1924 | GILMARTIN ST | 41-16-377-006 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1925 | GILMARTIN ST | 41-16-378-006 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1929 | GILMARTIN ST | 41-16-378-007 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1932 | GILMARTIN ST | 41-16-377-008 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 1933 | GILMARTIN ST | 41-16-378-008 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
GILMARTIN ST | 1936 | GILMARTIN ST | 41-16-377-009 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 1937 | GILMARTIN ST | 41-16-378-009 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 1941 | GILMARTIN ST | 41-16-378-010 | No restoration work needed; door hanger left 7/25/24
GILMARTIN ST | 1949 | GILMARTIN ST | 41-16-378-012 | No restoration work needed; door hanger left 7/25/24
GILMARTIN ST | 2001 | GILMARTIN ST | 41-16-378-013 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 2002 | GILMARTIN ST | 41-16-377-014 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 2006 | GILMARTIN ST | 41-16-377-015 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GILMARTIN ST | 2108 | GILMARTIN ST | 41-16-377-020 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLENN AVE | 5805 | GLENN AVE | 46-26-426-033 | No restoration work needed; door hanger left 7/9/24
GLENN AVE | 5909 | GLENN AVE | 46-26-426-027 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
GLENN AVE | 5918 | GLENN AVE | 46-26-427-002 | Completed | 2024-09-25 | 2024-10-02 | 2024-09-25 | 2024-09-25 | 2024-10-02 | 2024-10-02
GLOUCESTER ST | 3516 | GLOUCESTER ST | 41-16-453-034 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLOUCESTER ST | 3523 | GLOUCESTER ST | 41-16-452-016 | Completed | 2024-08-14 | 2024-08-20 | 2024-08-14 | 2024-08-15 | 2024-08-20 | 2024-08-20
GLOUCESTER ST | 3528 | GLOUCESTER ST | 41-16-453-007 | No restoration work needed; door hanger left 7/25/24
GLOUCESTER ST | 3535 | GLOUCESTER ST | 41-16-452-019 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLOUCESTER ST | 3536 | GLOUCESTER ST | 41-16-453-008 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLOUCESTER ST | 3544 | GLOUCESTER ST | 41-16-453-009 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLOUCESTER ST | 3602 | GLOUCESTER ST | 41-16-453-010 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GLOUCESTER ST | 3743 | GLOUCESTER ST | 41-16-476-024 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
GOLD AVE | 2014 | GOLD AVE | 41-08-404-006 | No restoration work needed; door hanger left 7/23/24
GOLD AVE | 2413 | GOLD AVE | 41-08-428-016 | No restoration work needed; door hanger left 7/23/24
GOLD AVE | 2414 | GOLD AVE | 41-08-429-010 | No restoration work needed; door hanger left 7/23/24
GOLD AVE | 2419 | GOLD AVE | 41-08-428-017 | Completed | 2024-08-14 | 2024-09-05 | 2024-08-14 | 2024-08-20 | 2024-09-05 | 2024-09-05
GOLD AVE | 2425 | GOLD AVE | 41-08-428-018 | No restoration work needed; door hanger left 7/23/24
GOLD AVE | 2426 | GOLD AVE | 41-08-429-013 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
GOLFSIDE LN | 2721 | GOLFSIDE LN | 40-11-351-046 | No restoration work needed; door hanger left 7/16/24
GOLFSIDE LN | 2729 | GOLFSIDE LN | 40-11-351-102 | No restoration work needed; door hanger left 7/16/24
GOLFSIDE LN | 2733 | GOLFSIDE LN | 40-11-351-111 | Completed | 2024-09-19 | 2024-10-30 | 2024-09-19 | 2024-09-20 | 2024-10-30 | 2024-10-30
GRANDY ST | 1213 | GRANDY ST | 41-07-203-005 | No restoration work needed; door hanger left 8/19/24
GRATIOT AVE | 3410 | GRATIOT AVE | 40-14-303-018 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
GRATIOT AVE | 3417 | GRATIOT AVE | 40-14-302-006 | No restoration work needed; door hanger left 8/15/24
GRATIOT AVE | 3710 | GRATIOT AVE | 40-14-157-019 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-27 | 2024-10-02 | 2024-10-02
GRATIOT AVE | 3714 | GRATIOT AVE | 40-14-157-018 | No restoration work needed; door hanger left 8/15/24
GRATIOT AVE | 3721 | GRATIOT AVE | 40-14-158-003 | No restoration work needed; door hanger left 7/29/24
GRATIOT AVE | 3722 | GRATIOT AVE | 40-14-157-016 | Completed | 2024-09-23 | 2024-10-03 | 2024-09-23 | 2024-09-24 | 2024-10-03 | 2024-10-03
GREEN ST | 506 | GREEN ST | 40-01-307-023 | Completed | 2024-09-12 | 2024-10-18 | 2024-09-12 | 2024-09-12 | 2024-10-18 | 2024-10-18
GREENBRIAR LN | 1829 | GREENBRIAR LN | 40-25-106-015 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
GREENBROOK LN | 1802 | GREENBROOK LN | 40-25-251-034 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
GREENBROOK LN | 1920 | GREENBROOK LN | 40-25-251-023 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
GREENFIELD AVE | 602 | GREENFIELD AVE | 41-08-477-023 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
GREENFIELD AVE | 610 | GREENFIELD AVE | 41-08-477-025 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
GREENLAWN DR | 4617 | GREENLAWN DR | 46-35-130-032 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-30 | 2024-10-08 | 2024-10-08
GREENWAY AVE | 1707 | GREENWAY AVE | 40-02-377-002 | No restoration work needed; door hanger left 8/22/24
GRIGGS DR | 1814 | GRIGGS DR | 46-26-330-037 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
HAMMOND ST | 916 | HAMMOND ST | 40-14-381-014 | No restoration work needed; door hanger left 7/29/24
HAMMOND ST | 987 | HAMMOND ST | 40-14-454-011 | Completed | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-31 | 2024-10-31 | 2024-10-31
HAMMOND ST | 1010 | HAMMOND ST | 40-14-390-010 | Completed | 2024-10-14 | 2024-10-31 | 2024-10-14 | 2024-10-17 | 2024-10-31 | 2024-10-31
HARMON ST | 1114 | HARMON ST | 40-24-226-005 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
HAWTHORNE DR | 3006 | HAWTHORNE DR | 40-23-305-063 | No restoration work needed; door hanger left 8/20/24
HAWTHORNE DR | 3312 | HAWTHORNE DR | 40-23-305-048 | No restoration work needed; door hanger left 7/30/24
HAWTHORNE DR | 3321 | HAWTHORNE DR | 40-23-326-002 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
HAWTHORNE DR | 3401 | HAWTHORNE DR | 40-23-306-006 | No restoration work needed; door hanger left 7/30/24
HAWTHORNE DR | 3420 | HAWTHORNE DR | 40-23-305-044 | Completed | 2024-07-30 | 2024-07-30 |  |  | 2024-07-30 | 2024-07-30
HAWTHORNE DR | 3470 | HAWTHORNE DR | 40-23-305-038 | No restoration work needed; door hanger left 7/30/24
HELBER ST | 3023 | HELBER ST | 40-02-351-009 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HELBER ST | 3201 | HELBER ST | 40-03-427-013 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HELBER ST | 3314 | HELBER ST | 40-02-312-003 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HELBER ST | 3315 | HELBER ST | 40-03-427-001 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HERRICK ST | 3210 | HERRICK ST | 40-23-152-017 | No restoration work needed; door hanger left 7/29/24
HERRICK ST | 3402 | HERRICK ST | 40-23-151-030 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-13 | 2024-09-19 | 2024-09-19
HERRICK ST | 3605 | HERRICK ST | 40-22-279-012 | No restoration work needed; door hanger left 7/29/24
HERRICK ST | 3933 | HERRICK ST | 40-22-278-001 | No restoration work needed; door hanger left 7/29/24
HILLCREST AVE | 2627 | HILLCREST AVE | 41-20-254-006 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
HILLCREST AVE | 2702 | HILLCREST AVE | 41-20-253-007 | No restoration work needed; door hanger left 9/9/24
HILLCREST AVE | 2721 | HILLCREST AVE | 41-20-254-010 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
HILLS ST | 2215 | HILLS ST | 41-17-228-020 | No restoration work needed; door hanger left 7/23/24
HOFF ST | 2521 | HOFF ST | 41-05-430-017 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
HOGARTH AVE | 3402 | HOGARTH AVE | 40-23-158-025 | Completed | 2024-09-06 | 2024-09-19 | 2024-09-06 | 2024-09-13 | 2024-09-19 | 2024-09-19
HOGARTH AVE | 3909 | HOGARTH AVE | 40-22-284-008 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
HOLLY AVE | 3715 | HOLLY AVE | 41-04-476-057 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HOLLY AVE | 3833 | HOLLY AVE | 41-04-476-081 | Completed | 2024-09-16 | 2024-10-19 | 2024-09-16 | 2024-09-18 | 2024-10-19 | 2024-10-19
HUBBARD AVE | 711 | HUBBARD AVE | 40-14-305-003 | No restoration work needed; door hanger left 9/23/24
HUBBARD AVE | 719 | HUBBARD AVE | 40-14-305-004 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
HUBBARD AVE | 730 | HUBBARD AVE | 40-14-301-022 | Completed | 2024-09-23 | 2024-10-17 | 2024-09-23 | 2024-09-27 | 2024-10-17 | 2024-10-17
HUBBARD AVE | 968 | HUBBARD AVE | 40-14-357-019 | No restoration work needed; door hanger left 8/15/24
HUBBARD AVE | 988 | HUBBARD AVE | 40-14-357-024 | No restoration work needed; door hanger left 8/15/24
HUCKLEBERRY LN | 4314 | HUCKLEBERRY LN | 40-25-254-004 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
HUCKLEBERRY LN | 4405 | HUCKLEBERRY LN | 40-25-253-005 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
HUGGINS ST | 3807 | HUGGINS ST | 47-33-452-033 | Completed | 2024-09-23 | 2024-10-21 | 2024-09-23 | 2024-09-23 | 2024-10-21 | 2024-10-21
HUGHES AVE | 1422 | HUGHES AVE | 40-23-131-036 | No restoration work needed; door hanger left 8/14/24
HULL AVE | 3308 | HULL AVE | 07-25-579-023 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
HUMBOLDT AVE | 2405 | HUMBOLDT AVE | 40-02-401-027 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
HURON ST | 620 | HURON ST | 41-30-177-021 | No restoration work needed; door hanger left 7/17/24
HURON ST | 841 | HURON ST | 41-30-154-009 | No restoration work needed; door hanger left 8/21/24
HURON ST | 1238 | HURON ST | 40-25-276-038 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
HURON ST | 1310 | HURON ST | 40-25-276-018 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
IDA AVE | 1112 | IDA AVE | 40-13-356-005 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
ILLINOIS AVE | 1405 | ILLINOIS AVE | 41-08-103-026 | Completed | 2024-09-19 | 2024-10-19 | 2024-09-19 | 2024-09-19 | 2024-10-19 | 2024-10-19
ILLINOIS AVE | 1414 | ILLINOIS AVE | 41-08-105-004 | No restoration work needed; door hanger left 8/19/24
INDUSTRIAL AVE | 4510 | INDUSTRIAL AVE | 47-31-179-012 | No restoration work needed; door hanger left 8/14/24
INDUSTRIAL AVE | 7020 | INDUSTRIAL AVE | 47-30-127-002 | No restoration work needed; door hanger left 8/16/24
INGLESIDE AVE | 818 | INGLESIDE AVE | 41-30-154-031 | Completed
INGLESIDE AVE | 821 | INGLESIDE AVE | 41-30-156-013 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
IRENE AVE | 1404 | IRENE AVE | 40-23-210-007 | No restoration work needed; door hanger left 7/29/24
IROQUOIS AVE | 3015 | IROQUOIS AVE | 40-01-107-010 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
IROQUOIS AVE | 3114 | IROQUOIS AVE | 40-01-106-002 | No restoration work needed; door hanger left 7/11/24
IVANHOE AVE | 3721 | IVANHOE AVE | 41-09-228-017 | No restoration work needed; door hanger left 7/18/24
IVANHOE AVE | 3737 | IVANHOE AVE | 41-09-228-021 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
IVANHOE AVE | 3802 | IVANHOE AVE | 41-09-231-001 | No restoration work needed; door hanger left 7/18/24
IVANHOE AVE | 3818 | IVANHOE AVE | 41-09-231-005 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
IVANHOE AVE | 3821 | IVANHOE AVE | 41-09-229-017 | No restoration work needed; door hanger left 7/18/24
JACQUE ST | 4019 | JACQUE ST | 40-15-429-002 | No restoration work needed; door hanger left 7/29/24
JANE AVE | 1417 | JANE AVE | 41-05-305-021 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
JANE AVE | 1422 | JANE AVE | 41-05-307-006 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
JANE AVE | 1425 | JANE AVE | 41-05-305-024 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
JANE AVE | 1449 | JANE AVE | 41-05-305-030 | No restoration work needed; door hanger left 7/18/24
JANE AVE | 1452 | JANE AVE | 41-05-307-014 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
JANE AVE | 1502 | JANE AVE | 41-05-308-001 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
JANE AVE | 1546 | JANE AVE | 41-05-308-013 | No restoration work needed; door hanger left 7/18/24
JANE AVE | 1738 | JANE AVE | 41-05-333-011 | No restoration work needed; door hanger left 7/18/24
JASMINE AVE | 1826 | JASMINE AVE | 41-17-308-022 | Completed | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-08 | 2024-08-12 | 2024-08-12
JOAL LN | 3753 | JOAL LN | 47-33-476-044 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
JOHNSON AVE | 955 | JOHNSON AVE | 40-15-487-002 | No restoration work needed; door hanger left 7/29/24
JOHNSON AVE | 972 | JOHNSON AVE | 40-15-486-017 | No restoration work needed; door hanger left 7/29/24 |  |  | 2022-12-15 | 2022-12-22
JOLIET ST | 1908 | JOLIET ST | 40-14-227-036 | Completed | 2024-09-19 | 2024-10-15 | 2024-09-19 | 2024-09-20 | 2024-10-15 | 2024-10-15
JOLIET ST | 2237 | JOLIET ST | 40-14-203-005 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
JOSEPHINE ST | 516 | JOSEPHINE ST | 40-01-353-020 | Completed | 2024-10-23 | 2024-10-31 | 2024-10-23 | 2024-10-31 | 2024-10-30 | 2024-10-30
JOSEPHINE ST | 602 | JOSEPHINE ST | 40-01-353-017 | Completed | 2024-09-25 | 2024-10-31 | 2024-09-25 | 2024-10-31 | 2024-10-03 | 2024-10-03
JOYNER ST | 3820 | JOYNER ST | 40-15-432-042 | Completed | 2024-09-13 | 2024-10-11 | 2024-09-13 | 2024-10-02 | 2024-10-11 | 2024-10-11
JOYNER ST | 3905 | JOYNER ST | 40-15-434-008 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
KANSAS AVE | 1706 | KANSAS AVE | 41-08-185-002 | Completed | 2024-09-19 | 2024-10-19 | 2024-09-19 | 2024-09-19 | 2024-10-19 | 2024-10-19
KANSAS AVE | 1725 | KANSAS AVE | 41-08-183-026 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
KEARSLEY PK BLVD | 1709 | KEARSLEY PK BLVD | 41-08-176-002 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
KELLAR AVE | 2340 | KELLAR AVE | 40-02-309-010 | No restoration work needed; door hanger left 9/5/24
KELLAR AVE | 2414 | KELLAR AVE | 40-02-309-006 | Completed | 2024-09-12 | 2024-10-17 | 2024-09-12 | 2024-09-16 | 2024-10-17 | 2024-10-17
KELLAR AVE | 2426 | KELLAR AVE | 40-02-309-004 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-17 | 2024-09-18 | 2024-09-18
KELLAR AVE | 2905 | KELLAR AVE | 40-02-109-029 | Completed | 2024-09-09 | 2024-10-02 | 2024-09-09 | 2024-09-09 | 2024-10-02 | 2024-10-02
KELLAR AVE | 4207 | KELLAR AVE | 46-35-304-013 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
KELLAR AVE | 4208 | KELLAR AVE | 46-35-305-006 | No restoration work needed; door hanger left 8/22/24
KELLAR AVE | 4225 | KELLAR AVE | 46-35-304-010 | Completed | 2024-09-10 | 2024-10-08 | 2024-09-10 | 2024-09-10 | 2024-10-08 | 2024-10-08
KENSINGTON AVE | 805 | KENSINGTON AVE | 41-08-384-011 | No restoration work needed; door hanger left 7/23/24
KENSINGTON AVE | 916 | KENSINGTON AVE | 41-17-128-019 | No restoration work needed; door hanger left 7/23/24
KENSINGTON AVE | 1010 | KENSINGTON AVE | 41-17-128-027 | Completed | 2024-08-13 | 2024-09-03 | 2024-08-13 | 2024-08-29 | 2024-09-03 | 2024-09-03
KENSINGTON AVE | 1025 | KENSINGTON AVE | 41-17-129-020 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
KENSINGTON AVE | 1110 | KENSINGTON AVE | 41-17-133-021 | Completed | 2024-08-08 | 2024-09-03 | 2024-08-08 | 2024-08-13 | 2024-09-03 | 2024-09-03
KENSINGTON AVE | 1134 | KENSINGTON AVE | 41-17-133-027 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
KENSINGTON AVE | 1137 | KENSINGTON AVE | 41-17-134-011 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
KENSINGTON AVE | 1625 | KENSINGTON AVE | 41-17-180-012 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
KENT ST | 1602 | KENT ST | 41-17-451-012 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
KENT ST | 1606 | KENT ST | 41-17-451-013 | No restoration work needed; door hanger left 7/25/24
KENT ST | 3535 | KENT ST | 41-16-403-026 | No restoration work needed; door hanger left 7/25/24
KENT ST | 3622 | KENT ST | 41-16-452-012 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
KENT ST | 3730 | KENT ST | 41-16-476-006 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
KENT ST | 3736 | KENT ST | 41-16-476-007 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
KENTUCKY AVE | 1636 | KENTUCKY AVE | 41-08-180-001 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
KENTUCKY AVE | 2102 | KENTUCKY AVE | 41-08-253-013 | Completed | 2023-06-20 | 2024-07-23 | 2023-06-20 | 2023-06-29 | 2024-07-23 | 2024-07-23
KIRKWOOD LN | 3123 | KIRKWOOD LN | 40-02-126-041 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
KIRKWOOD LN | 3206 | KIRKWOOD LN | 40-02-127-001 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
KIRKWOOD LN | 3209 | KIRKWOOD LN | 40-02-126-038 | No restoration work needed; door hanger left 10/2/24 | It was determined road patch was not related to SLE; it was CtoC
KLEINPELL ST | 3410 | KLEINPELL ST | 41-21-376-021 | No restoration work needed; door hanger left 7/11/24; gravel drive
KLEINPELL ST | 3601 | KLEINPELL ST | 41-21-379-008 | No restoration work needed; door hanger left 9/3/24
KLEINPELL ST | 3625 | KLEINPELL ST | 41-21-379-014 | No restoration work needed; door hanger left 7/11/24; gravel drive
KNAPP AVE | 923 | KNAPP AVE | 40-14-356-009 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
KNAPP AVE | 956 | KNAPP AVE | 40-14-362-009 | No restoration work needed; door hanger left 7/29/24
KNAPP AVE | 1024 | KNAPP AVE | 40-14-371-011 | Completed | 2024-10-24 | 2024-10-31 | 2024-10-24 | 2024-10-31 | 2024-10-31 | 2024-10-31
KNAPP AVE | 1115 | KNAPP AVE | 40-23-126-005 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-12 | 2024-09-18 | 2024-09-18
KNAPP AVE | 1217 | KNAPP AVE | 40-23-126-011 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-13 | 2024-09-18 | 2024-09-18
KNAPP AVE | 1326 | KNAPP AVE | 40-23-110-026 | No restoration work needed; door hanger left 8/15/24
KNAPP AVE | 1618 | KNAPP AVE | 40-23-157-015 | No restoration work needed; door hanger left 8/30/24
KNAPP AVE | 1714 | KNAPP AVE | 40-23-157-022 | Completed | 2024-09-04 | 2024-09-19 | 2024-09-04 | 2024-09-13 | 2024-09-19 | 2024-09-19
KNIGHT AVE | 1214 | KNIGHT AVE | 40-23-127-025 | Completed | 2024-09-04 | 2024-09-17 | 2024-09-04 | 2024-09-09 | 2024-09-17 | 2024-09-17
KNIGHT AVE | 1305 | KNIGHT AVE | 40-23-133-002 | No restoration work needed; door hanger left 9/3/24
KNIGHT AVE | 1502 | KNIGHT AVE | 40-23-132-033 | Completed | 2024-09-04 | 2024-09-17 | 2024-09-04 | 2024-09-05 | 2024-09-17 | 2024-09-17
KNIGHT AVE | 1522 | KNIGHT AVE | 40-23-132-039 | Completed | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-05 | 2024-09-19 | 2024-09-19
KNIGHT AVE | 1602 | KNIGHT AVE | 40-23-177-005 | Completed | 2024-08-20 | 2024-08-20 |  |  | 2024-08-20 | 2024-08-20
KUMMER ST | 804 | KUMMER ST | 40-14-426-018 | Completed | 2024-09-12 | 2024-09-27 | 2024-09-12 | 2024-09-27 | 2024-09-18 | 2024-09-18
LAFAYETTE ST | 321 | LAFAYETTE ST | 41-08-404-005 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
LAFAYETTE ST | 413 | LAFAYETTE ST | 41-08-407-003 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
LAFAYETTE ST | 601 | LAFAYETTE ST | 41-08-451-011 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
LAFAYETTE ST | 1060 | LAFAYETTE ST | 41-17-201-013 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
LAKE FOREST DR | 1421 | LAKE FOREST DR | 46-35-252-006 | No restoration work needed; door hanger left 10/3/24 | Appears the city may have replaced the sidewalk
LANDON ST | 2626 | LANDON ST | 40-02-180-006 | No restoration work needed; door hanger left 8/22/24
LAPEER RD | 1105 | LAPEER RD | 41-18-276-001 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-20
LAPEER RD | 1109 | LAPEER RD | 41-18-276-003 | Completed | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-20 | 2024-09-23 | 2024-09-23
LAPEER RD | 1113 | LAPEER RD | 41-18-276-004 | Completed | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-20 | 2024-09-23 | 2024-09-23
LAPEER RD | 1201 | LAPEER RD | 41-18-277-001 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-20
LAPEER RD | 1305 | LAPEER RD | 41-18-280-002 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
LAPEER RD | 1357 | LAPEER RD | 41-18-284-002 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
LAPEER RD | 1361 | LAPEER RD | 41-18-284-003 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-20
LAPEER RD | 1409 | LAPEER RD | 41-18-285-004 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-17 | 2024-09-20 | 2024-09-20
LAPEER RD | 1505 | LAPEER RD | 41-17-152-029 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-17 | 2024-09-20 | 2024-09-20
LAPEER RD | 1511 | LAPEER RD | 41-17-152-023 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-17 | 2024-09-20 | 2024-09-20
LAPEER RD | 1519 | LAPEER RD | 41-17-152-025 | Completed | 2024-09-17 | 2024-09-20 | 2024-09-17 | 2024-09-17 | 2024-09-20 | 2024-09-20
LAPEER RD | 2357 | LAPEER RD | 41-17-401-004 | Completed | 2024-10-08 | 2024-10-26 | 2024-10-08 | 2024-10-12 | 2024-10-26 | 2024-10-26
LAPEER RD | 3201 | LAPEER RD | 41-16-301-013 | Completed | 2024-08-20 | 2024-08-20 |  |  | 2024-08-20 | 2024-08-20
LARCHMONT ST | 3805 | LARCHMONT ST | 40-22-282-016 | No restoration work needed; door hanger left 9/11/24 | 2024-09-20 | 2024-11-01 | 2024-09-20 | 2024-09-20 | 2024-11-01 | 2024-11-01
LARCHMONT ST | 3825 | LARCHMONT ST | 40-22-282-012 | No restoration work needed; door hanger left 7/29/24
LAUREL OAK DR | 1846 | LAUREL OAK DR | 40-25-152-052 | Completed | 2024-07-22 | 2024-07-31 | 2024-07-22 | 2024-07-24 | 2024-07-31 | 2024-07-31
LAUREL OAK DR | 1857 | LAUREL OAK DR | 40-25-153-044 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LAVENDER AVE | 1485 | LAVENDER AVE | 40-11-129-016 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
LAVENDER AVE | 1502 | LAVENDER AVE | 40-11-128-014 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
LAVENDER AVE | 1552 | LAVENDER AVE | 40-11-126-014 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
LAVENDER AVE | 1601 | LAVENDER AVE | 40-02-380-030 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
LAVENDER AVE | 1652 | LAVENDER AVE | 40-02-458-014 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
LAWNDALE AVE | 2113 | LAWNDALE AVE | 40-02-452-022 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
LAWNDALE AVE | 2314 | LAWNDALE AVE | 40-02-405-012 | Completed | 2024-09-09 | 2024-10-03 | 2024-09-09 | 2024-09-09 | 2024-10-03 | 2024-10-03
LAWNDALE AVE | 2402 | LAWNDALE AVE | 40-02-405-007 | Completed | 2024-09-09 | 2024-10-03 | 2024-09-09 | 2024-09-09 | 2024-10-03 | 2024-10-03
LAWNDALE AVE | 2922 | LAWNDALE AVE | 40-02-208-001 | No restoration work needed; door hanger left 8/22/24
LAWNDALE AVE | 3506 | LAWNDALE AVE | 46-35-460-010 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
LAWNDALE AVE | 3701 | LAWNDALE AVE | 46-35-454-033 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-23 | 2024-10-02 | 2024-10-02
LAWNDALE AVE | 4101 | LAWNDALE AVE | 46-35-407-030 | Completed | 2024-09-23 | 2024-10-02 | 2024-09-23 | 2024-09-23 | 2024-10-02 | 2024-10-02
LAWNDALE AVE | 4109 | LAWNDALE AVE | 46-35-407-027 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
LAWNDALE AVE | 4114 | LAWNDALE AVE | 46-35-408-007 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
LE ERDA AVE | 3505 | LE ERDA AVE | 46-35-383-027 | Completed | 2024-09-19 | 2024-10-17 | 2024-09-19 | 2024-10-02 | 2024-10-17 | 2024-10-17
LEITH ST | 3302 | LEITH ST | 41-04-251-001 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
LEITH ST | 3601 | LEITH ST | 41-04-206-034 | No restoration work needed; door hanger left 7/17/24
LEITH ST | 3614 | LEITH ST | 41-04-251-021 | No restoration work needed; door hanger left 7/17/24
LEITH ST | 3733 | LEITH ST | 41-04-276-007 | Completed | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-29 | 2024-07-31 | 2024-07-31
LELAND ST | 639 | LELAND ST | 41-30-131-005 | No restoration work needed; door hanger left 7/26/24
LELAND ST | 649 | LELAND ST | 41-30-131-002 | No restoration work needed; door hanger left 7/26/24
LELAND ST | 709 | LELAND ST | 41-30-130-011 | Completed | 2023-10-06 | 2024-07-18 | 2023-10-06 | 2023-12-29 | 2024-07-18 | 2024-07-18
LELAND ST | 714 | LELAND ST | 41-30-128-021 | No restoration work needed; door hanger left 7/26/24
LELAND ST | 729 | LELAND ST | 41-30-130-031 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LELAND ST | 737 | LELAND ST | 41-30-130-005 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LELAND ST | 834 | LELAND ST | 41-30-104-024 | Completed | 2024-07-23 | 2024-07-31 | 2024-07-23 | 2024-07-24 | 2024-07-31 | 2024-07-31
LELAND ST | 845 | LELAND ST | 41-30-106-009 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LELAND ST | 932 | LELAND ST | 41-30-103-036 | No restoration work needed; door hanger left 7/26/24
LELAND ST | 936 | LELAND ST | 41-30-103-018 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LELAND ST | 944 | LELAND ST | 41-30-103-016 | Completed | 2024-07-26 | 2024-07-26 |  |  | 2024-07-26 | 2024-07-26
LELAND ST | 1109 | LELAND ST | 40-25-231-006 | Completed | 2024-07-18 | 2024-07-31 | 2024-07-22 | 2024-07-24 | 2024-07-31 | 2024-07-31
LELAND ST | 1212 | LELAND ST | 40-25-228-037 | Completed | 2024-10-11 | 2024-10-17 | 2024-10-11 | 2024-10-17 | 2024-10-15 | 2024-10-15
LESLIE DR | 5401 | LESLIE DR | 46-26-377-041 | No restoration work needed; door hanger left 8/22/24
LETA AVE | 511 | LETA AVE | 41-29-203-024 | Completed | 2024-07-11 | 2024-07-19 | 2024-07-11 | 2024-07-19 | 2024-07-18 | 2024-07-18
LEVERN ST | 1713 | LEVERN ST | 41-08-226-020 | Completed | 2024-09-19 | 2024-10-02 | 2024-09-19 | 2024-09-19 | 2024-10-02 | 2024-10-02
LEWIS ST | 3208 | LEWIS ST | 41-05-107-004 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
LEXINGTON AVE | 850 | LEXINGTON AVE | 41-19-153-008 | No restoration work needed; door hanger left 7/25/24
LEXINGTON AVE | 931 | LEXINGTON AVE | 41-19-155-009 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
LIBERTY ST | 1701 | LIBERTY ST | 41-18-435-010 | Completed | 2024-08-01 | 2024-10-17 | 2024-08-01 | 2024-10-17 | 2024-08-12 | 2024-08-12
LIBERTY ST | 1705 | LIBERTY ST | 41-18-435-011 | Completed | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-02 | 2024-08-12 | 2024-08-12
LILLIAN DR | 1306 | LILLIAN DR | 46-26-252-050 | No restoration work needed; door hanger left 8/23/24
LILLIAN DR | 1318 | LILLIAN DR | 46-26-252-047 | No restoration work needed; door hanger left 9/3/24
LILLIAN DR | 1322 | LILLIAN DR | 46-26-252-046 | No restoration work needed; door hanger left 7/9/24
LILLIAN DR | 1401 | LILLIAN DR | 46-26-253-005 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
LILLIAN DR | 1402 | LILLIAN DR | 46-26-252-045 | Completed | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09
LINCOLN DR | 1402 | LINCOLN DR | 40-23-229-015 | No restoration work needed; door hanger left 7/29/24
LINCOLN DR | 1425 | LINCOLN DR | 40-23-231-007 | No restoration work needed; door hanger left 7/29/24
LINCOLN DR | 1429 | LINCOLN DR | 40-23-231-008 | No restoration work needed; door hanger left 7/29/24
LINCOLN DR | 1437 | LINCOLN DR | 40-23-231-010 | No restoration work needed; door hanger left 7/29/24
LINCOLN DR | 1945 | LINCOLN DR | 40-24-152-021 | No restoration work needed; door hanger left 7/29/24
LINCOLN DR | 2001 | LINCOLN DR | 40-24-152-022 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
LINWOOD AVE | 1514 | LINWOOD AVE | 41-17-176-005 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
LINWOOD AVE | 1702 | LINWOOD AVE | 41-17-176-010 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
LIPPINCOTT BLVD | 615 | LIPPINCOTT BLVD | 41-17-356-033 | Completed | 2024-10-28 | 2024-10-31 | 2024-10-28 | 2024-10-30 | 2024-10-31 | 2024-10-31
LIPPINCOTT BLVD | 705 | LIPPINCOTT BLVD | 41-17-357-018 | Completed | 2024-10-24 | 2024-10-31 | 2024-10-24 | 2024-10-30 | 2024-10-31 | 2024-10-31
LIPPINCOTT BLVD | 1108 | LIPPINCOTT BLVD | 41-20-127-003 | No restoration work needed; door hanger left 10/17/24 | Sidewalk was completed when arrived to the site
LIPPINCOTT BLVD | 1305 | LIPPINCOTT BLVD | 41-17-380-029 | Completed | 2024-07-24 | 2024-10-30 | 2024-10-28 | 2024-10-30 | 2024-07-24 | 2024-07-24
LIPPINCOTT BLVD | 1613 | LIPPINCOTT BLVD | 41-17-456-036 | Completed | 2024-10-28 | 2024-10-31 | 2024-10-28 | 2024-10-29 | 2024-10-31 | 2024-10-31
LIPPINCOTT BLVD | 3617 | LIPPINCOTT BLVD | 41-16-456-033 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
LOMITA AVE | 722 | LOMITA AVE | 47-31-102-007 | No restoration work needed; door hanger left 7/29/24
LOMITA AVE | 921 | LOMITA AVE | 47-31-126-030 | Completed | 2024-09-20 | 2024-10-30 | 2024-09-20 | 2024-10-11 | 2024-10-30 | 2024-10-30
LOMITA AVE | 945 | LOMITA AVE | 47-31-126-041 | No restoration work needed; door hanger left 7/29/24
LORRAINE AVE | 3712 | LORRAINE AVE | 41-09-234-003 | Completed | 2024-09-16 | 2024-10-02 | 2024-09-16 | 2024-09-18 | 2024-10-02 | 2024-10-02
LYMAN ST | 2309 | LYMAN ST | 41-06-431-018 | No restoration work needed; door hanger left 7/18/24
LYNBROOK DR | 1709 | LYNBROOK DR | 40-25-177-011 | No restoration work needed; door hanger left 7/26/24
LYNN CT | 3809 | LYNN CT | 41-16-477-042 | No restoration work needed; door hanger left 8/9/24
LYNN CT | 3813 | LYNN CT | 41-16-477-043 | Completed | 2024-08-09 | 2024-08-20 | 2024-08-09 | 2024-08-12 | 2024-08-20 | 2024-08-20
LYNN ST | 3528 | LYNN ST | 41-16-455-006 | No restoration work needed; door hanger left 8/9/24
LYNN ST | 3607 | LYNN ST | 41-16-454-029 | No restoration work needed; door hanger left 8/9/24
LYNN ST | 3608 | LYNN ST | 41-16-455-011 | Completed | 2024-07-25 | 2024-07-25 |  |  | 2024-07-25 | 2024-07-25
LYNN ST | 3619 | LYNN ST | 41-16-454-031 | No restoration work needed; door hanger left 7/25/24
LYON ST | 909 | LYON ST | 40-12-405-018 | No restoration work needed; house demo'd
LYON ST | 929 | LYON ST | 40-12-405-012 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
LYON ST | 1116 | LYON ST | 40-12-258-008 | Completed | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | Not needed
LYON ST | 1518 | LYON ST | 40-12-129-018 | No restoration work needed; door hanger left 8/30/24
LYON ST | 1619 | LYON ST | 40-12-128-030 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
M L KING AVE | 1216 | M L KING AVE | 40-12-209-051 | No restoration work needed; door hanger left 9/5/24
M L KING AVE | 1220 | M L KING AVE | 40-12-209-024 | No restoration work needed; door hanger left 9/5/24
M L KING AVE | 1906 | M L KING AVE | 40-01-451-016 | No restoration work needed; door hanger left 8/20/24
M L KING AVE | 2110 | M L KING AVE | 40-01-414-009 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
M L KING AVE | 3008 | M L KING AVE | 40-01-203-003 | No restoration work needed; door hanger left 8/20/24
M L KING AVE | 3618 | M L KING AVE | 46-36-381-013 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
M L KING AVE | 4002 | M L KING AVE | 46-36-408-004 | Completed | 2024-10-09 | 2024-10-17 | 2024-10-09 | 2024-10-09 | 2024-10-17 | 2024-10-17
M L KING AVE | 4321 | M L KING AVE | 46-36-179-032 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
M L KING AVE | 6101 | M L KING AVE | 46-25-326-019 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
MABEL AVE | 1302 | MABEL AVE | 41-06-477-001 | No restoration work needed; door hanger left 7/18/24
MABEL AVE | 1422 | MABEL AVE | 41-05-351-007 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
MABEL AVE | 1513 | MABEL AVE | 41-05-308-020 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
MABEL AVE | 1622 | MABEL AVE | 41-05-376-007 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
MABEL AVE | 1658 | MABEL AVE | 41-05-376-017 | Completed | 2024-07-18 | 2024-07-18 |  |  | 2024-07-18 | 2024-07-18
MABEL AVE | 1826 | MABEL AVE | 41-05-377-039 | No restoration work needed; door hanger left 7/18/24
MACKIN RD | 1141 | MACKIN RD | 40-12-328-004 | Completed | 2024-10-16 | 2024-11-08 | 2024-10-16 | 2024-10-28 | 2024-11-08 | 2024-11-08
MACKIN RD | 1301 | MACKIN RD | 40-12-303-016 | No restoration work needed; door hanger left 8/21/24
MACKIN RD | 2828 | MACKIN RD | 40-11-133-024 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
MACKIN RD | 2840 | MACKIN RD | 40-11-133-020 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
MACKIN RD | 2849 | MACKIN RD | 40-11-107-007 | No restoration work needed; door hanger left 8/21/24
MACKIN RD | 2927 | MACKIN RD | 40-11-106-002 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3105 | MACKIN RD | 40-10-227-015 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3126 | MACKIN RD | 40-10-226-010 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACKIN RD | 3430 | MACKIN RD | 40-03-484-014 | Completed | 2024-09-12 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-10-07 | 2024-10-07
MACOMBER ST | 2602 | MACOMBER ST | 41-08-432-002 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
MAJOR ST | 802 | MAJOR ST | 41-30-156-026 | Completed | 2024-07-22 | 2024-07-31 | 2024-07-22 | 2024-07-24 | 2024-07-31 | 2024-07-31
MAJOR ST | 806 | MAJOR ST | 41-30-156-025 | Completed | 2024-07-22 | 2024-08-09 | 2024-07-22 | 2024-08-08 | 2024-08-09 | 2024-08-09
MALLERY ST | 2718 | MALLERY ST | 40-11-126-016 | Completed | 2024-10-17 | 2024-10-30 | 2024-10-17 | 2024-10-23 | 2024-10-30 | 2024-10-30
MALLERY ST | 2827 | MALLERY ST | 40-11-127-013 | No restoration work needed; door hanger left 7/16/24
MALLERY ST | 2942 | MALLERY ST | 40-02-354-018 | Completed | 2024-07-16 | 2024-07-16 |  |  | 2024-07-16 | 2024-07-16
MANHALL AVE | 3926 | MANHALL AVE | 40-15-477-019 | Completed | 2024-09-18 | 2024-10-31 | 2024-09-18 | 2024-09-26 | 2024-10-31 | 2024-10-31
MANN AVE | 915 | MANN AVE | 40-14-354-008 | Completed | 2024-09-18 | 2024-10-11 | 2024-09-18 | 2024-09-26 | 2024-10-11 | 2024-10-11
MANN AVE | 916 | MANN AVE | 40-14-353-014 | No restoration work needed; door hanger left 8/15/24
MANN AVE | 939 | MANN AVE | 40-14-354-014 | No restoration work needed; door hanger left 8/15/24
MANN AVE | 1213 | MANN AVE | 40-23-104-012 | Completed | 2024-09-11 | 2024-09-19 | 2024-09-11 | 2024-09-19 | 2024-09-18 | 2024-09-18
MANN AVE | 1313 | MANN AVE | 40-23-109-005 | No restoration work needed; door hanger left 7/29/24
MANN AVE | 1322 | MANN AVE | 40-23-108-018 | Completed | 2024-08-12 | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12
MANN AVE | 1325 | MANN AVE | 40-23-109-008 | No restoration work needed; door hanger left 9/6/24
MANN AVE | 1326 | MANN AVE | 40-23-108-019 | No restoration work needed; door hanger left 9/6/24
MANN AVE | 1402 | MANN AVE | 40-23-108-020 | No restoration work needed; door hanger left 9/5/24
MANN AVE | 1409 | MANN AVE | 40-23-109-011 | No restoration work needed; door hanger left 8/30/24
MAPLEWOOD AVE | 1310 | MAPLEWOOD AVE | 41-08-212-010 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
MARJA ST | 5301 | MARJA ST | 46-26-453-031 | Completed | 2024-07-11 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11
MARMION AVE | 3510 | MARMION AVE | 41-09-205-002 | Completed | 2024-09-18 | 2024-09-18 |  |  | 2024-09-18 | 2024-09-18
MARMION AVE | 3715 | MARMION AVE | 41-09-226-012 | No restoration work needed; door hanger left 8/29/24
MARMION AVE | 3826 | MARMION AVE | 41-09-229-007 | Completed | 2024-10-11 | 2024-10-31 | 2024-10-11 | 2024-10-11 | 2024-10-31 | 2024-10-31
MARQUETTE ST | 507 | MARQUETTE ST | 40-11-352-015 | Completed | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | Not needed
MARSHALL ST | 2002 | MARSHALL ST | 47-32-455-032 | No restoration work needed; door hanger left 7/23/24
MARY ST | 313 | MARY ST | 40-12-203-019 | No restoration work needed; door hanger left 8/18/24
MARYLAND AVE | 2112 | MARYLAND AVE | 41-05-259-016 | Completed | 2024-09-03 | 2024-09-03 |  |  | 2024-09-03 | 2024-09-03
MARYLAND AVE | 2611 | MARYLAND AVE | 41-05-284-014 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
MARYLAND AVE | 3151 | MARYLAND AVE | 41-04-178-038 | No restoration work needed; door hanger left 7/17/24
MASON ST | 1632 | MASON ST | 40-12-128-009 | No restoration work needed; door hanger left 8/18/24
MASON ST | 2515 | MASON ST | 40-01-160-015 | Completed | 2024-10-01 | 2024-10-17 | 2024-10-01 | 2024-10-07 | 2024-10-17 | 2024-10-17
MASON ST | 2915 | MASON ST | 40-01-152-030 | Completed | 2024-10-01 | 2024-10-03 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-03
MASON ST | 3007 | MASON ST | 40-01-108-029 | No restoration work needed; door hanger left 10/1/24 | When Dewane visited site on 8/20/24, sidewalk needed to be replaced. When Greg and the contractor went back on 10/1/24, the sidewalk had been replaced and greenbelt restored. Assuming this was part of the city's sidewalk replacement program currently taking place.
MASON ST | 3401 | MASON ST | 46-36-376-042 | Completed | 2024-09-30 | 2024-10-15 | 2024-09-30 | 2024-10-03 | 2024-10-15 | 2024-10-15
MASON ST | 3426 | MASON ST | 46-36-382-006 | No restoration work needed; door hanger left 8/21/24
MASON ST | 3427 | MASON ST | 46-36-376-040 | Completed | 2024-09-04 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-04
MASON ST | 3717 | MASON ST | 46-36-376-017 | Completed | 2024-09-30 | 2024-10-15 | 2024-09-30 | 2024-10-07 | 2024-10-15 | 2024-10-15
MAXINE ST | 624 | MAXINE ST | 41-08-377-004 | No restoration work needed; door hanger left 8/8/24
MAXINE ST | 638 | MAXINE ST | 41-08-377-006 | No restoration work needed; door hanger left 7/23/24
MAXINE ST | 814 | MAXINE ST | 41-08-381-005 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
MAXINE ST | 820 | MAXINE ST | 41-08-381-007 | Completed | 2024-07-23 | 2024-07-23 |  |  | 2024-07-23 | 2024-07-23
MAXINE ST | 922 | MAXINE ST | 41-17-126-018 | Completed
MAXINE ST | 1021 | MAXINE ST | 41-17-127-015 | Completed | 2024-08-07 | 2024-08-29 | 2024-08-07 | 2024-08-29 | 2024-08-20 | 2024-08-20
MAXINE ST | 1301 | MAXINE ST | 41-17-132-011 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
MAXINE ST | 1315 | MAXINE ST | 41-17-132-014 | Completed | 2024-08-07 | 2024-08-29 | 2024-08-07 | 2024-08-29 | 2024-08-20 | 2024-08-20
MAXINE ST | 1318 | MAXINE ST | 41-17-131-023 | Completed | 2024-08-07 | 2024-09-03 | 2024-08-07 | 2024-08-20 | 2024-09-03 | 2024-09-03
MAYBURY AVE | 2013 | MAYBURY AVE | 41-17-381-004 | Completed | 2024-08-05 | 2024-08-13 | 2024-08-05 | 2024-08-12 | 2024-08-13 | 2024-08-13
MAYBURY AVE | 2234 | MAYBURY AVE | 41-20-131-042 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
MC ARAS CT | 506 | MC ARAS CT | 40-13-106-010 | Completed | 2024-09-03 | 2024-09-18 | 2024-09-03 | 2024-09-03 | 2024-09-18 | 2024-09-18
MC AVOY ST | 2049 | MC AVOY ST | 41-17-456-017 | Completed | 2024-08-09 | 2024-09-10 | 2024-08-09 | 2024-08-12 | 2024-09-10 | 2024-09-10
MC CLURE AVE | 3226 | MC CLURE AVE | 41-04-126-023 | Completed | 2024-08-19 | 2024-09-16 | 2024-08-19 | 2024-08-21 | 2024-09-16 | 2024-09-16
MC KEIGHAN AVE | 526 | MC KEIGHAN AVE | 41-29-257-006 | Completed | 2024-08-20 | 2024-09-10 | 2024-08-20 | 2024-08-26 | 2024-09-10 | 2024-09-10
MC KEIGHAN AVE | 913 | MC KEIGHAN AVE | 41-29-256-036 | No restoration work needed; door hanger left 8/10/24
MC KINLEY AVE | 810 | MC KINLEY AVE | 41-29-252-010 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MC PHAIL ST | 1822 | MC PHAIL ST | 41-17-428-019 | No restoration work needed; door hanger left 8/10/24
MC PHAIL ST | 1930 | MC PHAIL ST | 41-17-477-017 | Completed | 2024-08-09 | 2024-09-10 | 2024-08-09 | 2024-08-09 | 2024-09-10 | 2024-09-10
MC PHAIL ST | 2018 | MC PHAIL ST | 41-17-480-018 | No restoration work needed; door hanger left 8/10/24
MC QUEEN ST | 935 | MC QUEEN ST | 40-14-380-010 | Completed | 2024-07-18 | 2024-09-09 | 2024-07-18 | 2024-08-08 | 2024-09-09 | 2024-09-09
MEISNER ST | 2976 | MEISNER ST | 47-33-355-019 | Completed | 2024-10-11 | 2024-11-01 | 2024-10-11 | 2024-10-11 | 2024-11-01 | 2024-11-01
MENOMINEE AVE | 3102 | MENOMINEE AVE | 41-20-429-031 | No restoration work needed; door hanger left 10/14/24
MENOMINEE AVE | 3113 | MENOMINEE AVE | 41-20-430-014 | No restoration work needed; door hanger left 8/10/24
MENTON AVE | 4135 | MENTON AVE | 41-29-178-005 | Completed | 2024-08-20 | 2024-10-23 | 2024-08-20 | 2024-10-23 | 2024-09-09 | 2024-09-09
MENTON AVE | 4214 | MENTON AVE | 41-29-177-044 | Completed | 2024-08-20 | 2024-09-09 | 2024-08-20 | 2024-08-26 | 2024-09-09 | 2024-09-09
MILBOURNE AVE | 1650 | MILBOURNE AVE | 40-11-226-017 | No restoration work needed; door hanger left 7/29/24
MILBOURNE AVE | 2239 | MILBOURNE AVE | 40-02-426-023 | No restoration work needed; door hanger left 7/29/24
MILBOURNE AVE | 3301 | MILBOURNE AVE | 40-02-226-021 | No restoration work needed; door hanger left 7/29/24
MILBOURNE AVE | 3602 | MILBOURNE AVE | 46-35-482-004 | No restoration work needed; door hanger left 7/29/24
MILBOURNE AVE | 3610 | MILBOURNE AVE | 46-35-482-002 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
MILBOURNE AVE | 4018 | MILBOURNE AVE | 46-35-429-017 | Completed | 2024-07-23 | 2024-09-17 | 2024-07-23 | 2024-07-31 | 2024-09-17 | 2024-09-17
MILLER RD | 2204 | MILLER RD | 40-23-232-026 | Completed | 2024-07-17 | 2024-09-09 | 2024-07-17 | 2024-07-23 | 2024-09-09 | 2024-09-09
MILLER RD | 2306 | MILLER RD | 40-23-231-029 | No restoration work needed; door hanger left 7/29/24
MILLER RD | 2610 | MILLER RD | 40-23-212-023 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILLER RD | 2802 | MILLER RD | 40-23-184-024 | No restoration work needed; door hanger left 10/25/24
MILLER RD | 2810 | MILLER RD | 40-23-184-023 | No restoration work needed; door hanger left 7/29/24
MILLER RD | 3105 | MILLER RD | 40-23-305-028 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILTON DR | 4525 | MILTON DR | 41-29-152-022 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MILTON DR | 4629 | MILTON DR | 41-29-152-029 | Completed | 2024-08-20 | 2024-11-01 | 2024-08-20 | 2024-08-26 | 2024-11-01 | 2024-11-01
MISSOURI AVE | 1903 | MISSOURI AVE | 41-08-211-012 | No restoration work needed; door hanger left 10/25/24
MISSOURI AVE | 2106 | MISSOURI AVE | 41-08-251-049 | No restoration work needed; door hanger left 8/12/24
MISSOURI AVE | 2402 | MISSOURI AVE | 41-08-276-001 | No restoration work needed; door hanger left 8/20/24
MISSOURI AVE | 2430 | MISSOURI AVE | 41-08-276-008 | Completed | 2024-08-09 | 2024-09-10 | 2024-08-09 | 2024-08-21 | 2024-09-10 | 2024-09-10
MISSOURI AVE | 2601 | MISSOURI AVE | 41-08-238-014 | Completed | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-29 | 2024-07-31 | 2024-07-31
MONTANA AVE | 1518 | MONTANA AVE | 41-05-110-005 | No restoration work needed; door hanger left 8/28/24
MONTANA AVE | 1529 | MONTANA AVE | 41-05-108-021 | No restoration work needed; door hanger left 8/28/24
MONTANA AVE | 1817 | MONTANA AVE | 41-05-133-044 | Completed | 2024-08-19 | 2024-09-16 | 2024-08-19 | 2024-09-03 | 2024-09-16 | 2024-09-16
MONTCLAIR AVE | 1623 | MONTCLAIR AVE | 41-08-378-024 | No restoration work needed; door hanger left 8/10/24
MONTCLAIR AVE | 1918 | MONTCLAIR AVE | 41-08-456-004 | Completed | 2024-11-01 | 2024-11-08 | 2024-11-01 | 2024-11-06 | 2024-11-08 | 2024-11-08
MONTEITH ST | 1909 | MONTEITH ST | 40-14-229-015 | Completed | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-18 | Not needed
MONTEITH ST | 1921 | MONTEITH ST | 40-14-229-012 | Completed | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | Turf was established
MONTEITH ST | 1922 | MONTEITH ST | 40-14-228-031 | Completed | 2024-08-01 | 2024-09-18 | 2024-08-01 | 2024-08-08 | 2024-09-18 | 2024-09-18
MONTEITH ST | 2007 | MONTEITH ST | 40-14-229-008 | Completed | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17 | Not needed
MONTEITH ST | 2008 | MONTEITH ST | 40-14-228-028 | Completed | 2023-07-19 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-07-19 | 2023-07-19
MONTEITH ST | 2101 | MONTEITH ST | 40-14-202-009 | No restoration work needed; door hanger left 8/28/24
MONTEITH ST | 2107 | MONTEITH ST | 40-14-202-008 | Completed | 2024-07-17 | 2024-09-18 | 2024-07-17 | 2024-08-08 | 2024-09-18 | 2024-09-18
MONTEITH ST | 2215 | MONTEITH ST | 40-14-202-002 | No restoration work needed; door hanger left 7/29/24
MONTEITH ST | 2308 | MONTEITH ST | 40-11-458-018 | Completed | 2023-07-19 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-07-19 | 2023-07-19
MONTERAY AVE | 1514 | MONTERAY AVE | 40-23-211-007 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MONTERAY AVE | 1518 | MONTERAY AVE | 40-23-211-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
MONTERAY AVE | 1550 | MONTERAY AVE | 40-23-254-014 | No restoration work needed; door hanger left 7/29/24
MOUNTAIN AVE | 2006 | MOUNTAIN AVE | 41-08-459-012 | No restoration work needed; door hanger left 8/6/24
MOUNTAIN AVE | 2014 | MOUNTAIN AVE | 41-08-459-014 | No restoration work needed; door hanger left 8/6/24
MOUNTAIN AVE | 2102 | MOUNTAIN AVE | 41-08-459-015 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2201 | MOUNTAIN AVE | 41-08-481-016 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2215 | MOUNTAIN AVE | 41-08-481-020 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2224 | MOUNTAIN AVE | 41-08-483-005 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2405 | MOUNTAIN AVE | 41-08-481-030 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2522 | MOUNTAIN AVE | 41-08-484-007 | No restoration work needed; door hanger left 8/10/24
MOUNTAIN AVE | 2526 | MOUNTAIN AVE | 41-08-484-008 | No restoration work needed; door hanger left 10/12/24
MOUNTAIN AVE | 2617 | MOUNTAIN AVE | 41-08-482-021 | No restoration work needed; door hanger left 8/28/24
MT ELLIOTT AVE | 2526 | MT ELLIOTT AVE | 40-02-284-010 | Completed | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | Not needed
MT ELLIOTT AVE | 2723 | MT ELLIOTT AVE | 40-02-279-026 | Completed | 2024-08-08 | 2024-09-17 | 2024-08-08 | 2024-08-08 | 2024-09-17 | 2024-09-17
MULBERRY LN | 1406 | MULBERRY LN | 40-25-202-047 | No restoration work needed; door hanger left 8/28/24
N AVERILL AVE | 2058 | N AVERILL AVE | 41-04-455-003 | Completed | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Not needed
N AVERILL AVE | 2062 | N AVERILL AVE | 41-04-455-002 | No restoration work needed; door hanger left 7/30/24 | 2023-08-29 | 2024-08-08 | 2023-08-29 | 2024-08-08 | 2023-12-20 | 2023-12-20
N AVERILL AVE | 2117 | N AVERILL AVE | 41-04-380-025 | No restoration work needed; door hanger left 8/12/24
N AVERILL AVE | 2207 | N AVERILL AVE | 41-04-377-021 | No restoration work needed; door hanger left 8/12/24
N AVERILL AVE | 2211 | N AVERILL AVE | 41-04-377-020 | No restoration work needed; door hanger left 8/12/24
N BALLENGER HWY | 1401 | N BALLENGER HWY | 40-11-104-028 | No restoration work needed; door hanger left 7/29/24
N BALLENGER HWY | 1701 | N BALLENGER HWY | 40-02-356-026 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
N BALLENGER HWY | 1801 | N BALLENGER HWY | 40-02-354-026 | Completed | 2024-07-25 | 2024-08-09 | 2024-07-25 | 2024-08-08 | 2024-08-09 | 2024-08-09
N CHEVROLET AVE | 902 | N CHEVROLET AVE | 40-11-455-023 | Completed | 2024-08-01 | 2024-09-18 | 2024-08-01 | 2024-08-08 | 2024-09-18 | 2024-09-18
N CHEVROLET AVE | 971 | N CHEVROLET AVE | 40-11-456-001 | No restoration work needed; door hanger left 10/14/24
N CHEVROLET AVE | 1009 | N CHEVROLET AVE | 40-11-380-033 | No restoration work needed; door hanger left 10/14/24
N CHEVROLET AVE | 1348 | N CHEVROLET AVE | 40-11-281-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
N CHEVROLET AVE | 1401 | N CHEVROLET AVE | 40-11-253-024 | No restoration work needed; door hanger left 8/12/24
N CHEVROLET AVE | 1601 | N CHEVROLET AVE | 40-11-229-033 | Completed | 2024-07-30 | 2024-09-17 | 2024-07-30 | 2024-08-08 | 2024-09-17 | 2024-09-17
N CHEVROLET AVE | 2722 | N CHEVROLET AVE | 40-02-279-004 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
N DEXTER ST | 1421 | N DEXTER ST | 41-09-210-008 | Completed | 2024-08-19 | 2024-09-10 | 2024-08-19 | 2024-08-21 | 2024-09-10 | 2024-09-10
N DEXTER ST | 2070 | N DEXTER ST | 41-04-477-002 | Completed | 2024-11-01 | 2024-11-13 | 2024-11-01 | 2024-11-12 | 2024-11-13 | 2024-11-13
N FRANKLIN AVE | 2302 | N FRANKLIN AVE | 41-05-406-018 | No restoration work needed; door hanger left 8/12/24
N FRANKLIN AVE | 3718 | N FRANKLIN AVE | 47-32-454-031 | No restoration work needed; door hanger left 8/28/24
N GRAND TRAVERSE | 504 | N GRAND TRAVERSE | 40-12-460-005 | No restoration work needed; door hanger left 10/15/24
N GRAND TRAVERSE | 622 | N GRAND TRAVERSE | 40-12-457-004 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N GRAND TRAVERSE | 712 | N GRAND TRAVERSE | 40-12-453-006 | No restoration work needed; door hanger left 10/15/24
N GRAND TRAVERSE | 928 | N GRAND TRAVERSE | 40-12-404-001 | Completed | 2024-10-08 | 2024-10-18 | 2024-10-08 | 2024-10-10 | 2024-10-18 | 2024-10-18
N GRAND TRAVERSE | 1633 | N GRAND TRAVERSE | 40-12-106-027 | No restoration work needed; door hanger left 7/29/24
N GRAND TRAVERSE | 1636 | N GRAND TRAVERSE | 40-12-107-010 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N MEADE ST | 1709 | N MEADE ST | 41-08-228-013 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 816 | N STEVENSON ST | 40-12-377-004 | No restoration work needed; door hanger left 8/28/24
N STEVENSON ST | 1209 | N STEVENSON ST | 40-12-352-002 | Completed | 2024-10-04 | 2024-10-30 | 2024-10-04 | 2024-10-05 | 2024-10-30 | 2024-10-30
N STEVENSON ST | 2502 | N STEVENSON ST | 40-11-179-033 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 2606 | N STEVENSON ST | 40-11-179-023 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
N STEVENSON ST | 3018 | N STEVENSON ST | 40-10-232-015 | Completed | 2024-07-24 | 2024-10-17 | 2024-07-24 | 2024-07-31 | 2024-10-17 | 2024-10-17
N VERNON AVE | 1705 | N VERNON AVE | 41-08-203-031 | Completed | 2024-08-19 | 2024-09-10 | 2024-08-19 | 2024-08-21 | 2024-09-10 | 2024-09-10
N VERNON AVE | 2007 | N VERNON AVE | 41-05-457-016 | Completed | 2024-08-19 | 2024-10-19 | 2024-08-19 | 2024-08-21 | 2024-10-19 | 2024-10-19
N VERNON AVE | 2208 | N VERNON AVE | 41-05-411-009 | Completed | 2024-08-19 | 2024-09-10 | 2024-08-19 | 2024-09-03 | 2024-09-10 | 2024-09-10
NATHAN AVE | 2960 | NATHAN AVE | 47-33-353-014 | Completed | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Not needed
NEBRASKA AVE | 2004 | NEBRASKA AVE | 41-08-255-008 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
NEBRASKA AVE | 2100 | NEBRASKA AVE | 41-08-255-014 | Completed | 2024-07-31 | 2024-11-08 | 2024-07-31 | 2024-10-29 | 2024-11-08 | 2024-11-08
NEBRASKA AVE | 2606 | NEBRASKA AVE | 41-08-282-006 | No restoration work needed; door hanger left 8/29/24
NELSON ST | 1101 | NELSON ST | 41-07-201-059 | No restoration work needed; door hanger left 8/29/24
NEW YORK AVE | 1805 | NEW YORK AVE | 41-05-327-031 | No restoration work needed; door hanger left 8/29/24
NINTH AVE | 420 | NINTH AVE | 40-12-185-030 | No restoration work needed; door hanger left 10/14/24
NOLEN DR | 2202 | NOLEN DR | 40-14-252-027 | No restoration work needed; door hanger left 8/29/24
NORBERT ST | 2714 | NORBERT ST | 40-11-304-017 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
NORWOOD DR | 3110 | NORWOOD DR | 40-14-328-022 | No restoration work needed; door hanger left 7/29/24
NORWOOD DR | 3218 | NORWOOD DR | 40-14-328-011 | No restoration work needed; door hanger left 8/29/24
NORWOOD DR | 3314 | NORWOOD DR | 40-14-160-022 | Completed | 2024-07-18 | 2024-10-08 | 2024-07-18 | 2024-07-19 | 2024-10-08 | 2024-10-08
NORWOOD DR | 3315 | NORWOOD DR | 40-14-304-010 | Completed | 2024-07-18 | 2024-10-08 | 2024-07-18 | 2024-07-19 | 2024-10-08 | 2024-10-08
NORWOOD DR | 3510 | NORWOOD DR | 40-14-160-015 | Completed | 2024-09-03 | 2024-10-11 | 2024-09-03 | 2024-09-04 | 2024-10-11 | 2024-10-11
NORWOOD DR | 3628 | NORWOOD DR | 40-14-155-030 | Completed | 2024-07-18 | 2024-11-01 | 2024-07-18 | 2024-08-08 | 2024-11-01 | 2024-11-01
OAK ST | 608 | OAK ST | 40-13-284-007 | Completed | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18
OAK ST | 717 | OAK ST | 41-18-153-005 | No restoration work needed; door hanger left 7/29/24
OAK ST | 723 | OAK ST | 41-18-153-006 | No restoration work needed; door hanger left 7/29/24
OAK ST | 725 | OAK ST | 41-18-153-025 | No restoration work needed; door hanger left 7/29/24
OAK ST | 803 | OAK ST | 41-18-153-008 | No restoration work needed; door hanger left 7/29/24
OAK ST | 923 | OAK ST | 41-18-302-028 | No restoration work needed; door hanger left 7/29/24
OAK ST | 1028 | OAK ST | 41-18-304-005 | Completed | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18
ODETTE ST | 201 | ODETTE ST | 40-01-377-010 | Completed | 2024-07-24 | 2024-09-17 | 2024-07-24 | 2024-07-31 | 2024-09-17 | 2024-09-17
ODETTE ST | 207 | ODETTE ST | 40-01-377-009 | Completed | 2024-07-24 | 2024-09-17 | 2024-07-24 |  | 2024-09-17 | 2024-09-17
ODETTE ST | 223 | ODETTE ST | 40-01-377-004 | No restoration work needed; door hanger left 7/29/24
ODETTE ST | 228 | ODETTE ST | 40-01-376-024 | Completed | 2024-07-24 | 2024-09-17 | 2024-07-24 | 2024-07-31 | 2024-09-17 | 2024-09-17
ODETTE ST | 405 | ODETTE ST | 40-01-354-007 | No restoration work needed; door hanger left 7/29/24
ODETTE ST | 521 | ODETTE ST | 40-01-353-008 | No restoration work needed; door hanger left 7/29/24
OGEMA AVE | 4319 | OGEMA AVE | 41-29-254-004 | Completed | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | Not needed
OHIO AVE | 1629 | OHIO AVE | 41-08-133-024 | No restoration work needed; door hanger left 8/29/24
OHIO AVE | 2131 | OHIO AVE | 41-08-208-036 | No restoration work needed; door hanger left 8/29/24
OKLAHOMA AVE | 2218 | OKLAHOMA AVE | 41-05-256-006 | Completed | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Not needed
ORANGE LN | 6708 | ORANGE LN | 46-26-204-015 | Completed | 2024-07-30 | 2024-09-16 | 2024-07-30 | 2024-07-31 | 2024-09-16 | 2024-09-16
ORANGE LN | 6908 | ORANGE LN | 46-26-204-003 | Completed | 2024-07-30 | 2024-09-16 | 2024-07-30 | 2024-07-31 | 2024-09-16 | 2024-09-16
ORCHARD LN | 2520 | ORCHARD LN | 40-11-329-055 | No restoration work needed; door hanger left 7/29/24
OREN AVE | 1807 | OREN AVE | 40-01-458-021 | No restoration work needed; door hanger left 7/29/24
OREN AVE | 2101 | OREN AVE | 40-01-417-007 | No restoration work needed; door hanger left 7/29/24
ORR ST | 4011 | ORR ST | 40-15-456-008 | No restoration work needed; door hanger left 8/29/24
ORR ST | 4023 | ORR ST | 40-15-456-005 | No restoration work needed; door hanger left 8/29/24
ORR ST | 4039 | ORR ST | 40-15-456-002 | Completed | 2024-08-01 | 2024-09-09 | 2024-08-01 | 2024-08-08 | 2024-09-09 | 2024-09-09
OVERHILL DR | 1707 | OVERHILL DR | 40-23-255-001 | No restoration work needed; door hanger left 8/29/24
OVERHILL DR | 1827 | OVERHILL DR | 40-23-255-004 | Completed | 2024-08-01 | 2024-09-09 | 2024-08-01 | 2024-08-29 | 2024-09-09 | 2024-09-09
OWEN ST | 1851 | OWEN ST | 41-17-430-012 | No restoration work needed; door hanger left 8/29/24
OWEN ST | 1857 | OWEN ST | 41-17-430-042 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
OXFORD LN | 2011 | OXFORD LN | 40-23-328-002 | No restoration work needed; door hanger left 8/29/24
OXFORD LN | 2040 | OXFORD LN | 40-23-327-020 | No restoration work needed; door hanger left 8/29/24
OXLEY DR | 1811 | OXLEY DR | 46-26-379-014 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
OXLEY DR | 2020 | OXLEY DR | 46-26-377-001 | No restoration work needed; door hanger left 7/29/24
PADDINGTON AVE | 850 | PADDINGTON AVE | 41-19-156-020 | No restoration work needed; door hanger left 8/23/24
PADDINGTON AVE | 938 | PADDINGTON AVE | 41-19-155-035 | No restoration work needed; door hanger left 8/23/24
PADDINGTON AVE | 950 | PADDINGTON AVE | 41-19-155-018 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PADUCAH ST | 2518 | PADUCAH ST | 40-11-376-031 | Completed | 2024-10-04 | 2024-10-21 | 2024-10-04 | 2024-10-12 | 2024-10-21 | 2024-10-21
PADUCAH ST | 2534 | PADUCAH ST | 40-11-376-027 | No restoration work needed; door hanger left 7/29/24
PADUCAH ST | 2547 | PADUCAH ST | 40-11-377-010 | Completed | 2024-09-18 | 2024-11-08 | 2024-11-05 | 2024-11-08 | 2024-09-18 | 2024-09-18
PAGE ST | 309 | PAGE ST | 40-01-462-019 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PAGE ST | 326 | PAGE ST | 40-12-203-010 | No restoration work needed; door hanger left 7/29/24
PAGE ST | 401 | PAGE ST | 40-01-485-013 | No restoration work needed; door hanger left 7/29/24
PAGE ST | 425 | PAGE ST | 40-01-485-020 | Completed | 2023-08-08 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-08-08 | 2023-08-08
PAGE ST | 517 | PAGE ST | 40-01-486-014 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PARK FOREST DR | 3911 | PARK FOREST DR | 40-25-104-006 | No restoration work needed; door hanger left 8/23/24
PARK FOREST DR | 3914 | PARK FOREST DR | 40-25-101-076 | No restoration work needed; door hanger left 8/23/24
PARK FOREST DR | 4106 | PARK FOREST DR | 40-25-101-032 | No restoration work needed; door hanger left 8/23/24
PARK FOREST DR | 4110 | PARK FOREST DR | 40-25-101-034 | No restoration work needed; door hanger left 11/1/24
PARK ST | 1601 | PARK ST | 41-18-436-043 | No restoration work needed; door hanger left 8/23/24
PARK ST | 1720 | PARK ST | 41-18-435-025 | Completed | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2024-08-07 | 2024-08-09 | 2024-08-09
PARKSIDE DR | 3340 | PARKSIDE DR | 40-23-351-018 | No restoration work needed; door hanger left 8/29/24
PARTRIDGE ST | 619 | PARTRIDGE ST | 41-19-132-007 | No restoration work needed; door hanger left 9/3/24
PEER AVE | 202 | PEER AVE | 41-19-427-001 | Completed | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-26 | 2024-07-31 | 2024-07-31
PENBROOK LN | 1935 | PENBROOK LN | 40-25-104-011 | No restoration work needed; door hanger left 9/3/24
PENCOMBE PL | 3117 | PENCOMBE PL | 40-14-180-014 | Completed | 2024-07-16 | 2024-09-12 | 2024-07-16 | 2024-07-31 | 2024-09-12 | 2024-09-12
PENCOMBE PL | 3201 | PENCOMBE PL | 40-14-180-010 | No restoration work needed; door hanger left 7/29/24
PENCOMBE PL | 3205 | PENCOMBE PL | 40-14-180-009 | Completed | 2024-10-04 | 2024-10-15 | 2024-10-04 | 2024-10-12 | 2024-10-15 | 2024-10-15
PENCOMBE PL | 3306 | PENCOMBE PL | 40-14-177-019 | Completed | 2024-10-04 | 2024-10-15 | 2024-10-04 | 2024-10-05 | 2024-10-15 | 2024-10-15
PENCOMBE PL | 3312 | PENCOMBE PL | 40-14-177-017 | No restoration work needed; door hanger left 7/29/24
PENCOMBE PL | 3324 | PENCOMBE PL | 40-14-177-014 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PENGELLY RD | 4429 | PENGELLY RD | 41-29-151-065 | No restoration work needed; door hanger left 8/23/24
PENGELLY RD | 4513 | PENGELLY RD | 41-29-151-051 | No restoration work needed; door hanger left 9/3/24
PENNSYLVANIA AVE | 1640 | PENNSYLVANIA AVE | 41-08-176-011 | No restoration work needed; door hanger left 10/25/24
PENOYER CT | 1720 | PENOYER CT | 41-08-205-011 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
PERRY ST | 913 | PERRY ST | 40-11-482-013 | No restoration work needed; door hanger left 7/29/24
PERRY ST | 916 | PERRY ST | 40-14-226-001 | Completed | 2024-07-16 | 2024-09-18 | 2024-07-16 | 2024-07-17 | 2024-09-18 | 2024-09-18
PERRY ST | 962 | PERRY ST | 40-11-481-004 | Completed | 2024-07-16 | 2024-09-18 | 2024-07-16 | 2024-07-18 | 2024-09-18 | 2024-09-18
PERRY ST | 970 | PERRY ST | 40-11-481-002 | No restoration work needed; door hanger left 7/29/24
PERSHING ST | 1017 | PERSHING ST | 40-13-359-008 | No restoration work needed; door hanger left 7/29/24
PERSHING ST | 1202 | PERSHING ST | 40-13-362-007 | Completed | 2024-07-19 | 2024-09-09 | 2024-07-19 | 2024-09-09 | 2024-09-09
PETTIBONE AVE | 747 | PETTIBONE AVE | 41-19-382-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PETTIBONE AVE | 748 | PETTIBONE AVE | 41-19-380-017 | Completed | 2024-11-01 | 2024-11-08 | 2024-11-01 | 2024-11-08 | Not needed
PETTIBONE AVE | 916 | PETTIBONE AVE | 41-19-355-030 | No restoration work needed; door hanger left 9/3/24
PETTIBONE AVE | 1016 | PETTIBONE AVE | 40-24-481-035 | No restoration work needed; door hanger left 8/15/24
PETTIBONE AVE | 1210 | PETTIBONE AVE | 40-24-480-030 | No restoration work needed; door hanger left 8/15/24
PETTIBONE AVE | 1313 | PETTIBONE AVE | 40-24-482-031 | No restoration work needed; door hanger left 8/15/24
PINEHURST AVE | 1036 | PINEHURST AVE | 40-25-281-023 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PINGREE AVE | 1902 | PINGREE AVE | 41-17-479-001 | No restoration work needed; door hanger left 8/23/24
PINGREE AVE | 2016 | PINGREE AVE | 41-17-480-029 | No restoration work needed; door hanger left 8/23/24
PITKIN AVE | 3701 | PITKIN AVE | 41-09-230-015 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
PITKIN AVE | 3743 | PITKIN AVE | 41-09-230-028 | No restoration work needed; door hanger left 8/23/24
PITKIN AVE | 3846 | PITKIN AVE | 41-09-233-013 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
PLAINFIELD AVE | 2518 | PLAINFIELD AVE | 47-32-234-020 | Completed | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | Not needed
PLAINFIELD AVE | 2818 | PLAINFIELD AVE | 47-33-105-011 | No restoration work needed; door hanger left 9/3/24
POPLAR ST | 1247 | POPLAR ST | 41-07-282-035 | Completed | 2024-09-03 | 2024-09-10 | 2024-09-03 | 2024-09-04 | 2024-09-10 | 2024-09-10
POPLAR ST | 1251 | POPLAR ST | 41-07-282-036 | No restoration work needed; door hanger left 7/29/24
POPLAR ST | 1369 | POPLAR ST | 41-07-284-018 | Completed | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-09-03 | Not needed
PROCTOR AVE | 1905 | PROCTOR AVE | 40-02-457-016 | Completed | 2024-07-30 | 2024-09-17 | 2024-07-30 | 2024-08-08 | 2024-09-17 | 2024-09-17
PROCTOR AVE | 2213 | PROCTOR AVE | 40-02-405-037 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PROCTOR AVE | 2614 | PROCTOR AVE | 40-02-276-036 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
PROCTOR AVE | 3209 | PROCTOR AVE | 40-02-204-018 | No restoration work needed; door hanger left 7/29/24
PROSPECT ST | 729 | PROSPECT ST | 40-12-384-017 | No restoration work needed; door hanger left 9/3/24
PROSPECT ST | 1517 | PROSPECT ST | 40-12-304-004 | Completed | 2024-07-31 | 2024-10-18 | 2024-07-31 | 2024-07-31 | 2024-10-18 | 2024-10-18
PROSPECT ST | 2710 | PROSPECT ST | 40-11-176-021 | No restoration work needed; door hanger left 7/29/24
PROSPECT ST | 2729 | PROSPECT ST | 40-11-177-002 | No restoration work needed; door hanger left 7/29/24
RACE ST | 3422 | RACE ST | 46-35-485-011 | No restoration work needed; door hanger left 7/29/24
RACE ST | 3609 | RACE ST | 46-35-484-016 | No restoration work needed; door hanger left 7/29/24
RADCLIFFE AVE | 2112 | RADCLIFFE AVE | 40-24-104-007 | No restoration work needed; door hanger left 7/29/24
RADCLIFFE AVE | 2115 | RADCLIFFE AVE | 40-24-106-006 | No restoration work needed; door hanger left 7/29/24
RADCLIFFE AVE | 2202 | RADCLIFFE AVE | 40-24-104-005 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
RADCLIFFE AVE | 2208 | RADCLIFFE AVE | 40-24-104-004 | No restoration work needed; door hanger left 7/29/24
RAMSAY BLVD | 1606 | RAMSAY BLVD | 40-24-105-003 | No restoration work needed; door hanger left 7/29/24
RAMSAY BLVD | 1818 | RAMSAY BLVD | 40-24-106-014 | No restoration work needed; door hanger left 7/29/24
RAMSAY BLVD | 1901 | RAMSAY BLVD | 40-24-152-003 | No restoration work needed; door hanger left 7/29/24
RANDY CT | 1510 | RANDY CT | 46-26-403-008 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 1909 | RASKOB ST | 40-11-431-011 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 1912 | RASKOB ST | 40-11-430-027 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 2001 | RASKOB ST | 40-11-431-008 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2005 | RASKOB ST | 40-11-431-007 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 2202 | RASKOB ST | 40-11-405-037 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 2206 | RASKOB ST | 40-11-405-036 | No restoration work needed; door hanger left 10/7/24 | Once MissDig marked the water line, it was determined that the repairs were not related to the SLE
RASKOB ST | 2213 | RASKOB ST | 40-11-406-016 | No restoration work needed; door hanger left 9/3/24
RASKOB ST | 2218 | RASKOB ST | 40-11-405-032 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2317 | RASKOB ST | 40-11-406-008 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 2321 | RASKOB ST | 40-11-406-006 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2501 | RASKOB ST | 40-11-402-003 | Completed | 2024-07-23 | 2024-10-15 | 2024-07-23 | 2024-07-24 | 2024-10-15 | 2024-10-15
RASKOB ST | 2506 | RASKOB ST | 40-11-401-011 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
RASKOB ST | 2612 | RASKOB ST | 40-11-183-033 | No restoration work needed; door hanger left 9/3/24
RASKOB ST | 2648 | RASKOB ST | 40-11-183-022 | No restoration work needed; door hanger left 7/29/24
RASKOB ST | 2932 | RASKOB ST | 40-11-155-012 | Completed | 2024-07-23 | 2024-09-18 | 2024-07-23 | 2024-07-24 | 2024-09-18 | 2024-09-18
RASPBERRY LN | 1401 | RASPBERRY LN | 40-25-255-028 | No restoration work needed; door hanger left 9/3/24
RASPBERRY LN | 1601 | RASPBERRY LN | 40-25-254-026 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
RED ARROW RD | 3914 | RED ARROW RD | 41-29-104-013 | No restoration work needed; door hanger left 9/3/24
REID ST | 2302 | REID ST | 40-14-477-021 | Completed | 2024-11-01 | 2024-11-09 | 2024-11-01 | 2024-11-09 | 2024-11-08 | 2024-11-08
REID ST | 2426 | REID ST | 40-14-458-022 | Completed | 2024-07-18 | 2024-09-09 | 2024-07-18 | 2024-08-08 | 2024-09-09 | 2024-09-09
REID ST | 2434 | REID ST | 40-14-458-021 | No restoration work needed; door hanger left 7/29/24
REID ST | 2438 | REID ST | 40-14-458-020 | Completed | 2024-07-18 | 2024-09-09 | 2024-07-18 | 2024-08-08 | 2024-09-09 | 2024-09-09
REID ST | 2450 | REID ST | 40-14-458-018 | No restoration work needed; door hanger left 9/3/24
REMINGTON AVE | 1034 | REMINGTON AVE | 40-24-277-020 | Completed | 2024-08-08 | 2024-09-09 | 2024-08-08 | 2024-08-29 | 2024-09-09 | 2024-09-09
REMINGTON AVE | 1133 | REMINGTON AVE | 40-24-278-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
REYNOLDS ST | 2718 | REYNOLDS ST | 40-14-387-023 | Completed | 2023-07-28 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2023-07-28 | 2023-07-28
REYNOLDS ST | 2823 | REYNOLDS ST | 40-14-389-004 | No restoration work needed; door hanger left 7/29/24
REYNOLDS ST | 2830 | REYNOLDS ST | 40-14-387-012 | Completed | 2024-07-18 | 2024-09-09 | 2024-07-18 | 2024-07-24 | 2024-09-09 | 2024-09-09
RISEDORPH AVE | 3136 | RISEDORPH AVE | 41-04-332-011 | No restoration work needed; door hanger left 11/1/24 | Sidewalk and driveway completed by COF; not related to this project
RISEDORPH AVE | 3814 | RISEDORPH AVE | 41-04-432-004 | No restoration work needed; door hanger left 8/21/24
RISEDORPH AVE | 3834 | RISEDORPH AVE | 41-04-432-010 | No restoration work needed; door hanger left 8/21/24
ROCKCREEK LN | 1802 | ROCKCREEK LN | 40-25-106-043 | Completed | 2024-11-01 | 2024-11-08 | 2024-11-01 | 2024-11-06 | 2024-11-08 | 2024-11-08
ROOT ST | 1036 | ROOT ST | 40-12-282-059 | No restoration work needed; door hanger left 7/29/24
ROOT ST | 1214 | ROOT ST | 40-12-278-010 | Completed | 2024-10-30 | 2024-10-30 |  |  | 2024-10-30 | 2024-10-30
ROOT ST | 1529 | ROOT ST | 40-12-231-037 | No restoration work needed; door hanger left 7/29/24
ROOT ST | 1914 | ROOT ST | 40-01-479-012 | Completed | 2024-10-11 | 2024-10-30 | 2024-10-11 | 2024-10-11 | 2024-10-30
ROOT ST | 1917 | ROOT ST | 40-01-478-015 | No restoration work needed; door hanger left 7/29/24
ROSALIE DR | 117 | ROSALIE DR | 41-19-433-005 | Completed | 2024-07-17 | 2024-07-31 | 2024-07-17 | 2024-07-26 | 2024-07-31 | 2024-07-31
ROSALIE DR | 121 | ROSALIE DR | 41-19-433-025 | Completed | 2024-07-23 | 2024-07-31 | 2024-07-23 | 2024-07-26 | 2024-07-31 | 2024-07-31
ROSEANNA DR | 6701 | ROSEANNA DR | 47-29-201-038 | No restoration work needed; door hanger left 9/4/24
ROSELAWN DR | 1706 | ROSELAWN DR | 46-35-127-044 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1726 | ROSELAWN DR | 46-35-127-039 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1813 | ROSELAWN DR | 46-35-128-014 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1814 | ROSELAWN DR | 46-35-127-035 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1818 | ROSELAWN DR | 46-35-127-034 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1901 | ROSELAWN DR | 46-35-128-010 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1905 | ROSELAWN DR | 46-35-128-009 | No restoration work needed; door hanger left 7/29/24
ROSELAWN DR | 1922 | ROSELAWN DR | 46-35-127-047 | No restoration work needed; door hanger left 7/29/24
S BALLENGER HWY | 909 | S BALLENGER HWY | 40-14-351-002 | No restoration work needed; door hanger left 8/20/24
S BALLENGER HWY | 917 | S BALLENGER HWY | 40-14-351-003 | Completed | 2024-10-16 | 2024-11-01 | 2024-10-16 | 2024-10-17 | 2024-11-01 | 2024-11-01
S BALLENGER HWY | 921 | S BALLENGER HWY | 40-14-351-004 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
S BALLENGER HWY | 932 | S BALLENGER HWY | 40-15-479-030 | Completed | 2024-11-05 | 2024-11-08 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-08
S BALLENGER HWY | 945 | S BALLENGER HWY | 40-14-351-012 | No restoration work needed; door hanger left 8/20/24
S BALLENGER HWY | 979 | S BALLENGER HWY | 40-14-357-009 | No restoration work needed; door hanger left 8/20/24
S BALLENGER HWY | 995 | S BALLENGER HWY | 40-14-357-013 | Completed | 2024-11-05 | 2024-11-08 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-08
S BALLENGER HWY | 1706 | S BALLENGER HWY | 40-22-281-026 | Completed | 2024-08-28 | 2024-10-25 | 2024-08-28 | 2024-10-25 | 2024-09-09 | 2024-09-09
S FRANKLIN AVE | 411 | S FRANKLIN AVE | 41-08-331-005 | Completed | 2024-08-09 | 2024-09-10 | 2024-08-09 | 2024-08-21 | 2024-09-10 | 2024-09-10
S FRANKLIN AVE | 426 | S FRANKLIN AVE | 41-08-330-006 | No restoration work needed; door hanger left 8/20/24
S FRANKLIN AVE | 601 | S FRANKLIN AVE | 41-08-380-008 | Completed | 2024-08-09 | 2024-09-10 | 2024-08-09 | 2024-08-21 | 2024-09-10 | 2024-09-10
S GRAND TRAVERSE | 936 | S GRAND TRAVERSE | 41-18-302-017 | Completed | 2024-10-10 | 2024-10-18 | 2024-10-10 | 2024-10-10 | 2024-10-18 | 2024-10-18
S GRAND TRAVERSE | 1010 | S GRAND TRAVERSE | 41-18-307-013 | Completed | 2024-10-10 | 2024-11-13 | 2024-10-10 | 2024-11-07 | 2024-11-13 | 2024-11-13
S GRAND TRAVERSE | 1041 | S GRAND TRAVERSE | 41-18-309-002 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 1108 | S GRAND TRAVERSE | 41-18-308-014 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 1110 | S GRAND TRAVERSE | 41-18-308-015 | Completed | 2024-10-10 | 2024-10-25 | 2024-10-10 | 2024-10-25 | 2024-10-18 | 2024-10-18
S GRAND TRAVERSE | 1114 | S GRAND TRAVERSE | 41-18-308-025 | Completed | 2024-10-10 | 2024-10-18 | 2024-10-10 | 2024-10-10 | 2024-10-18 | 2024-10-18
S GRAND TRAVERSE | 2110 | S GRAND TRAVERSE | 41-19-132-018 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 2202 | S GRAND TRAVERSE | 41-19-132-023 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 2314 | S GRAND TRAVERSE | 41-19-133-016 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 2902 | S GRAND TRAVERSE | 41-19-331-029 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE | 2914 | S GRAND TRAVERSE | 41-19-331-032 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE | 3012 | S GRAND TRAVERSE | 41-19-333-037 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 3108 | S GRAND TRAVERSE | 41-19-335-031 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE |  |  | 41-19-337-032 | Completed | 2024-11-12 | 2024-11-16 | 2024-11-12 | 2024-11-16 | Not needed
S GRAND TRAVERSE | 3520 | S GRAND TRAVERSE | 41-19-381-026 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
S GRAND TRAVERSE | 3902 | S GRAND TRAVERSE | 41-30-129-021 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE | 3906 | S GRAND TRAVERSE | 41-30-129-022 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE | 3912 | S GRAND TRAVERSE | 41-30-129-023 | No restoration work needed; door hanger left 8/20/24
S GRAND TRAVERSE | 3914 | S GRAND TRAVERSE | 41-30-129-024 | Completed | 2024-10-02 | 2024-10-26 | 2024-10-02 | 2024-10-02 | 2024-10-26 | 2024-10-26
S GRAND TRAVERSE | 4108 | S GRAND TRAVERSE | 41-30-133-025 | No restoration work needed; door hanger left 8/15/24
S MEADE ST | 701 | S MEADE ST | 41-08-485-021 | No restoration work needed; door hanger left 8/9/24
S VERNON AVE | 617 | S VERNON AVE | 41-08-455-014 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SALLY CT | 6122 | SALLY CT | 46-26-255-011 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SALLY CT | 6709 | SALLY CT | 46-26-205-035 | Completed | 2024-10-30 | 2024-10-30 |  |  | 2024-10-30 | 2024-10-30
SANFORD PL | 104 | SANFORD PL | 40-12-460-009 | No restoration work needed; door hanger left 10/14/24
SANTA BARBARA DR | 1910 | SANTA BARBARA DR | 46-35-176-026 | Completed | 2024-07-31 | 2024-08-29 | 2024-07-31 | 2024-08-29 | Not needed
SANTA BARBARA DR | 2007 | SANTA BARBARA DR | 46-35-177-026 | No restoration work needed; door hanger left 7/29/24
SANTA BARBARA DR | 2210 | SANTA BARBARA DR | 46-35-154-039 | No restoration work needed; door hanger left 7/29/24
SANTA BARBARA DR | 2314 | SANTA BARBARA DR | 46-35-154-031 | No restoration work needed; door hanger left 7/29/24
SCOTT ST | 921 | SCOTT ST | 40-13-426-005 | No restoration work needed; door hanger left 8/22/24
SCOTT ST | 925 | SCOTT ST | 40-13-426-003 | Completed | 2024-10-17 | 2024-11-01 | 2024-10-17 | 2024-10-17 | 2024-11-01 | 2024-11-01
SELBY ST | 5309 | SELBY ST | 47-30-377-017 | Completed | 2024-10-23 | 2024-10-26 | 2024-10-23 | 2024-10-24 | 2024-10-26 | 2024-10-26
SENECA ST | 1718 | SENECA ST | 40-02-357-001 | No restoration work needed; door hanger left 8/22/24
SENECA ST | 2201 | SENECA ST | 40-02-306-050 | Completed | 2024-08-27 | 2024-09-17 | 2024-08-27 | 2024-09-11 | 2024-09-17 | 2024-09-17
SENECA ST | 3006 | SENECA ST | 40-02-109-009 | Completed | 2024-08-30 | 2024-09-16 | 2024-08-30 | 2024-09-03 | 2024-09-16 | 2024-09-16
SENECA ST | 3017 | SENECA ST | 40-02-108-029 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SENECA ST | 4227 | SENECA ST | 46-35-303-006 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SEVENTH AVE | 311 | SEVENTH AVE | 40-12-405-011 | No restoration work needed; house demo'd
SEVENTH AVE | 320 | SEVENTH AVE | 40-12-402-029 | No restoration work needed; house demo'd
SEYMOUR ST | 1810 | SEYMOUR ST | 41-17-402-007 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SEYMOUR ST | 1827 | SEYMOUR ST | 41-17-403-010 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SEYMOUR ST | 2018 | SEYMOUR ST | 41-17-456-020 | Completed | 2024-07-24 | 2024-07-24 |  |  | 2024-07-24 | 2024-07-24
SHAWNEE AVE | 3017 | SHAWNEE AVE | 41-20-428-009 | Completed | 2024-09-03 | 2024-09-10 | 2024-09-03 | 2024-09-04 | 2024-09-10 | 2024-09-10
SHAWNEE AVE | 4314 | SHAWNEE AVE | 41-29-254-027 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERMAN AVE | 229 | SHERMAN AVE | 46-25-409-025 | No restoration work needed; door hanger left 10/15/24
SHERMAN AVE | 602 | SHERMAN AVE | 46-25-437-001 | No restoration work needed; door hanger left 8/22/24
SHERWOOD DR | 3119 | SHERWOOD DR | 40-14-326-007 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3321 | SHERWOOD DR | 40-14-159-012 | Completed | 2024-08-27 | 2024-11-01 | 2024-08-27 | 2024-08-29 | 2024-11-01 | 2024-11-01
SHERWOOD DR | 3322 | SHERWOOD DR | 40-14-179-011 | No restoration work needed; door hanger left 8/21/24
SHERWOOD DR | 3409 | SHERWOOD DR | 40-14-159-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3509 | SHERWOOD DR | 40-14-159-003 | No restoration work needed; door hanger left 8/21/24
SHERWOOD DR | 3515 | SHERWOOD DR | 40-14-159-001 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SHERWOOD DR | 3763 | SHERWOOD DR | 40-14-154-009 | No restoration work needed; door hanger left 8/29/24
SIMCOE AVE | 728 | SIMCOE AVE | 41-19-330-017 | No restoration work needed; door hanger left 8/21/24
SIMCOE AVE | 741 | SIMCOE AVE | 41-19-332-007 | No restoration work needed; door hanger left 8/21/24
SIMCOE AVE | 750 | SIMCOE AVE | 41-19-330-012 | No restoration work needed; door hanger left 8/21/24
SIMCOE AVE | 839 | SIMCOE AVE | 41-19-308-003 | No restoration work needed; door hanger left 8/21/24
SIMCOE AVE | 1125 | SIMCOE AVE | 40-24-429-048 | No restoration work needed; door hanger left 8/21/24
SIMCOE AVE | 1138 | SIMCOE AVE | 40-24-428-020 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2005 | SLOAN ST | 40-11-476-004 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2013 | SLOAN ST | 40-11-476-002 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SLOAN ST | 2310 | SLOAN ST | 40-11-406-032 | No restoration work needed; house demo'd 8/21/24
SLOAN ST | 2313 | SLOAN ST | 40-11-407-010 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2536 | SLOAN ST | 40-11-402-012 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SLOAN ST | 2602 | SLOAN ST | 40-11-326-032 | Completed | 2024-10-04 | 2024-10-17 | 2024-10-04 | 2024-10-12 | 2024-10-17 | 2024-10-17
SLOAN ST | 2613 | SLOAN ST | 40-11-327-015 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2617 | SLOAN ST | 40-11-327-014 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2620 | SLOAN ST | 40-11-326-026 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SLOAN ST | 2621 | SLOAN ST | 40-11-327-013 | No restoration work needed; door hanger left 8/21/24
SLOAN ST | 2716 | SLOAN ST | 40-11-184-029 | No restoration work needed; door hanger left 8/21/24
SOMERSET LN | 923 | SOMERSET LN | 41-16-228-006 | No restoration work needed; door hanger left 8/22/24
SOMERSET LN | 931 | SOMERSET LN | 41-16-228-008 | No restoration work needed; door hanger left 8/22/24
SOMERSET LN | 936 | SOMERSET LN | 41-16-227-026 | No restoration work needed; door hanger left 8/22/24
SOMERSET LN | 1001 | SOMERSET LN | 41-16-228-009 | Completed | 2024-08-28 | 2024-09-10 | 2024-08-28 | 2024-08-30 | 2024-09-10 | 2024-09-10
SOMERSET LN | 1002 | SOMERSET LN | 41-16-227-027 | Completed | 2024-08-28 | 2024-09-10 | 2024-08-28 | 2024-08-30 | 2024-09-10 | 2024-09-10
SOMERSET LN | 1207 | SOMERSET LN | 41-16-229-020 | Completed | 2024-08-28 | 2024-09-10 | 2024-08-28 | 2024-09-04 | 2024-09-10 | 2024-09-10
SOMERSET LN | 1223 | SOMERSET LN | 41-16-229-025 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SOMERSET LN | 1237 | SOMERSET LN | 41-16-229-030 | No restoration work needed; door hanger left 8/22/24
SOUTH DR | 1018 | SOUTH DR | 40-13-364-011 | No restoration work needed; door hanger left 9/4/24
SOUTHLAWN AVE | 1002 | SOUTHLAWN AVE | 41-29-228-006 | No restoration work needed; door hanger left 9/3/24
SPENCER ST | 501 | SPENCER ST | 46-36-486-019 | No restoration work needed; door hanger left 10/15/24
SPENCER ST | 906 | SPENCER ST | 41-06-127-014 | No restoration work needed; door hanger left 9/4/24
ST CLAIR ST | 702 | ST CLAIR ST | 40-14-277-003 | No restoration work needed; door hanger left 9/4/24
STANFORD AVE | 1951 | STANFORD AVE | 41-17-353-003 | No restoration work needed; door hanger left 9/3/24
STANFORD AVE | 2113 | STANFORD AVE | 41-20-104-006 | No restoration work needed; door hanger left 9/3/24
STARKWEATHER ST | 2201 | STARKWEATHER ST | 41-04-453-026 | No restoration work needed; door hanger left 8/22/24
STERLING ST | 3601 | STERLING ST | 46-35-458-022 | No restoration work needed; door hanger left 8/22/24
STERLING ST | 4033 | STERLING ST | 46-35-406-011 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
STERLING ST | 4102 | STERLING ST | 46-35-407-010 | No restoration work needed; door hanger left 10/15/24
STEVENS ST | 803 | STEVENS ST | 41-18-204-002 | Completed | 2024-10-09 | 2024-10-18 | 2024-10-09 | 2024-10-10 | 2024-10-18 | 2024-10-18
STOCKDALE ST | 101 | STOCKDALE ST | 40-12-126-017 | Completed | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Not needed
STOCKDALE ST | 211 | STOCKDALE ST | 40-12-126-007 | Completed | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Not needed
STOCKDALE ST | 318 | STOCKDALE ST | 40-01-360-024 | No restoration work needed; door hanger left 10/15/24
STOCKDALE ST | 511 | STOCKDALE ST | 40-12-101-013 | No restoration work needed; door hanger left 8/22/24
STOCKDALE ST | 701 | STOCKDALE ST | 40-11-227-020 | No restoration work needed; door hanger left 8/22/24
STOCKDALE ST | 718 | STOCKDALE ST | 40-02-483-022 | No restoration work needed; door hanger left 10/15/24
STOCKDALE ST | 812 | STOCKDALE ST | 40-02-482-021 | No restoration work needed; door hanger left 8/22/24
STOCKDALE ST | 908 | STOCKDALE ST | 40-02-481-031 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
STOCKER AVE | 1122 | STOCKER AVE | 40-23-104-019 | No restoration work needed; door hanger left 9/4/24
STOCKER AVE | 1705 | STOCKER AVE | 40-23-157-009 | No restoration work needed; door hanger left 9/4/24
STOCKTON ST | 714 | STOCKTON ST | 40-13-286-022 | Completed | 2024-07-25 | 2024-08-08 | 2024-07-25 | 2024-08-08 | 2024-07-31 | 2024-07-31
STOCKTON ST | 1501 | STOCKTON ST | 41-18-379-012 | No restoration work needed; door hanger left 9/3/24
STONE ST | 1422 | STONE ST | 40-12-179-005 | Completed | 2024-08-27 | 2024-09-17 | 2024-08-27 | 2024-09-11 | 2024-09-17 | 2024-09-17
STONEY BROOK CT | 2004 | STONEY BROOK CT | 40-25-127-025 | No restoration work needed; door hanger left 8/22/24
SUNRIDGE DR | 3615 | SUNRIDGE DR | 47-33-376-096 | Completed | 2024-08-28 | 2024-09-16 | 2024-08-28 | 2024-08-30 | 2024-09-16 | 2024-09-16
SUNRIDGE DR | 3710 | SUNRIDGE DR | 47-33-377-026 | No restoration work needed; door hanger left 8/22/24
SUNSET DR | 3305 | SUNSET DR | 40-14-177-026 | Completed | 2024-08-27 | 2024-10-15 | 2024-08-27 | 2024-08-29 | 2024-10-15 | 2024-10-15
SUNSET DR | 3759 | SUNSET DR | 40-14-103-004 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
SUSAN ST | 5215 | SUSAN ST | 46-26-455-036 | No restoration work needed; door hanger left 9/4/24
SUSSEX DR | 5329 | SUSSEX DR | 46-26-379-017 | No restoration work needed; door hanger left 9/4/24
SUSSEX DR | 5330 | SUSSEX DR | 46-26-380-019 | No restoration work needed; door hanger left 10/15/24
SUTTON AVE | 1310 | SUTTON AVE | 40-10-232-003 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
SWAYZE ST | 2121 | SWAYZE ST | 40-14-486-015 | No restoration work needed; door hanger left 9/4/24
SWAYZE ST | 2202 | SWAYZE ST | 40-14-484-033 | No restoration work needed; door hanger left 9/4/24
SWAYZE ST | 2306 | SWAYZE ST | 40-14-484-025 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
SWAYZE ST | 2522 | SWAYZE ST | 40-23-202-011 | No restoration work needed; door hanger left 9/4/24
SWAYZE ST | 2618 | SWAYZE ST | 40-23-201-016 | Completed | 2024-08-20 | 2024-09-09 | 2024-08-20 | 2024-09-09 | 2024-09-09
SWAYZE ST | 2641 | SWAYZE ST | 40-23-203-002 | Completed | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Not needed
TACKEN ST | 859 | TACKEN ST | 40-15-432-002 | No restoration work needed; door hanger left 9/4/24
TACKEN ST | 866 | TACKEN ST | 40-15-431-011 | No restoration work needed; door hanger left 9/4/24
TACKEN ST | 870 | TACKEN ST | 40-15-433-005 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TACKEN ST | 874 | TACKEN ST | 40-15-433-007 | No restoration work needed; door hanger left 9/3/24
TACKEN ST | 878 | TACKEN ST | 40-15-433-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TACKEN ST | 964 | TACKEN ST | 40-15-454-025 | Completed | 2024-08-21 | 2024-10-11 | 2024-08-21 | 2024-08-30 | 2024-10-11 | 2024-10-11
TACKEN ST | 1031 | TACKEN ST | 40-15-483-001 | Completed | 2024-07-29 | 2024-07-29 |  |  | 2024-07-29 | 2024-07-29
TACKEN ST | 1052 | TACKEN ST | 40-15-457-012 | No restoration work needed; door hanger left 8/22/24
TACKEN ST | 1058 | TACKEN ST | 40-15-457-013 | No restoration work needed; door hanger left 11/5/24
TACOMA ST | 1714 | TACOMA ST | 41-19-128-010 | No restoration work needed; door hanger left 8/22/24
TEBO ST | 1856 | TEBO ST | 41-16-329-030 | No restoration work needed; door hanger left 8/22/24
TEBO ST | 1910 | TEBO ST | 41-16-378-019 | No restoration work needed; door hanger left 8/22/24
TEBO ST | 1928 | TEBO ST | 41-16-378-023 | No restoration work needed; door hanger left 8/22/24
TEBO ST | 1936 | TEBO ST | 41-16-378-025 | Completed | 2024-10-10 | 2024-10-10 |  |  | 2024-10-10 | 2024-10-10
TEBO ST | 1941 | TEBO ST | 41-16-379-010 | No restoration work needed; door hanger left 8/22/24
TEBO ST | 2006 | TEBO ST | 41-16-378-029 | No restoration work needed; door hanger left 8/22/24
TENNYSON AVE | 359 | TENNYSON AVE | 41-29-158-012 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TERM ST | 3411 | TERM ST | 41-04-201-008 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
THETA PASSAGE | 4927 | THETA PASSAGE | 47-32-228-017 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
THOM ST | 2210 | THOM ST | 41-05-252-004 | No restoration work needed; door hanger left 8/22/24
THOM ST | 2218 | THOM ST | 41-05-252-006 | No restoration work needed; door hanger left 8/22/24
THOM ST | 3137 | THOM ST | 41-04-130-065 | No restoration work needed; door hanger left 9/3/24
THOM ST | 3138 | THOM ST | 41-04-176-035 | No restoration work needed; door hanger left 8/22/24
THOMSON ST | 804 | THOMSON ST | 41-18-207-022 | No restoration work needed; door hanger left 8/22/24
TIFFIN ST | 2517 | TIFFIN ST | 40-11-376-016 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
TILDEN ST | 755 | TILDEN ST | 47-31-305-029 | No restoration work needed; door hanger left 8/29/24
TIMBERLANE DR | 1820 | TIMBERLANE DR | 40-24-380-004 | No restoration work needed; door hanger left 9/3/24
TORRANCE ST | 2427 | TORRANCE ST | 41-05-431-036 | Completed | 2024-08-27 | 2024-09-10 | 2024-08-27 | 2024-08-29 | 2024-09-10 | 2024-09-10
TORRANCE ST | 2428 | TORRANCE ST | 41-05-432-017 | No restoration work needed; could not leave door hanger due to dog in the yard 8/22/24
TORRANCE ST | 2433 | TORRANCE ST | 41-05-431-035 | Completed | 2024-09-10 | 2024-09-10 |  |  | 2024-09-10 | 2024-09-10
TORRANCE ST | 2525 | TORRANCE ST | 41-05-431-028 | No restoration work needed; door hanger left 8/22/24
TORRANCE ST | 2526 | TORRANCE ST | 41-05-432-007 | Completed | 2024-08-27 | 2024-09-10 | 2024-08-27 | 2024-08-29 | 2024-09-10 | 2024-09-10
TORRANCE ST | 2601 | TORRANCE ST | 41-05-431-025 | No restoration work needed; door hanger left 8/22/24
TRUMBULL AVE | 2608 | TRUMBULL AVE | 40-02-181-008 | Completed | 2024-10-04 | 2024-10-21 | 2024-10-04 | 2024-10-12 | 2024-10-21 | 2024-10-21
TRUMBULL AVE | 3002 | TRUMBULL AVE | 40-02-130-003 | No restoration work needed; door hanger left 8/22/24
TRUMBULL AVE | 3606 | TRUMBULL AVE | 46-35-385-005 | No restoration work needed; door hanger left 10/14/24
TRUMBULL AVE | 3813 | TRUMBULL AVE | 46-35-379-022 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
TRUMBULL AVE | 4212 | TRUMBULL AVE | 46-35-331-004 | No restoration work needed; door hanger left 8/22/24
TULANE CIR | 1514 | TULANE CIR | 41-07-117-018 | Completed | 2024-08-27 | 2024-10-21 | 2024-08-27 | 2024-08-27 | 2024-10-21 | 2024-10-21
TYRONE ST | 2532 | TYRONE ST | 40-11-377-029 | No restoration work needed; door hanger left 9/4/24
VERMILYA AVE | 715 | VERMILYA AVE | 41-19-378-012 | No restoration work needed; door hanger left 9/4/24
VERMILYA AVE | 1326 | VERMILYA AVE | 40-24-476-018 | No restoration work needed; door hanger left 9/4/24
VICTORIA AVE | 705 | VICTORIA AVE | 41-19-334-017 | No restoration work needed; door hanger left 8/26/24
VICTORIA AVE | 1019 | VICTORIA AVE | 40-24-430-014 | No restoration work needed; door hanger left 8/26/24
VICTORIA AVE | 1034 | VICTORIA AVE | 40-24-429-032 | No restoration work needed; door hanger left 8/26/24
VICTORIA AVE | 1136 | VICTORIA AVE | 40-24-429-020 | No restoration work needed; door hanger left 8/26/24
VINCENT AVE | 902 | VINCENT AVE | 40-12-309-005 | No restoration work needed; door hanger left 8/26/24
VOSBURG ST | 916 | VOSBURG ST | 40-14-476-031 | No restoration work needed; door hanger left 8/26/24
VOSBURG ST | 917 | VOSBURG ST | 40-14-480-004 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W ALMA AVE | 501 | W ALMA AVE | 46-25-108-007 | No restoration work needed; door hanger left 11/6/24
W ALMA AVE | 514 | W ALMA AVE | 46-25-106-015 | No restoration work needed; door hanger left 8/26/24
W AUSTIN AVE | 401 | W AUSTIN AVE | 46-25-158-016 | No restoration work needed; door hanger left 8/26/24
W BAKER ST | 426 | W BAKER ST | 40-01-158-005 | No restoration work needed; door hanger left 8/26/24
W BAKER ST | 515 | W BAKER ST | 40-01-159-009 | No restoration work needed; door hanger left 9/17/24
W BAKER ST | 609 | W BAKER ST | 40-01-159-003 | No restoration work needed; door hanger left 10/14/24
W BALTIMORE BLVD | 909 | W BALTIMORE BLVD | 46-35-277-003 | Completed | 2024-10-09 | 2024-10-09 |  |  | 2024-10-09 | 2024-10-09
W BISHOP AVE | 317 | W BISHOP AVE | 46-36-177-013 | No restoration work needed; door hanger left 8/26/24
W BISHOP AVE | 525 | W BISHOP AVE | 46-36-152-044 | No restoration work needed; door hanger left 8/26/24
W BUNDY AVE | 202 | W BUNDY AVE | 46-25-126-022 | Completed | 2024-11-05 | 2024-11-16 | 2024-11-05 | 2024-11-16 | 2024-11-08 | 2024-11-08
W BUNDY AVE | 305 | W BUNDY AVE | 46-25-126-030 | No restoration work needed; door hanger left 8/26/24
W BUNDY AVE | 613 | W BUNDY AVE | 46-25-103-010 | No restoration work needed; door hanger left 8/26/24
W BUNDY AVE | 633 | W BUNDY AVE | 46-25-103-005 | Completed | 2024-10-30 | 2024-10-30 |  |  | 2024-10-30 | 2024-10-30
W BUNDY AVE | 637 | W BUNDY AVE | 46-25-103-003 | No restoration work needed; door hanger left 8/26/24
W CARPENTER RD | 301 | W CARPENTER RD | 46-25-126-012 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Not needed
W CARPENTER RD | 325 | W CARPENTER RD | 46-25-126-064 | Completed | 2024-08-27 | 2024-10-01 | 2024-08-27 | 2024-08-29 | 2024-10-01 | 2024-10-01
W CARPENTER RD | 1001 | W CARPENTER RD | 46-26-227-028 | Completed | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25
W CARPENTER RD | 1735 | W CARPENTER RD | 46-26-126-044 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W COURT ST | 608 | W COURT ST | 40-13-286-041 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1533 | W COURT ST | 40-13-376-008 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1605 | W COURT ST | 40-13-376-007 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 1631 | W COURT ST | 40-13-376-001 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 1632 | W COURT ST | 40-13-328-045 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 1701 | W COURT ST | 40-13-364-004 | Completed | 2024-08-28 | 2024-11-01 | 2024-08-28 | 2024-08-28 | 2024-11-01 | 2024-11-01
W COURT ST | 1715 | W COURT ST | 40-13-364-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 1936 | W COURT ST | 40-13-302-004 | No restoration work needed; door hanger left 8/21/24
W COURT ST | 2020 | W COURT ST | 40-14-429-014 | Completed | 2024-09-25 | 2024-10-04 | 2024-09-25 | 2024-09-30 | 2024-10-04 | 2024-10-04
W COURT ST | 2201 | W COURT ST | 40-14-476-016 | Completed | 2023-10-24 | 2023-12-05 | 2023-10-24 | 2023-12-05 | Turf established
W COURT ST | 2455 | W COURT ST | 40-14-453-011 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2477 | W COURT ST | 40-14-453-013 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2489 | W COURT ST | 40-14-453-003 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2493 | W COURT ST | 40-14-453-002 | Completed | 2024-08-29 | 2024-09-18 | 2024-08-29 | 2024-09-17 | 2024-09-18 | 2024-09-18
W COURT ST | 2605 | W COURT ST | 40-14-451-015 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2609 | W COURT ST | 40-14-451-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 2663 | W COURT ST | 40-14-381-002 | Completed | 2024-08-28 | 2024-10-07 | 2024-08-28 | 2024-08-28 | 2024-10-07 | 2024-10-07
W COURT ST | 3009 | W COURT ST | 40-14-356-003 | Completed | 2024-08-29 | 2024-10-07 | 2024-08-29 | 2024-08-29 | 2024-10-07 | 2024-10-07
W COURT ST | 3017 | W COURT ST | 40-14-356-001 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-17 | 2024-09-18 | 2024-09-18
W COURT ST | 3106 | W COURT ST | 40-14-307-047 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3118 | W COURT ST | 40-14-307-053 | No restoration work needed; door hanger left 8/21/24
W COURT ST | 3205 | W COURT ST | 40-14-354-004 | Completed | 2024-08-29 | 2024-10-04 | 2024-08-29 | 2024-08-29 | 2024-10-04 | 2024-10-04
W COURT ST | 3208 | W COURT ST | 40-14-307-039 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3209 | W COURT ST | 40-14-354-003 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3610 | W COURT ST | 40-15-435-013 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3614 | W COURT ST | 40-15-435-012 | Completed | 2024-08-28 | 2024-10-04 | 2024-08-28 | 2024-08-28 | 2024-10-04 | 2024-10-04
W COURT ST | 3702 | W COURT ST | 40-15-435-011 | Completed | 2024-08-29 | 2024-10-04 | 2024-08-29 | 2024-08-29 | 2024-10-04 | 2024-10-04
W COURT ST | 3802 | W COURT ST | 40-15-434-029 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W COURT ST | 3810 | W COURT ST | 40-15-434-027 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W COURT ST | 3822 | W COURT ST | 40-15-434-023 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
W COURT ST | 4018 | W COURT ST | 40-15-433-010 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
W DARTMOUTH ST | 312 | W DARTMOUTH ST | 40-01-152-029 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W DARTMOUTH ST | 401 | W DARTMOUTH ST | 40-01-153-011 | No restoration work needed; door hanger left 8/31/24
W DARTMOUTH ST | 426 | W DARTMOUTH ST | 40-01-152-018 | Completed | 2024-09-09 | 2024-10-21 | 2024-09-09 | 2024-09-09 | 2024-10-21 | 2024-10-21
W DARTMOUTH ST | 722 | W DARTMOUTH ST | 40-02-277-023 | No restoration work needed; door hanger left 10/14/24 | Hard surface information originally noted on wrong address. |  | 2024-09-09 | 2024-09-09
W DARTMOUTH ST | 1106 | W DARTMOUTH ST | 40-02-208-007 | Completed | 2024-09-09 | 2024-09-18 | 2024-09-09 | 2024-09-17 | 2024-09-18 | 2024-09-18
W DARTMOUTH ST | 1514 | W DARTMOUTH ST | 40-02-132-027 | No restoration work needed; door hanger left 8/27/24
W DARTMOUTH ST | 1533 | W DARTMOUTH ST | 40-02-177-006 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-29 | 2024-10-02 | 2024-10-02
W DARTMOUTH ST | 1701 | W DARTMOUTH ST | 40-02-176-017 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-29 | 2024-10-02 | 2024-10-02
W DARTMOUTH ST | 1707 | W DARTMOUTH ST | 40-02-176-016 | No restoration work needed; door hanger left 8/31/24
W DARTMOUTH ST | 1819 | W DARTMOUTH ST | 40-02-176-007 | No restoration work needed; door hanger left 8/27/24
W DAYTON ST | 319 | W DAYTON ST | 40-01-304-014 | Completed | 2024-09-24 | 2024-09-30 | 2024-09-24 | 2024-09-30 | Not needed
W DAYTON ST | 721 | W DAYTON ST | 40-02-429-001 | No restoration work needed; door hanger left 8/26/24
W DAYTON ST | 1808 | W DAYTON ST | 40-02-179-033 | No restoration work needed; door hanger left 8/31/24
W DAYTON ST | 2015 | W DAYTON ST | 40-02-327-001 | No restoration work needed; door hanger left 8/15/24
W DAYTON ST | 2108 | W DAYTON ST | 40-02-305-002 | Completed | 2024-09-25 | 2024-09-30 | 2024-09-25 | 2024-09-30 | Not needed
W DAYTON ST | 2114 | W DAYTON ST | 40-02-305-001 | No restoration work needed; door hanger left 8/26/24
W DAYTON ST | 2214 | W DAYTON ST | 40-02-304-001 | No restoration work needed; door hanger left 8/26/24
W DEWEY ST | 200 | W DEWEY ST | 40-01-126-025 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W DEWEY ST | 205 | W DEWEY ST | 40-01-127-007 | No restoration work needed; door hanger left 8/31/24
W DEWEY ST | 220 | W DEWEY ST | 40-01-126-018 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W DEWEY ST | 221 | W DEWEY ST | 40-01-127-003 | No restoration work needed; door hanger left 8/27/24
W DEWEY ST | 406 | W DEWEY ST | 40-01-102-022 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W DEWEY ST | 409 | W DEWEY ST | 40-01-104-011 | Completed | 2024-07-25 | 2024-07-31 | 2024-07-25 | 2024-07-29 | 2024-07-31 | 2024-07-31
W FIFTH AVE | 427 | W FIFTH AVE | 40-12-453-018 | No restoration work needed; door hanger left 8/15/24
W FIFTH ST | 407 | W FIFTH ST | 41-18-307-005 | No restoration work needed; door hanger left 8/27/24
W FIFTH ST | 512 | W FIFTH ST | 41-18-301-011 | No restoration work needed; door hanger left 8/15/24
W FIFTH ST | 514 | W FIFTH ST | 41-18-301-010 | Completed | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | Not needed
W FLINT PARK BLVD | 633 | W FLINT PARK BLVD | 46-36-153-003 | Completed | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25 | Not needed
W FOSS AVE | 306 | W FOSS AVE | 46-25-132-021 | Completed | 2024-08-26 | 2024-10-01 | 2024-08-26 | 2024-08-28 | 2024-10-01 | 2024-10-01
W GENESEE ST | 132 | W GENESEE ST | 40-01-129-026 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
W GENESEE ST | 916 | W GENESEE ST | 40-02-233-017 | No restoration work needed; door hanger left 8/27/24
W GENESEE ST | 1402 | W GENESEE ST | 40-02-130-025 | No restoration work needed; door hanger left 8/31/24
W GENESEE ST | 1508 | W GENESEE ST | 40-02-130-022 | Completed | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | Not needed
W GENESEE ST | 1512 | W GENESEE ST | 40-02-130-021 | No restoration work needed; door hanger left 8/28/24
W GENESEE ST | 1902 | W GENESEE ST | 40-02-129-017 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W GENESEE ST | 1914 | W GENESEE ST | 40-02-129-014 | No restoration work needed; door hanger left 8/31/24
W GRACELAWN AVE | 211 | W GRACELAWN AVE | 46-25-303-038 | Completed | 2024-08-26 | 2024-10-02 | 2024-08-26 | 2024-08-28 | 2024-10-02 | 2024-10-02
W GRACELAWN AVE | 606 | W GRACELAWN AVE | 46-25-302-043 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-29 | 2024-10-21 | 2024-10-21
W HAMILTON AVE | 121 | W HAMILTON AVE | 40-01-331-013 | No restoration work needed; door hanger left 8/31/24
W HAMILTON AVE | 136 | W HAMILTON AVE | 40-01-330-031 | No restoration work needed; door hanger left 10/14/24
W HAMILTON AVE | 519 | W HAMILTON AVE | 40-01-311-009 | Completed | 2024-09-24 | 2024-10-21 | 2024-09-24 | 2024-09-24 | 2024-10-21 | 2024-10-21
W HAMILTON AVE | 1202 | W HAMILTON AVE | 40-02-404-045 | No restoration work needed; door hanger left 8/15/24
W HOME AVE | 634 | W HOME AVE | 46-25-301-011 | No restoration work needed; door hanger left 8/27/24
W HOME AVE | 1502 | W HOME AVE | 46-26-401-006 | Completed | 2024-08-26 | 2024-10-08 | 2024-08-26 | 2024-08-29 | 2024-10-08 | 2024-10-08
W JACKSON AVE | 715 | W JACKSON AVE | 40-02-280-003 | No restoration work needed; door hanger left 8/28/24
W JACKSON AVE | 1802 | W JACKSON AVE | 40-02-176-024 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W JACKSON AVE | 1826 | W JACKSON AVE | 40-02-176-020 | No restoration work needed; door hanger left 8/31/24
W KEARSLEY ST | 3909 | W KEARSLEY ST | 40-15-432-008 | Completed | 2024-09-25 | 2024-10-04 | 2024-09-25 | 2024-09-25 | 2024-10-04 | 2024-10-04
W LORADO AVE | 509 | W LORADO AVE | 46-25-154-005 | Completed | 2024-08-28 | 2024-10-01 | 2024-08-28 | 2024-08-28 | 2024-10-01 | 2024-10-01
W LORADO AVE | 518 | W LORADO AVE | 46-25-152-017 | No restoration work needed; door hanger left 8/27/24
W MARENGO AVE | 414 | W MARENGO AVE | 46-36-127-028 | No restoration work needed; door hanger left 8/27/24
W MARENGO AVE | 520 | W MARENGO AVE | 46-36-102-048 | No restoration work needed; door hanger left 9/16/24
W MARENGO AVE | 549 | W MARENGO AVE | 46-36-103-013 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W MARENGO AVE | 809 | W MARENGO AVE | 46-35-234-004 | No restoration work needed; door hanger left 8/27/24
W MARENGO AVE | 901 | W MARENGO AVE | 46-35-233-005 | No restoration work needed; door hanger left 8/27/24
W MC CLELLAN ST | 129 | W MC CLELLAN ST | 40-01-129-011 | Completed | 2024-08-26 | 2024-10-03 | 2024-08-26 | 2024-08-28 | 2024-10-03 | 2024-10-03
W MC CLELLAN ST | 132 | W MC CLELLAN ST | 40-01-128-024 | No restoration work needed; door hanger left 8/31/24
W MC CLELLAN ST | 315 | W MC CLELLAN ST | 40-01-108-013 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W MC CLELLAN ST | 747 | W MC CLELLAN ST | 40-02-234-009 | No restoration work needed; door hanger left 8/31/24
W MOORE ST | 1210 | W MOORE ST | 46-35-402-002 | No restoration work needed; door hanger left 8/26/24
W MOTT AVE | 1108 | W MOTT AVE | 46-26-407-022 | No restoration work needed; door hanger left 8/26/24
W MOTT AVE | 1510 | W MOTT AVE | 46-26-403-042 | Completed | 2024-09-25 | 2024-10-08 | 2024-09-25 | 2024-09-30 | 2024-10-08 | 2024-10-08
W PASADENA AVE | 519 | W PASADENA AVE | 40-01-101-013 | No restoration work needed; door hanger left 8/31/24
W PASADENA AVE | 1402 | W PASADENA AVE | 46-35-457-037 | No restoration work needed; door hanger left 8/28/24
W PASADENA AVE | 1414 | W PASADENA AVE | 46-35-457-035 | Completed | 2024-10-25 | 2024-11-16 | 2024-10-25 | 2024-11-16 | Not needed
W PASADENA AVE | 1717 | W PASADENA AVE | 40-02-126-013 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PASADENA AVE | 1801 | W PASADENA AVE | 40-02-126-012 | No restoration work needed; door hanger left 8/27/24
W PASADENA AVE | 1909 | W PASADENA AVE | 40-02-126-004 | No restoration work needed; door hanger left 8/27/24
W PASADENA AVE | 1918 | W PASADENA AVE | 46-35-382-032 | No restoration work needed; door hanger left 8/27/24
W PASADENA AVE | 2017 | W PASADENA AVE | 40-02-105-001 | No restoration work needed; door hanger left 8/27/24
W PATERSON ST | 112 | W PATERSON ST | 40-01-378-036 | No restoration work needed; door hanger left 8/31/24
W PATERSON ST | 228 | W PATERSON ST | 40-01-378-021 | No restoration work needed; door hanger left 9/3/24
W PATERSON ST | 426 | W PATERSON ST | 40-01-356-017 | Completed | 2024-09-11 | 2024-09-17 | 2024-09-11 | 2024-09-17
W PATERSON ST | 511 | W PATERSON ST | 40-01-357-013 | No restoration work needed; door hanger left 10/15/24
W PATERSON ST | 909 | W PATERSON ST | 40-02-481-013 | No restoration work needed; door hanger left 8/31/24
W PATERSON ST | 1311 | W PATERSON ST | 40-02-455-003 | No restoration work needed; door hanger left 8/15/24
W PATERSON ST | 1318 | W PATERSON ST | 40-02-451-023 | No restoration work needed; door hanger left 8/31/24
W PATERSON ST | 1410 | W PATERSON ST | 40-02-451-017 | Completed | 2024-08-26 | 2024-10-07 | 2024-08-26 | 2024-08-29 | 2024-10-07 | 2024-10-07
W PATERSON ST | 1530 | W PATERSON ST | 40-02-377-013 | Completed | 2024-09-11 | 2024-10-07 | 2024-09-11 | 2024-09-11 | 2024-10-07 | 2024-10-07
W PHILADELPHIA BLV | 105 | W PHILADELPHIA BLV | 46-36-129-023 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PHILADELPHIA BLV | 127 | W PHILADELPHIA BLV | 46-36-129-019 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PIERSON RD | 624 | W PIERSON RD | 46-25-355-018 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W PIERSON RD | 812 | W PIERSON RD | 46-26-481-023 | No restoration work needed; door hanger left 8/7/24
W PIERSON RD | 902 | W PIERSON RD | 46-26-481-020 | No restoration work needed; door hanger left 8/26/24
W PIERSON RD | 1109 | W PIERSON RD | 46-35-226-002 | Completed | 2024-10-30 | 2024-10-30 |  |  | 2024-10-30 | 2024-10-30
W PIERSON RD | 1206 | W PIERSON RD | 46-26-455-032 | No restoration work needed; door hanger left 8/31/24
W PIERSON RD | 1310 | W PIERSON RD | 46-26-455-027 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
W PIPER AVE | 221 | W PIPER AVE | 46-25-328-003 | Completed | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Not needed
W RANKIN ST | 418 | W RANKIN ST | 40-01-156-016 | Completed | 2024-08-26 | 2024-10-03 | 2024-08-26 | 2024-08-28 | 2024-10-03 | 2024-10-03
W RANKIN ST | 701 | W RANKIN ST | 40-02-284-007 | No restoration work needed; door hanger left 8/27/24
W RIDGEWAY AVE | 624 | W RIDGEWAY AVE | 46-25-354-011 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W RUSSELL AVE | 521 | W RUSSELL AVE | 46-25-159-002 | No restoration work needed; door hanger left 8/27/24
W RUTH AVE | 609 | W RUTH AVE | 46-25-155-011 | No restoration work needed; door hanger left 8/27/24
W SECOND ST | 1421 | W SECOND ST | 40-13-330-008 | Completed | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2024-07-31 | 2024-08-09 | 2024-08-09
W SIXTH ST | 403 | W SIXTH ST | 41-18-308-029 | No restoration work needed; door hanger left 8/31/24
W SIXTH ST | 512 | W SIXTH ST | 41-18-306-022 | No restoration work needed; door hanger left 8/15/24
W STEWART AVE | 117 | W STEWART AVE | 46-36-180-027 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W STEWART AVE | 121 | W STEWART AVE | 46-36-180-026 | Completed | 2024-10-02 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02
W STEWART AVE | 217 | W STEWART AVE | 46-36-180-021 | No restoration work needed; door hanger left 8/27/24
W STEWART AVE | 218 | W STEWART AVE | 46-36-179-053 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 222 | W STEWART AVE | 46-36-179-052 | No restoration work needed; door hanger left 8/27/24
W STEWART AVE | 325 | W STEWART AVE | 46-36-180-011 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 401 | W STEWART AVE | 46-36-180-009 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 402 | W STEWART AVE | 46-36-179-041 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 410 | W STEWART AVE | 46-36-179-040 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 511 | W STEWART AVE | 46-36-155-015 | No restoration work needed; door hanger left 8/27/24
W STEWART AVE | 516 | W STEWART AVE | 46-36-154-043 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 525 | W STEWART AVE | 46-36-155-013 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 541 | W STEWART AVE | 46-36-155-011 | No restoration work needed; door hanger left 8/27/24
W STEWART AVE | 542 | W STEWART AVE | 46-36-154-038 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 602 | W STEWART AVE | 46-36-154-035 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 614 | W STEWART AVE | 46-36-154-032 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 817 | W STEWART AVE | 46-35-282-004 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 833 | W STEWART AVE | 46-35-281-022 | No restoration work needed; door hanger left 8/26/24
W STEWART AVE | 841 | W STEWART AVE | 46-35-281-024 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 845 | W STEWART AVE | 46-35-281-025 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1208 | W STEWART AVE | 46-35-255-044 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1209 | W STEWART AVE | 46-35-257-003 | No restoration work needed; door hanger left 8/26/24
W STEWART AVE | 1301 | W STEWART AVE | 46-35-256-017 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1309 | W STEWART AVE | 46-35-256-016 | Completed | 2024-10-03 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-03
W STEWART AVE | 1317 | W STEWART AVE | 46-35-256-013 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1419 | W STEWART AVE | 46-35-256-008 | Completed | 2024-09-25 | 2024-10-03 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
W STEWART AVE | 1510 | W STEWART AVE | 46-35-255-027 | No restoration work needed; door hanger left 8/31/24
W STEWART AVE | 1922 | W STEWART AVE | 46-35-155-056 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2002 | W STEWART AVE | 46-35-155-052 | No restoration work needed; door hanger left 8/26/24
W STEWART AVE | 2010 | W STEWART AVE | 46-35-155-050 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2014 | W STEWART AVE | 46-35-155-049 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2213 | W STEWART AVE | 46-35-158-001 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W STEWART AVE | 2218 | W STEWART AVE | 46-35-155-035 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
W THIRD ST A | 418 | W THIRD ST A | 40-13-285-011 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-17 | 2024-09-18 | 2024-09-18
W THIRD ST B | 418 | W THIRD ST B | 40-13-285-011 | Completed | 2024-09-11 | 2024-09-18 | 2024-09-11 | 2024-09-17 | 2024-09-18 | 2024-09-18
W TWELFTH ST | 210 | W TWELFTH ST | 41-18-451-062 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-27 | 2024-10-21 | 2024-10-21
W TWELFTH ST | 421 | W TWELFTH ST | 41-18-384-005 | Completed | 2023-11-14 | 2024-07-25 | 2023-11-14 | 2023-12-14 | 2024-07-25 | 2024-07-25
W TWELFTH ST | 1025 | W TWELFTH ST | 40-24-231-007 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-27 | 2024-10-21 | 2024-10-21
W TWELFTH ST | 1029 | W TWELFTH ST | 40-24-231-006 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-27 | 2024-10-21 | 2024-10-21
W UNIVERSITY AVE | 1202 | W UNIVERSITY AVE | 40-13-126-019 | Completed | 2024-09-09 | 2024-09-18 | 2024-09-09 | 2024-09-09 | 2024-09-18 | 2024-09-18
W UNIVERSITY AVE | 1204 | W UNIVERSITY AVE | 40-13-126-018 | No restoration work needed; door hanger left 8/27/24
W VAN WAGONER AVE | 213 | W VAN WAGONER AVE | 46-36-379-004 | No restoration work needed; door hanger left 8/26/24
W WITHERBEE ST | 210 | W WITHERBEE ST | 40-01-331-024 | Completed | 2024-08-26 | 2024-10-04 | 2024-08-26 | 2024-08-28 | 2024-10-04 | 2024-10-04
W WITHERBEE ST | 524 | W WITHERBEE ST | 40-01-311-019 | Completed | 2024-09-24 | 2024-10-03 | 2024-09-24 | 2024-09-30 | 2024-10-03 | 2024-10-03
W WITHERBEE ST | 618 | W WITHERBEE ST | 40-01-311-014 | Completed | 2024-07-17 | 2024-07-17 |  |  | 2024-07-17 | 2024-07-17
W WITHERBEE ST | 623 | W WITHERBEE ST | 40-01-351-001 | No restoration work needed; door hanger left 8/15/24
W YORK AVE | 112 | W YORK AVE | 46-25-126-044 | Completed | 2024-08-26 | 2024-10-01 | 2024-08-26 | 2024-08-30 | 2024-10-01 | 2024-10-01
W YORK AVE | 305 | W YORK AVE | 46-25-128-005 | No restoration work needed; door hanger left 8/27/24
WALDMAN AVE | 720 | WALDMAN AVE | 41-19-382-024 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-27 | 2024-10-21 | 2024-10-21
WALKER ST | 1207 | WALKER ST | 41-18-354-015 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-17 | 2024-09-18 | 2024-09-18
WALTER ST | 2601 | WALTER ST | 40-02-178-030 | No restoration work needed; door hanger left 8/31/24
WALTER ST | 2714 | WALTER ST | 40-02-179-003 | Completed | 2024-09-09 | 2024-09-18 | 2024-09-09 | 2024-09-17 | 2024-09-18 | 2024-09-18
WARRINGTON DR | 4618 | WARRINGTON DR | 46-35-178-068 | Completed | 2024-08-29 | 2024-10-08 | 2024-08-29 | 2024-08-29 | 2024-10-08 | 2024-10-08
WASHINGTON AVE | 1317 | WASHINGTON AVE | 41-07-232-001 | No restoration work needed; door hanger left 8/26/24
WASHINGTON AVE | 1320 | WASHINGTON AVE | 41-07-277-011 | Completed | 2024-09-10 | 2024-10-01 | 2024-09-10 | 2024-09-10 | 2024-10-01 | 2024-10-01
WASHINGTON AVE | 1376 | WASHINGTON AVE | 41-07-278-011 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-16 | 2024-09-18 | 2024-09-18
WEAVER ST | 1911 | WEAVER ST | 47-32-451-019 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-16 | 2024-09-18 | 2024-09-18
WEAVER ST | 2007 | WEAVER ST | 47-32-451-023 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-16 | 2024-09-18 | 2024-09-18
WEBSTER RD | 6920 | WEBSTER RD | 47-29-201-010 | Completed | 2024-09-25 | 2024-10-01 | 2024-09-25 | 2024-09-25 | 2024-10-01 | 2024-10-01
WELCH BLVD | 112 | WELCH BLVD | 40-12-126-030 | Completed | 2024-10-04 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-04
WELCH BLVD | 116 | WELCH BLVD | 40-12-126-029 | No restoration work needed; door hanger left 8/28/24
WELCH BLVD | 201 | WELCH BLVD | 40-12-129-004 | No restoration work needed; door hanger left 8/28/24
WELCH BLVD | 307 | WELCH BLVD | 40-12-128-004 | No restoration work needed; door hanger left 8/26/24
WELCH BLVD | 509 | WELCH BLVD | 40-12-106-003 | No restoration work needed; door hanger left 8/26/24
WELCH BLVD | 552 | WELCH BLVD | 40-12-101-030 | Completed | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2024-08-07 | 2024-08-09 | 2024-08-09
WELCH BLVD | 557 | WELCH BLVD | 40-12-105-002 | No restoration work needed; door hanger left 8/26/24
WELCH BLVD | 565 | WELCH BLVD | 40-12-105-001 | No restoration work needed; door hanger left 8/27/24
WELCH BLVD | 913 | WELCH BLVD | 40-11-226-007 | Completed | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31
WELCH BLVD | 1419 | WELCH BLVD | 40-02-458-005 | No restoration work needed; door hanger left 8/27/24
WELCH BLVD | 1601 | WELCH BLVD | 40-02-378-013 | No restoration work needed; door hanger left 8/27/24
WELCH BLVD | 2133 | WELCH BLVD | 40-02-310-009 | No restoration work needed; door hanger left 8/31/24
WELCH BLVD | 2213 | WELCH BLVD | 40-02-310-005 | No restoration work needed; door hanger left 8/27/24
WELCH BLVD | 2331 | WELCH BLVD | 40-02-306-010 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WELCH BLVD | 2402 | WELCH BLVD | 40-02-307-014 | Completed | 2024-07-30 | 2024-08-09 | 2024-07-30 | 2024-08-07 | 2024-08-09 | 2024-08-09
WELLER ST | 611 | WELLER ST | 40-11-379-010 | No restoration work needed; door hanger left 10/15/24 | Hard surface information originally noted on wrong address. |  | 2024-09-18 | 2024-09-18
WESLEY ST | 3506 | WESLEY ST | 46-36-460-007 | No restoration work needed; door hanger left 8/31/24
WESLEY ST | 3510 | WESLEY ST | 46-36-460-006 | No restoration work needed; door hanger left 8/27/24
WESTCOMBE AVE | 324 | WESTCOMBE AVE | 40-14-153-014 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WESTCOMBE AVE | 332 | WESTCOMBE AVE | 40-14-153-015 | No restoration work needed; door hanger left 8/31/24
WESTCOMBE AVE | 343 | WESTCOMBE AVE | 40-14-176-010 | Completed | 2024-09-11 | 2024-09-17 | 2024-09-11 | 2024-09-18 | 2024-09-18
WESTCOMBE AVE | 402 | WESTCOMBE AVE | 40-14-154-021 | No restoration work; resident declined to have restoration performed 10/7/24
WESTCOMBE AVE | 412 | WESTCOMBE AVE | 40-14-154-023 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-10-04 | 2024-10-04 | 2024-10-04
WESTCOMBE AVE | 417 | WESTCOMBE AVE | 40-14-159-002 | Completed | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | Not needed
WESTCOMBE AVE | 460 | WESTCOMBE AVE | 40-14-156-017 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-09-11 | 2024-10-04 | 2024-10-04
WESTCOMBE AVE | 713 | WESTCOMBE AVE | 40-14-301-004 | No restoration work needed; door hanger left 8/31/24
WESTERN RD | 4801 | WESTERN RD | 47-32-230-037 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WESTWOOD PKWY | 2641 | WESTWOOD PKWY | 40-23-256-014 | No restoration work needed; door hanger left 8/26/24
WHITINGHAM DR | 1001 | WHITINGHAM DR | 41-16-228-033 | No restoration work needed; door hanger left 8/15/24
WHITINGHAM DR | 1108 | WHITINGHAM DR | 41-16-229-028 | Completed | 2024-08-26 | 2024-09-18 | 2024-08-26 | 2024-08-27 | 2024-09-18 | 2024-09-18
WHITNEY AVE | 3150 | WHITNEY AVE | 07-22-502-257 | No restoration work needed; door hanger left 7/29/24
WHITNEY AVE | 3155 | WHITNEY AVE | 07-22-502-289 | No restoration work needed; door hanger left 8/26/24
WHITNEY AVE | 3613 | WHITNEY AVE | 40-22-233-009 | Completed | 2024-08-30 | 2024-10-04 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04
WHITTIER ST | 3125 | WHITTIER ST | 41-04-334-022 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3746 | WHITTIER ST | 41-04-476-013 | No restoration work needed; door hanger left 8/26/24
WHITTIER ST | 3809 | WHITTIER ST | 41-04-434-015 | No restoration work needed; door hanger left 8/26/24
WHITTIER ST | 3822 | WHITTIER ST | 41-04-476-021 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3829 | WHITTIER ST | 41-04-434-020 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTIER ST | 3837 | WHITTIER ST | 41-04-434-022 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WHITTLESEY ST | 1835 | WHITTLESEY ST | 41-17-427-012 | Completed | 2024-08-27 | 2024-09-18 | 2024-08-27 | 2024-08-29 | 2024-09-18 | 2024-09-18
WHITTLESEY ST | 1851 | WHITTLESEY ST | 41-17-427-017 | Completed | 2024-08-29 | 2024-09-18 | 2024-08-29 | 2024-08-29 | 2024-09-18 | 2024-09-18
WHITTLESEY ST | 2006 | WHITTLESEY ST | 41-17-458-016 | Completed | 2024-09-18 | 2024-09-18 |  |  | 2024-09-18 | 2024-09-18
WHITTLESEY ST | 2026 | WHITTLESEY ST | 41-17-458-021 | No restoration work needed; door hanger left 8/26/24
WILBERFORCE DR | 716 | WILBERFORCE DR | 41-07-114-005 | Completed | 2024-08-26 | 2024-10-04 | 2024-08-26 | 2024-08-27 | 2024-10-04 | 2024-10-04
WILBERFORCE LN | 701 | WILBERFORCE LN | 41-07-112-007 | No restoration work needed; door hanger left 8/26/24
WILTON PL | 2702 | WILTON PL | 47-29-476-005 | Completed | 2024-09-11 | 2024-10-01 | 2024-09-11 | 2024-09-11 | 2024-10-01 | 2024-10-01
WINANS AVE | 2016 | WINANS AVE | 41-17-378-021 | No restoration work needed; door hanger left 8/31/24
WINANS AVE | 2026 | WINANS AVE | 41-17-378-024 | No restoration work needed; door hanger left 8/26/24
WINANS AVE | 2113 | WINANS AVE | 41-20-130-006 | Completed | 2024-09-11 | 2024-09-17 | 2024-09-11 | 2024-09-17
WINDEMERE AVE | 2207 | WINDEMERE AVE | 41-08-455-028 | No restoration work needed; door hanger left 8/26/24
WINDEMERE AVE | 2211 | WINDEMERE AVE | 41-08-455-029 | No restoration work needed; door hanger left 8/26/24
WINDEMERE AVE | 2407 | WINDEMERE AVE | 41-08-477-029 | No restoration work needed; door hanger left 8/26/24
WINDEMERE AVE | 2411 | WINDEMERE AVE | 41-08-477-030 | No restoration work needed; door hanger left 8/26/24
WINDEMERE AVE | 2605 | WINDEMERE AVE | 41-08-479-030 | No restoration work needed; door hanger left 8/26/24
WINDEMERE AVE | 2618 | WINDEMERE AVE | 41-08-482-011 | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | Not needed
WINDEMERE AVE | 2622 | WINDEMERE AVE | 41-08-482-012 | No restoration work needed; door hanger left 8/26/24
WINDSOR LN | 1820 | WINDSOR LN | 40-25-104-035 | No restoration work needed; door hanger left 9/16/24
WINDSOR LN | 1830 | WINDSOR LN | 40-25-104-032 | Completed | 2024-08-27 | 2024-10-21 | 2024-08-27 | 2024-08-30 | 2024-10-21 | 2024-10-21
WINONA ST | 2408 | WINONA ST | 40-02-327-006 | No restoration work needed; door hanger left 8/27/24
WINONA ST | 3008 | WINONA ST | 40-02-111-001 | No restoration work needed; door hanger left 8/21/24
WINONA ST | 3419 | WINONA ST | 46-35-360-031 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 3505 | WINONA ST | 46-35-360-029 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 3514 | WINONA ST | 46-35-381-009 | No restoration work needed; door hanger left 8/31/24
WINONA ST | 3521 | WINONA ST | 46-35-360-025 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 3609 | WINONA ST | 46-35-360-022 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 3809 | WINONA ST | 46-35-355-022 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 3905 | WINONA ST | 46-35-355-019 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 4120 | WINONA ST | 46-35-327-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WINONA ST | 4124 | WINONA ST | 46-35-327-002 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WINONA ST | 4128 | WINONA ST | 46-35-327-029 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WINONA ST | 4207 | WINONA ST | 46-35-305-012 | No restoration work needed; door hanger left 8/7/24
WINONA ST | 4232 | WINONA ST | 46-35-326-002 | No restoration work needed; door hanger left 8/7/24
WISCONSIN AVE | 1539 | WISCONSIN AVE | 41-08-106-031 | Completed | 2024-09-10 | 2024-09-16 | 2024-09-10 | 2024-09-16 | Not needed
WISCONSIN AVE | 2128 | WISCONSIN AVE | 41-08-208-030 | No restoration work needed; door hanger left 8/27/24
WISCONSIN AVE | 2314 | WISCONSIN AVE | 41-08-210-013 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WISNER ST | 3105 | WISNER ST | 40-02-107-028 | Completed | 2024-09-24 | 2024-10-02 | 2024-09-24 | 2024-09-24 | 2024-10-02 | 2024-10-02
WISNER ST | 3821 | WISNER ST | 46-35-352-023 | No restoration work needed; door hanger left 8/15/24
WISNER ST | 4235 | WISNER ST | 46-35-156-003 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WISNER ST | 4605 | WISNER ST | 46-35-152-010 | No restoration work needed; door hanger left 8/26/24
WOLCOTT ST | 2526 | WOLCOTT ST | 40-11-255-030 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 2741 | WOLCOTT ST | 40-11-178-009 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 2953 | WOLCOTT ST | 40-11-111-002 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOLCOTT ST | 3201 | WOLCOTT ST | 40-10-231-011 | Completed | 2024-08-29 | 2024-10-21 | 2024-08-29 | 2024-08-29 | 2024-10-21 | 2024-10-21
WOODBRIDGE ST | 1342 | WOODBRIDGE ST | 40-11-427-030 | Completed | 2024-10-07 | 2024-10-07 |  |  | 2024-10-07 | 2024-10-07
WOODCROFT AVE | 1415 | WOODCROFT AVE | 40-23-233-003 | Completed | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | Not needed
WOODHALL DR | 1402 | WOODHALL DR | 46-35-252-033 | Completed | 2024-08-26 | 2024-10-21 | 2024-08-26 | 2024-08-28 | 2024-10-21 | 2024-10-21
WOODHALL DR | 1418 | WOODHALL DR | 46-35-252-029 | Completed | 2024-09-24 | 2024-10-08 | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08
WOODLIN DR | 1714 | WOODLIN DR | 46-26-126-018 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WOODLIN DR | 1810 | WOODLIN DR | 46-26-126-037 | Completed | 2024-10-08 | 2024-10-08 |  |  | 2024-10-08 | 2024-10-08
WOODROW AVE | 2614 | WOODROW AVE | 41-05-478-003 | Completed | 2024-09-10 | 2024-09-16 | 2024-09-10 | 2024-09-16 | Not needed
WOODROW AVE | 3801 | WOODROW AVE | 41-04-432-013 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WOODSIDE DR | 914 | WOODSIDE DR | 41-17-102-012 | No restoration work needed; door hanger left 8/15/24
WOODSLEA DR | 1251 | WOODSLEA DR | 41-20-176-005 | Completed | 2024-09-18 | 2024-09-18 |  |  | 2024-09-18 | 2024-09-18
WOODSLEA DR | 1302 | WOODSLEA DR | 41-20-177-002 | No restoration work needed; door hanger left 8/15/24
WOODSLEA DR | 1809 | WOODSLEA DR | 41-20-276-006 | Completed | 2024-08-27 | 2024-10-01 | 2024-08-27 | 2024-09-23 | 2024-10-01 | 2024-10-01
WYOMING AVE | 1618 | WYOMING AVE | 41-05-130-004 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WYOMING AVE | 1654 | WYOMING AVE | 41-05-130-013 | No restoration work needed; door hanger left 8/31/24
WYOMING AVE | 1702 | WYOMING AVE | 41-05-131-001 | Completed | 2024-08-27 | 2024-09-18 | 2024-08-27 | 2024-09-16 | 2024-09-18 | 2024-09-18
WYOMING AVE | 1816 | WYOMING AVE | 41-05-131-015 | Completed | 2024-09-10 | 2024-09-18 | 2024-09-10 | 2024-09-16 | 2024-09-18 | 2024-09-18
WYOMING AVE | 3013 | WYOMING AVE | 41-04-102-035 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WYOMING AVE | 3130 | WYOMING AVE | 41-04-128-008 | Completed | 2024-10-01 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-01
WYOMING AVE | 3316 | WYOMING AVE | 41-04-204-004 | No restoration work needed; door hanger left 8/27/24
YALE ST | 3014 | YALE ST | 40-23-181-016 | No restoration work needed; door hanger left 8/27/24
YALE ST | 3017 | YALE ST | 40-23-183-002 | Completed | 2024-10-21 | 2024-10-21 |  |  | 2024-10-21 | 2024-10-21
YALE ST | 3018 | YALE ST | 40-23-181-015 | Completed | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-09-30 | 2024-10-04 | 2024-10-04
YALE ST | 3022 | YALE ST | 40-23-181-014 | Completed | 2024-10-28 | 2024-11-07 | 2024-10-28 | 2024-11-07 | 2024-10-31 | 2024-10-31
ZIMMERMAN ST | 1801 | ZIMMERMAN ST | 40-13-360-013 | Completed | 2024-09-11 | 2024-09-26 | 2024-09-11 | 2024-09-26 | Not needed
ZIMMERMAN ST | 2460 | ZIMMERMAN ST | 40-14-456-010 | No restoration work needed; door hanger left 8/27/24
ZIMMERMAN ST | 2488 | ZIMMERMAN ST | 40-14-456-003 | No restoration work needed; door hanger left 8/15/24
ZIMMERMAN ST | 3816 | ZIMMERMAN ST | 40-15-476-028 | Completed | 2024-09-11 | 2024-10-04 | 2024-09-11 | 2024-09-11 | 2024-10-04 | 2024-10-04
Priority homes
Note on E375: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously marked NWN
Note on E902: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contractor removed sidewalk not part of Fast Start; work at no cost to project
Note on G902: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contractor removed sidewalk not part of Fast Start; work at no cost to project
Note on E1363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Originally marked "NWN"
Note on E1518: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Originally marked as NWN